## MetaData (hidden)
Client Name | Fieldstone CDD
Project Name | Fort Hamer Road Extension Segment B

## PHASE 1
APPENDIX K, BID PRICING FORM (REVISED) Moccasin Wallow, I-75 - 301 Segment 1 from US 301 To 115th Avenue East (Copperstone Entrance) PROJECT #'s 6071261, 6113370, 611390 |  |  |  |  | EOC STANTEC
Bidders must provide prices for each available line item on each tab for their bid to be considered responsive.
ITEM # | FDOT ITEM NUMBER | BRIEF DESCRIPTION OF ITEMS | ESTIMATED QUANTITY | UNIT | UNIT PRICE | EXTENDED AMOUNT | UNIT PRICE BID A 450 Calendar Days | EXTENDED AMOUNT BID A | UNIT PRICE BID B 540 Calendar Days | EXTENDED AMOUNT BID B
1 |  | Mobilization | 1 | LS | 75000 | 75000
2 |  | 2" Conduit (Material & Install) | 2000 | LF | 5.5 | 11000
3 |  | 4" Conduit (Material & Install) | 2000 | LF | 9 | 18000
4 |  | 6" Conduit (Material & Install) | 2000 | LF | 15 | 30000
5 |  | Density Testing (By Owner) | 1 | LS | 0 | 0 |  |  |  |  | Delete Line
6 |  | Construction Stakeout | 1 | LS | 50000 | 50000
7 |  | Demolition, per plan - Includes any demo work that needs to be done prior to clearing, i.e. removal of pipe, conduit, structures, fencing, etc. not otherwise specified in Schedule of Values | 1 | LS | 10000 | 10000
8 |  | Temporary Emergency & Construction Entrance | 1 | LS | 2500 | 2500
9 |  | Maintenance of Traffic | 1 | LS | 75000 | 75000
10 |  | Clearing and Grubbing | 34 | AC | 3600 | 122400
11 |  | Finish Grading | 34 | AC | 3000 | 102000
12 |  | Excavation Lake 2B & 3 (Insitu Measure) (Note: these lakes have already been excavated by developer) | 117111.8667 | CY | 4 | 468447.4667
13 |  | Excavation Lake 1 (Insitu Measure) | 8292.5333 | CY | 4
14 |  | Place and compact (Compacted measure) | 66508 | CY | 3.5 | 232778
15 |  | Import Fill (Trucked Measure) | 88556 | CY | 10 | 885560
16 |  | Demucking | 5641 | CY | 5 | 28205 |  |  |  |  | Updated
17 |  | Sod | 39682 | SY | 2.25 | 89284.5
18 |  | Ditch re-grading (Width Varies) | 1 | LS | 10000 | 10000
19 |  | Inlet Protection | 29 | EA | 275 | 7975
20 |  | Turbidity Barrier | 212 | LF | 17 | 3604
21 |  | Double Silt Fence | 3489 | LF | 3 | 10467
22 |  | Silt Fence | 10932 | LF | 1.5 | 16398
23 |  | 18" RCP | 1920 | LF | 66 | 126720
24 |  | 24" RCP | 3476 | LF | 75 | 260700
25 |  | 30" RCP | 2646 | LF | 100 | 264600
26 |  | 36" RCP | 632 | LF | 140 | 88480
27 |  | 42" RCP | 66 | LF | 175 | 11550
28 |  | 36" RCP Endwall (Includes rip rap) | 2 | EA | 2200 | 4400
29 |  | 42" RCP Endwall (Includes rip rap) | 1 | EA | 2400 | 2400
30 |  | 30" Headwall | 1 | EA | 2100 | 2100
31 |  | 6" Underdrain | 2761 | LF | 20 | 55220
32 |  | Underdrain Cleanout | 58 | EA | 700 | 40600
33 |  | FDOT Type 6 Inlet | 28 | EA | 4800 | 134400
34 |  | Storm Manhole | 12 | EA | 3800 | 45600
35 |  | Grate Inlet | 8 | EA | 4000 | 32000
36 |  | Junction Box | 2 | EA | 6000 | 12000
37 |  | 24"x38" ERCP (Replaces Existing 30"x42" Crossing) | 126 | LF | 125 | 15750
38 |  | 24"x38" Headwall (Replaces Existing 30"x42" Crossing) | 1 | EA | 2800 | 2800
39 |  | 42" RCP (Replaces Existing 30"x42" Crossing) | 137 | LF | 130 | 17810
40 |  | 42" Headwall (Replaces Existing 30"x42" Crossing) | 1 | EA | 2400 | 2400
41 |  | 36" RCP (Lake 3 Outfall) | 89 | LF | 110 | 9790
42 |  | 36" RCP Endwall (Lake 3 Outfall) | 1 | EA | 2200 | 2200
43 |  | Connect to Existing Storm Inlet | 1 | EA | 5000 | 5000
44 |  | Single Grate Control Structure (Includes rip rap) (Lake 3 Outfall) | 1 | EA | 4000 | 4000
45 |  | Double Grate Control Structure (Includes rip rap) | 4 | EA | 6000 | 24000
46 |  | Storm Sewer Testing (per Manatee County Standards) | 1 | LS | 15000 | 15000
47 |  | 3" Type SP Asphaltic Concrete (First Lift) | 58697 | SY | 18 | 1056546
48 |  | 1.5" FC-12.5 Asphaltic Concrete (Second Lift) | 58697 | SY | 14 | 821758
49 |  | Optional Base Group 9 | 58697 | SY | 21 | 1232637
50 |  | 12" Stabilized Subgrade (Min. LBR 60) | 66741 | SY | 12.5 | 834262.5
51 |  | Temporary Pavement | 1003 | SY | 18 | 18054
52 |  | Handicap Ramp (complete with Tactile Surface) | 25 | EA | 1350 | 33750
53 |  | 4" Concrete Sidewalk | 4515 | SY | 32 | 144480
54 |  | 6" Concrete Driveway | 314 | SY | 40 | 12560
55 |  | 1.5" Type SP Asphaltic Concrete for Shared Use Path | 5996.3333 | SY | 9.5 | 56965.1667
56 |  | Optional Base Group 1 for Shared Use Path | 5996.3333 | SY | 12 | 71956
57 |  | 12" Stabilized Subgrade (Min. LBR 60) for Shared Use Path | 8734 | SY | 21 | 183414
58 |  | 4" Concrete, Terracotta & Imprinted with Brick | 684.4444 | SY | 80 | 54755.5556
59 |  | Tactile Surface | 2 | EA | 500 | 1000
60 |  | Valley Crossing | 38 | SY | 45 | 1710
61 |  | Type "F" Curb & Gutter | 13054 | LF | 20 | 261080
62 |  | Type "E" Curb | 385 | LF | 30 | 11550
63 |  | Type "AB" Curb, Modified | 8495 | LF | 10 | 84950
64 |  | 3' Traffic Seperator | 1584 | LF | 25 | 39600
65 |  | Remove Existing Asphalt | 30313 | SY | 4 | 121252
66 |  | Remove Existing Base | 30313 | SY | 1 | 30313
67 |  | Handrail | 657 | LF | 50 | 32850
68 |  | Traffic Control Striping and Pavement Markings (Includes Temporary Paint Markings on Initial Lift) | 1 | LS | 75000 | 75000
69 |  | Traffic Control Signage | 1 | LS | 25000 | 25000
70 |  | Permanent Control Points | 1 | LS | 6000 | 6000
SUBTOTAL FOR ROADWAY (PHASE 1) | [5 empty] | 8639582.1889
SIGNALIZATION & LIGHTING (PHASE 1)
71 | 102-104 | TEMPORARY SIGNALIZATION AND MAINTENANCE, INTERSECTION | 200 | ED | 14 | 2800
72 | 102-107-1 | TEMPORARY TRAFFIC DETECTION AND MAINTENANCE, INTERSECTION | 200 | ED | 10 | 2000
73 | 630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | 4355 | LF | 13 | 56615
74 | 630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | 205 | LF | 26 | 5330
75 | 632-7-1 | SIGNAL CABLE - NEW OR RECONSTRUCTED INTERSECTION, F&I | 2 | PI | 7000 | 14000
76 | 633-1-121 | FIBER OPTIC CABLE, F&I, UNDERGROUND, 2-12 FIBERS | 2255 | LF | 3 | 6765
77 | 633-1-122 | FIBER OPTIC CABLE, F&I, UNDERGROUND, 13-48 FIBERS | 2135 | LF | 3 | 6405
78 | 633-2-31 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | 56 | EA | 48 | 2688
79 | 633-3-11 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE ENCLOSURE | 2 | EA | 1140 | 2280
80 | 633-3-12 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE TRAY | 2 | EA | 85 | 170
81 | 633-3-15 | FIBER OPTIC CONNECTION HARDWARE, F&I, PATCH PANEL, PRETERMINATED | 2 | EA | 1800 | 3600
82 | 633-8-1 | MULTI-CONDUCTOR COMMUNICATION CABLE, FURNISH & INSTALL | 1010 | LF | 5.5 | 5555
83 | 635-2-11 | PULL & SPLICE BOX, F&I, 13" X 24" COVER SIZE | 3 | EA | 1000 | 3000
84 | 635-2-12 | PULL & SPLICE BOX, F&I, 24" X 36" COVER SIZE | 5 | EA | 1800 | 9000
85 | 635-2-13 | PULL & SPLICE BOX, F&I, 30" X 60" RECTANGULAR OR 36" ROUND COVER SIZE | 1 | EA | 3000 | 3000
86 | 639-1-122 | ELECTRICAL POWER SEVICE, F&I, UNDERGROUND, METER PURCHASED BY CONTRACTOR | 1 | AS | 4500 | 4500
87 | 639-2-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | 135 | LF | 14 | 1890
88 | 639-3-11 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | 1 | EA | 1500 | 1500
89 | 641-2-12 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE POLE | 1 | EA | 2000 | 2000
90 | 641-2-13 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-III | 2 | EA | 15250 | 30500
91 | 646-1-11 | ALUMINUM SIGNALS POLE, F&I, PEDESTAL | 15 | EA | 1800 | 27000
92 | 649-21-21 | STEEL MAST ARM ASSEMBLY, F&I, SINGLE ARM 78' | 1 | EA | 92000 | 92000
93 | 649-26-03 | STEEL MAST ARM ASSEMBLY, REMOVE, SHALLOW, BOLT ON ATTACHMENT | 1 | EA | 4200 | 4200
94 | 650-1-34 | VEHICULAR TRAFFIC SIGNAL, FURNISH & INSTALL, POLYCARBONATE, 3 SECTION, 1 WAY | 12 | AS | 1200 | 14400
95 | 650-1-36 | VEHICULAR TRAFFIC SIGNAL, FURNISH & INSTALL, POLYCARBONATE, 4 SECTION, 1 WAY | 6 | AS | 1400 | 8400
96 | 650-1-39 | VEHICULAR TRAFFIC SIGNAL, FURNISH & INSTALL, POLYCARBONATE, 5 SECTION CLUSTER, 1 WAY | 4 | AS | 2000 | 8000
97 | 653-1-11 | PEDESTRIAN SIGNAL, F&I, LED COUNTDOWN, 1 WAY | 14 | AS | 780 | 10920
98 | 653-1-12 | PEDESTRIAN SIGNAL, F&I, LED COUNTDOWN, 2 WAYS | 1 | AS | 1300 | 1300
99 | 660-3-11 | VEHICLE DETECTION SYSTEM - WAVETRONIX SMARTSENSOR HD, F&I CABINET EQUIPMENT | 2 | EA | 4700 | 9400
100 | 660-3-12 | VEHICLE DETECTION SYSTEM - WAVETRONIX SMARTSENSOR HD, F&I, ABOVE GROUND EQUIPMENT | 2 | EA | 7500 | 15000
101 | 660-3-42A | VEHICLE DETECTION SYSTEM - WAVETRONIX SMARTSENSOR ADVANCE, RELOCATE, ABOVE GROUND EQUIPMENT | 1 | EA | 1500 | 1500
102 | 660-3-42M | VEHICLE DETECTION SYSTEM - WAVETRONIX SMARTSENSOR MATRIX, RELOCATE, ABOVE GROUND EQUIPMENT | 1 | EA | 1500 | 1500
103 | 665-1-11 | PEDESTRIAN DETECTOR, F&I, STANDARD | 16 | EA | 275 | 4400
104 | 676-2-122 | ITS CABINET, F&I, ITS CABINET, POLE MOUNT W/ SUNSHIELDS, 336S, 24"W X 46" H x 22" D | 1 | EA | 7000 | 7000
105 | 676-3-10 | SMALL EQUIPMENT ENCLOSURE, FURNISH AND INSTALL, LESS THAN 10"W X 13"H X 11" D | 1 | EA | 1200 | 1200
106 | 684-1-1 | MANAGED FIELD ETHERNET SWITCH, F&I | 1 | EA | 4000 | 4000
107 | 700-3-501 | SIGN PANEL, RELOCATE, UP TO 12 SF | 2 | EA | 210 | 420
108 | 700-5-50 | INTERNALLY ILLUMINATED SIGN, RELOCATE | 1 | EA | 2000 | 2000
109 | 630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | 13555 | LF | 13 | 176215
110 | 630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | 1236 | LF | 26 | 32136
111 | 635-2-11 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | 123 | EA | 900 | 110700
112 | 639-1-122 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER PURCHASED BY CONTRACTOR | 1 | AS | 4400 | 4400
113 | 641-2-12 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE POLE | 1 | EA | 1800 | 1800
114 | 715-1-12 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 8 - 6 | 52824 | LF | 2.45 | 129418.8
115 | 715-1-13 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 4 - 2 | 1686 | LF | 3.7 | 6238.2
116 | 715-4-13 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD POLE, STANDARD FOUNDATION, 40' MOUNTING HEIGHT | 84 | EA | 7760 | 651840
117 | 715-4-851 | LIGHT POLE COMPLETE, F&I UTILITY CONFLICT POL, INDEX 715-002 FOUND 40' HT | 20 | EA | 7000 | 140000
118 | 715-7-11 | LOAD CENTER, F&I, SECONDARY VOLTAGE | 1 | EA | 15000 | 15000
119 | 715-500-1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | 104 | EA | 800 | 83200
SUBTOTAL FOR SIGNALIZATION & LIGHTING (PHASE 1) | [5 empty] | 1727186
SUBTOTAL FOR ROADWAY, SIGNALIZATION & LIGHTING (PHASE 1) | [5 empty] | 10366768.1889
10% Contigency (PHASE 1) (CIP #6071261) |  |  | 10% |  | 10% | 1036676.8189
TOTAL FOR ROADWAY, SIGNALIZATION & LIGHTING (PHASE 1) (CIP #6071261) | [5 empty] | 11403445.0078
POTABLE WATER (PHASE 1)
120 |  | Mobilization | 1 | LS | 25000 | 25000
121 |  | 30" DIP Watermain | 6030 | LF | 325 | 1959750
122 |  | 30" Removal CIP Watermain | 5914 | LF | 12 | 70968
123 |  | 24" DIP Watermain | 726 | LF | 180 | 130680
124 |  | 18" Steel Casing | 125 | LF | 250 | 31250
125 |  | 24" Steel Casing | 134 | LF | 350 | 46900
126 |  | 42" Steel Casing | 32 | LF | 600 | 19200
127 |  | 24" PVC Watermain | 40 | LF | 150 | 6000
128 |  | 12" PVC Watermain | 199 | LF | 70 | 13930
129 |  | 8" PVC Watermain | 151 | LF | 40 | 6040
130 |  | 8" Gate Valve | 3 | EA | 3000 | 9000
131 |  | 12" Gate Valve | 4 | EA | 3500 | 14000
132 |  | 24" Gate Valve | 2 | EA | 20000 | 40000
133 |  | 30" Gate Valve | 20 | EA | 35000 | 700000
134 |  | 12" Blow Off Assembly | 1 | EA | 0 | 0 |  |  |  |  | Deleted
135 |  | 2" Blow Off Assembly w/ Auto Flushers 30" Blow-Off Assembly | 2 | EA | 4000 | 8000 |  |  |  |  | Updated
136 |  | Fire Hydrant, Complete | 5 | EA | 7000 | 35000
137 |  | Water Service | 8 | EA | 800 | 6400
138 |  | Water Meter | 2 | EA | 2500 | 5000
139 |  | Connect to Existing 8" PVC | 3 | EA | 8000 | 24000
140 |  | Connect to Existing 12" PVC | 2 | EA | 12000 | 24000
141 |  | Connect to Existing 24" DIP | 1 | EA | 15000 | 15000
142 |  | Connect to Existing 30" Watermain (30" x 30" Tapping Sleeve and Valve) | 1 | EA | 25000 | 25000 |  |  |  |  | Updated
143 |  | Record Drawings prepared by licensed surveyor in compliance with Manatee County & SWFWMD | 1 | LS | 25000 | 25000
144 |  | Potable Water Main Fittings | 1 | LS | 337800 | 337800
145 |  | Chlorination & Pressure Testing (per Manatee County Standards) | 1 | LS | 101340 | 101340
SUBTOTAL FOR POTABLE WATER (PHASE 1) | [5 empty] | 3679258
10% Contigency (PHASE 1) (CIP #6113370) |  |  | 10% |  | 10% | 367925.8
TOTAL FOR POTABLE WATER (PHASE 1) (CIP #6113370) | [5 empty] | 4047183.8
RECLAIM (PHASE 1)
146 |  | Mobilization | 1 | LS | 25000 | 25000
147 |  | 30" DIP Pipe Removal | 3639 | LF | 12 | 43668
148 |  | 24" DIP Pipe Removal | 213 | LF | 10 | 2130
149 |  | 6" PVC reclaim main | 15 | LF | 15 | 225
150 |  | 8" PVC reclaim main | 15 | LF | 40 | 600
151 |  | 24" DIP reclaim main | 243 | LF | 180 | 43740
152 |  | 30" DIP reclaim main | 3332 | LF | 325 | 1082900
153 |  | 6" Gate Valve | 1 | EA | 1400 | 1400
154 |  | 8" Gate Valve | 1 | EA | 3000 | 3000
155 |  | 24" Gate Valve | 1 | EA | 20000 | 20000
156 |  | 30" Gate Valve | 6 | EA | 35000 | 210000
157 |  | 2" Blow Off Assembly w/ Auto Flushers 8" Blow Off Assembly | 2 | EA | 4000 | 8000 |  |  |  |  | Updated
158 |  | Reclaim Fire Hydrants | 4 | EA | 7000 | 28000
159 |  | Single Irrigation Service (Long w/ Casing) | 5 | EA | 800 | 4000
160 |  | Connect to Existing 30" | 1 | EA | 18000 | 18000
161 |  | Connect to Existing 24" | 1 | EA | 15000 | 15000
162 |  | Record Drawings prepared by licensed surveyor in compliance with Manatee County & SWFWMD | 1 | LS | 25000 | 25000
163 |  | Reclaim Fittings | 1 | LS | 166600 | 166600
164 |  | Reclaim Main Testing per Manatee County Standards | 1 | LS | 49980 | 49980
SUBTOTAL FOR RECLAIM (PHASE 1) | [5 empty] | 1747243
10% Contigency (PHASE 1) (CIP #6113390) |  |  | 10% |  | 10% | 174724.3
TOTAL FOR RECLAIM (PHASE 1) (CIP #6113390) | [5 empty] | 1921967.3
TOTAL FOR PHASE 1 | [5 empty] | 17372596.1078
BOTH PHASES | [5 empty] | 19475014.6128
BIDDER NAME________________________________________________
BIDDER SIGNATURE___________________________________________

## PHASE 2
APPENDIX K, BID PRICING FORM (REVISED) Moccasin Wallow, I-75 - 301 Segment 1 from US 301 To 115th Avenue East (Copperstone Entrance) PROJECT #'s 6071261, 6113370, 611390 |  |  |  |  | EOC STANTEC
Bidders must provide prices for each available line item on each tab for their bid to be considered responsive.
ITEM # | FDOT ITEM NUMBER | BRIEF DESCRIPTION OF ITEMS | ESTIMATED QUANTITY | UNIT | UNIT PRICE | EXTENDED AMOUNT | UNIT PRICE BID A 450 Calendar Days | EXTENDED AMOUNT BID A | UNIT PRICE BID B 540 Calendar Days | EXTENDED AMOUNT BID B
U.S. 301 FDOT ROUNDABOUT (PHASE 2)
ROADWAY (PHASE 2)
1 |  | Mobilization | 1 | LS | 75000 | 75000
2 |  | 2" Conduit (Material & Install) | 500 | LF | 5.5 | 2750
3 |  | 4" Conduit (Material & Install) | 500 | LF | 9 | 4500
4 |  | 6" Conduit (Material & Install) | 500 | LF | 15 | 7500
5 |  | Density Testing (By Owner) | 1 | LS | 0 | 0 |  |  |  |  | Delete Line
6 |  | Construction Stakeout | 1 | LS | 15000 | 15000
7 |  | Demolition, per plan - Includes any demo work that needs to be done prior to clearing, i.e. removal of pipe, conduit, structures, fencing, etc. not otherwise specified in Schedule of Values | 1 | LS | 5000 | 5000
8 |  | Temporary Emergency & Construction Entrance | 1 | LS | 2500 | 2500
9 |  | Maintenance of Traffic | 1 | LS | 25000 | 25000
10 |  | Clearing and Grubbing | 7 | AC | 3600 | 25200
11 |  | Finish Grading | 7 | AC | 3000 | 21000
12 |  | Excavation (Insitu Measure) | 9411 | CY | 4 | 37644
13 |  | Place and compact (Compacted measure) | 7799 | CY | 3.5 | 27296.5
14 |  | Ex. Ditch re-grading (Width Varies) | 255 | LF | 10 | 2550
15 |  | Sod | 10773 | SY | 2.25 | 24239.25
16 |  | Inlet Protection | 13 | EA | 275 | 3575
17 |  | Synthetic Bales | 4 | EA | 250 | 1000
18 |  | Double Silt Fence | 1002 | LF | 3 | 3006
19 |  | Silt Fence | 2003 | LF | 1.5 | 3004.5
20 |  | 15" RCP | 47 | LF | 50 | 2350
21 |  | 18" RCP | 384 | LF | 66 | 25344
22 |  | 24" RCP | 722 | LF | 75 | 54150
23 |  | 30" RCP | 81 | LF | 100 | 8100
24 |  | 36" RCP | 296 | LF | 140 | 41440
25 |  | 42" RCP | 66 | LF | 175 | 11550
26 |  | 24" RCP Endwall (Includes rip rap) | 1 | EA | 1700 | 1700
27 |  | 30" RCP Endwall (Includes rip rap) | 1 | EA | 2000 | 2000
28 |  | 36" RCP Endwall (Includes rip rap) | 2 | EA | 2200 | 4400
29 |  | FDOT Type 6 Inlet | 4 | EA | 4800 | 19200
30 |  | Storm Manhole | 3 | EA | 3800 | 11400
31 |  | Grate Inlet | 2 | EA | 4000 | 8000
32 |  | 18" Mitered End | 4 | EA | 2500 | 10000
33 |  | 36" Mitered End | 1 | EA | 5000 | 5000
34 |  | Single Grate Control Structure (Includes rip rap) | 1 | EA | 4000 | 4000
35 |  | Connect to Existing Storm RCP | 1 | EA | 8000 | 8000
36 |  | Storm Sewer Testing (per Manatee County Standards) | 1 | LS | 5000 | 5000
37 |  | 3.5" SP-19 Asphaltic Concrete (First Lift) | 6665 | SY | 18 | 119970
38 |  | 1.5" FC-9.5 Asphaltic Concrete (Second Lift) | 6665 | SY | 14 | 93310
39 |  | 10" Optimal Base Group 9 | 6665 | SY | 21 | 139965
40 |  | 12" Type B Stabilized Subgrade (Min. LBR 40) | 8195 | SY | 12.5 | 102437.5
41 |  | Handicap Ramp (complete with Tactile Surface) | 6 | EA | 1350 | 8100
42 |  | Tactile Surface | 10 | EA | 500 | 5000
43 |  | 6" Concrete Driveway | 389 | SY | 41 | 15949
44 |  | 4" Concrete Sidewalk | 1233 | SY | 32 | 39456
45 |  | Type "F" Curb & Gutter | 1676 | LF | 20 | 33520
46 |  | Type "E" Curb | 1486 | LF | 30 | 44580
47 |  | Type "RA" Curb | 346 | LF | 30 | 10380
48 |  | Type "D" Curb | 243 | LF | 14 | 3402
49 |  | Valley Gutter Curb | 35 | LF | 20 | 700
50 |  | Truck Apron | 447 | SY | 50 | 22350
51 |  | Remove Existing Asphalt | 6470 | SY | 4 | 25880
52 |  | Remove Existing Base | 6470 | SY | 1 | 6470
53 |  | Traffic Control Striping and Pavement Markings (Includes Temporary Paint Markings on Initial Lift) | 1 | LS | 15000 | 15000
54 |  | Traffic Control Signage | 1 | LS | 60000 | 60000
55 |  | Permanent Control Points | 1 | LS | 3000 | 3000
SUBTOTAL FOR ROADWAY (PHASE 2) | [5 empty] | 1256868.75
LIGHTING (PHASE 2)
56 | 630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | 1470 | LF | 13 | 19110
57 | 630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | 230 | LF | 26 | 5980
58 | 635-2-11 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | 1 | EA | 900 | 900
59 | 715-1-12 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 8 - 6 | 5484 | LF | 2.45 | 13435.8
60 | 715-1-60 | LIGHTING CONDUCTORS, REMOVE & DISPOSE, CONTRACTOR OWNS | 1730 | LF | 0.5 | 865
61 | 715-4-13 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD POLE, STANDARD FOUNDATION, 40' MOUNTING HEIGHT | 14 | EA | 7760 | 108640
62 | 715-4-70 | LIGHT POLE COMPLETE, REMOVE POLE AND FOUNDATION | 4 | EA | 835 | 3340
63 | 715-500-1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | 14 | EA | 800 | 11200
SUBTOTAL FOR LIGHTING (PHASE 2) | [5 empty] | 163470.8
SUBTOTAL FOR ROADWAY & LIGHTING (PHASE 2) | [5 empty] | 1420339.55
10% Contigency (PHASE 2) (CIP #6071261) |  |  | 10% |  | 10% | 142033.955
TOTAL FOR ROADWAY & LIGHTING (PHASE 2) (CIP #6071261) | [5 empty] | 1562373.505
POTABLE WATER (PHASE 2)
64 |  | Mobilization | 1 | LS | 25000 | 25000
65 |  | 24" DIP Watermain | 218 | LF | 120 | 26160
66 |  | 24" Gate Valve | 3 | EA | 20000 | 60000
67 |  | 2" Blow Off Assembly w/ Auto Flushers 24" Blow Off Assembly | 2 | EA | 4000 | 8000 |  |  |  |  | Updated
68 |  | Record Drawings prepared by licensed surveyor in compliance with FDOT & SWFWMD | 1 | LS | 10000 | 10000
69 |  | Potable Water Main Fittings | 1 | LS | 10900 | 10900
70 |  | Chlorination & Pressure Testing (per Manatee County Standards) | 1 | LS | 3270 | 3270
POTABLE WATER (PHASE 2) SUBTOTAL | [5 empty] | 143330
10% Contigency (PHASE 2) (CIP #6113370) |  |  | 10% |  | 10% | 14333
TOTAL FOR POTABLE WATER (PHASE 2) (CIP #6113370) | [5 empty] | 157663
RECLAIM (PHASE 2)
71 |  | Mobilization | 1 | LS | 25000 | 25000
72 |  | 30" DIP reclaim main | 458 | LF | 325 | 148850
73 |  | 30" Gate Valve | 3 | EA | 35000 | 105000
74 |  | 2" Blow Off Assembly w/ Auto Flushers 30" Blow Off Assembly | 1 | EA | 4000 | 4000 |  |  |  |  | Updated
75 |  | Connect to Existing 30" DIP | 1 | EA | 10000 | 10000
76 |  | Record Drawings prepared by licensed surveyor in compliance with FDOT & SWFWMD | 1 | LS | 25000 | 25000
77 |  | Reclaim Fittings | 1 | LS | 22900 | 22900
78 |  | Reclaim Main Testing per Manatee County Standards | 1 | LS | 6870 | 6870
SUBTOTAL FOR RECLAIM (PHASE 2) | [5 empty] | 347620
10% Contigency (PHASE 2) (CIP #6113390) |  |  | 10% |  | 10% | 34762
TOTAL FOR RECLAIM (PHASE 2) (CIP #6113390) | [5 empty] | 382382
TOTAL FOR PHASE 2 | [5 empty] | 2102418.505
BIDDER NAME________________________________________________
BIDDER SIGNATURE___________________________________________