## Bid A Part I
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART IA - IW-1
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
I-1. | Mobilize and Demobilize All Equip. to the IW-1 Well Site to Complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for IW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
I-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
I-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,800 feet bls (Reverse-air) | FT | 1450 | 0 | 0
| c. 12-inch Diameter up to 3,500 feet bls (Reverse-air) | FT | 1900 | 0 | 0
I-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 41-inch Diameter to 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 31-inch Diameter to 1,600 feet bls (Reverse-air) | FT | 1250 | 0 | 0
| c. 23-inch Diameter up to 2,000 feet bls (Reverse-air) | FT | 400 | 0 | 0
| d. Re-establish 12-inch Diameter open hole up to 3,500 feet bls (Reverse-air) | FT | 1500 | 0 | 0
I-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,800 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Pilot hole up to 3,500 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 2,000 feet | EA | 1 | 0 | 0
| f. Completed Well up to 3,500 feet | EA | 1 | 0 | 0
| g. Temperature Log Following Each Cement Stage | EA | 5 | 0 | 0
| h. Cement Bond Log on Final Casing | EA | 1 | 0 | 0
I-6. | Furnish and Install Casing:
| a. 32-inch Dia. Carbon Steel | FT | 350 | 0 | 0
| b. 24-inch Dia. Carbon Steel | FT | 1600 | 0 | 0
| c. 12-inch Dia. Carbon Steel | FT | 2000 | 0 | 0
I-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 6000 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 3600 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 2400 | 0 | 0
I-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 20 | 0 | 0
I-9. | Pressure Test Casing - Successfully Complete Pressure Test on Final 24-Inch Casing Prior to Drilling Out Plug, Complete | LS | 1 | 0 | 0
I-10. | Cores - During Pilot Hole or Open Hole Drilling, Provide 10-Foot Length, 4-Inch Diameter Cores at Selected Intervals, Complete | Feet | 40 | 0 | 0
I-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 6 | 0 | 0
I-12. | Packer Test Pumping Time, Complete | HR | 100 | 0 | 0
I-13. | Pumping Test Setup, Complete | LS | 2 | 0 | 0
I-14. | Pumping Test Pumping Time, Complete | HR | 10 | 0 | 0
I-15. | Development - Develop Well, Complete | HR | 48 | 0 | 0
I-16. | Temporary Wellhead
| a. Install Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
| b. Temporary HDPE piping to reclaimed line as shown in Drawings (IW-1 only) | FT | 300 | 0 | 0
| c. Hot Tap Reclaimed line, Install Above Ground Appurtenances, and connect with DIP piping as shown in drawings (IW-1 only) | LS | 1 | 0 | 0
I-17. | Standby Time (Max. 12 hr/day) | HR | 40 | 0 | 0
I-18. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 40 | 0 | 0
I-19. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 35 | 0 | 0
| b. Exhibit 1, List A | EA | 70 | 0 | 0
| c. Exhibit 1, List B | EA | 12 | 0 | 0
| d. Exhibit 1, List C | EA | 1 | 0 | 0
I-20. | Acidization Setup - Setup for Acidization, Complete, Including well kills | LS | 1 | 0 | 0
I-21. | Furnish and Emplace Acid, Complete | GAL | 10000 | 0 | 0
|  |  | TOTAL PART IA |  | 0

## Bid A Part II
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART IIA - IW-2
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
II-1. | Mobilize and Demobilize All Equip. to the IW-2 Well Site to Complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for IW-2, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
II-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
II-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,800 feet bls (Reverse-air) | FT | 1450 | 0 | 0
| c. 12-inch Diameter up to 3,500 feet bls (Reverse-air) | FT | 1900 | 0 | 0
II-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 41-inch Diameter to 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 31-inch Diameter to 1,600 feet bls (Reverse-air) | FT | 1250 | 0 | 0
| c. 23-inch Diameter up to 2,000 feet bls (Reverse-air) | FT | 400 | 0 | 0
| d. Re-establish 12-inch Diameter open hole up to 3,500 feet bls (Reverse-air) | FT | 1500 | 0 | 0
II-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,800 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Pilot hole up to 3,500 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 2,000 feet | EA | 1 | 0 | 0
| f. Completed Well up to 3,500 feet | EA | 1 | 0 | 0
| g. Temperature Log Following Each Cement Stage | EA | 5 | 0 | 0
| h. Cement Bond Log on Final Casing | EA | 1 | 0 | 0
II-6. | Furnish and Install Casing:
| a. 32-inch Dia. Carbon Steel | FT | 350 | 0 | 0
| b. 24-inch Dia. Carbon Steel | FT | 1600 | 0 | 0
| c. 12-inch Dia. Carbon Steel | FT | 2000 | 0 | 0
II-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 6000 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 3600 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 2400 | 0 | 0
II-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 20 | 0 | 0
II-9. | Pressure Test Casing - Successfully Complete Pressure Test on Final 24-Inch Casing Prior to Drilling Out Plug, Complete | LS | 1 | 0 | 0
II-10. | Cores - During Pilot Hole or Open Hole Drilling, Provide 10-Foot Length, 4-Inch Diameter Cores at Selected Intervals, Complete | Feet | 40 | 0 | 0
II-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 6 | 0 | 0
II-12. | Packer Test Pumping Time, Complete | HR | 100 | 0 | 0
II-13. | Pumping Test Setup, Complete | LS | 2 | 0 | 0
II-14. | Pumping Test Pumping Time, Complete | HR | 10 | 0 | 0
II-15. | Development - Develop Well by Air Lifting, Complete | HR | 48 | 0 | 0
II-16. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
II-17. | Standby Time (Max. 12 hr/day) | HR | 40 | 0 | 0
II-18. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 40 | 0 | 0
II-19. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 35 | 0 | 0
| b. Exhibit 1, List A | EA | 70 | 0 | 0
| c. Exhibit 1, List B | EA | 12 | 0 | 0
| d. Exhibit 1, List C | EA | 1 | 0 | 0
II-20. | Acidization Setup - Setup for Acidization, Complete, Including well kills | LS | 1 | 0 | 0
II-21. | Furnish and Emplace Acid, Complete | GAL | 10000 | 0 | 0
|  |  | TOTAL PART IIA |  | 0

## Bid A Part III
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART IIIA - IW-3
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
III-1. | a. Mobilize and Demobilize All Equip. to the IW-3 Well Site at the NRWRF to Complete Drilling and Testing Activities for IW-3, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
| b. Additional Mobilization Cost to Construct Well at SEWRF | LS | 1 | 0 | 0
III-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
III-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,800 feet bls (Reverse-air) | FT | 1450 | 0 | 0
| c. 12-inch Diameter up to 3,500 feet bls (Reverse-air) | FT | 1900 | 0 | 0
III-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 47-inch Diameter to 350 feet bls (Mud Rotary) | FT | 350 | 0 | 0
| b. 33-inch Diameter to 1,600 feet bls (Reverse-air) | FT | 1250 | 0 | 0
| c. 25-inch Diameter up to 2,000 feet bls (Reverse-air) | FT | 400 | 0 | 0
| d. Re-establish 12-inch Diameter open hole up to 3,500 feet bls (Reverse-air) | FT | 1500 | 0 | 0
III-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,800 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Pilot hole up to 3,500 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 2,000 feet | EA | 1 | 0 | 0
| f. Completed Well up to 3,500 feet | EA | 1 | 0 | 0
| g. Temperature Log Following Each Cement Stage | EA | 5 | 0 | 0
| h. Cement Bond Log on Final Casing | EA | 1 | 0 | 0
III-6. | Furnish and Install Casing:
| a. 34-inch Dia. Carbon Steel | FT | 350 | 0 | 0
| b. 26-inch Dia. Carbon Steel | FT | 1600 | 0 | 0
| c. 16-inch Dia. Carbon Steel | FT | 2000 | 0 | 0
| d. 9.625-inch Dia. FRP Tubing | FT | 2000 | 0 | 0
III-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 7500 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 4500 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 3000 | 0 | 0
III-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 20 | 0 | 0
III-9. | Pressure Test Casing - Successfully Complete Pressure Test on Casings, Complete
| a. Final 16-Inch Casing Prior to Drilling Out Plug | LS | 1 | 0 | 0
| b. Final 9-Inch FRP Tubing using an Inflatable Packer | LS | 1 | 0 | 0
III-10. | Cores - During Pilot Hole or Open Hole Drilling, Provide 10-Foot Length, 4-Inch Diameter Cores at Selected Intervals, Complete | Feet | 40 | 0 | 0
III-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 8 | 0 | 0
III-12. | Packer Test Pumping Time, Complete | HR | 130 | 0 | 0
III-13. | Pumping Test Setup, Complete | LS | 2 | 0 | 0
III-14. | Pumping Test Pumping Time, Complete | HR | 10 | 0 | 0
III-15. | Development - Develop Well by Air Lifting, Complete | HR | 48 | 0 | 0
III-16. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
III-17. | Standby Time (Max. 12 hr/day) | HR | 40 | 0 | 0
III-18. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete: | HR | 40 | 0 | 0
III-19. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 52 | 0 | 0
| b. Exhibit 1, List A | EA | 70 | 0 | 0
| c. Exhibit 1, List B | EA | 16 | 0 | 0
| d. Exhibit 1, List C | EA | 1 | 0 | 0
III-20. | Acidization Setup - Setup for Acidization, Complete, Including well kills | LS | 1 | 0 | 0
III-21. | Furnish and Emplace Acid, Complete | GAL | 10000 | 0 | 0
|  |  | TOTAL PART IIIA |  | 0

## Bid A Part IV
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART IVA- DEEP ZONE MONITOR WELL (DZMW-1)
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
IV-1. | Mobilize and Demobilize All Equip. to the DZMW-1 Well Site to complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for DZMW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
IV-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
IV-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
IV-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 23-inch Diameter to 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 15-inch Diameter to 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
IV-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,600 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Completed Well to 1,600 feet | EA | 1 | 0 | 0
| f. Cement Bond Log on Final FRP Casing | EA | 1 | 0 | 0
IV-6. | Furnish and Install Casing: |  |  | 0
| a. 16-inch Dia. Carbon Steel to 350 feet | FT | 350 | 0 | 0
| b. 6-inch Dia. FRP to 1,500 feet | FT | 1150 | 0 | 0
IV-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 1500 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 900 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 600 | 0 | 0
IV-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 5 | 0 | 0
IV-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 | 0 | 0
IV-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
IV-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 2 | 0 | 0
IV-12. | Packer Test Pumping Time, Complete | HR | 32 | 0 | 0
IV-13. | Standby Time (Max. 12 hr/day) | HR | 20 | 0 | 0
IV-14. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 | 0 | 0
IV-15. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 22 | 0 | 0
| b. Exhibit 1, List A | EA | 28 | 0 | 0
| c. Exhibit 1, List C | EA | 1 | 0 | 0
|  |  | TOTAL PART IVA |  | 0

## Bid A Part V
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART VA- DEEP ZONE MONITOR WELL (DZMW-2)
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
3074 | Mobilize and Demobilize All Equip. to the DZMW-2 Well Site to complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for DZMW-2, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
IV-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
V-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
V-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 23-inch Diameter to 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 15-inch Diameter to 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
V-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,600 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Completed Well to 1,600 feet | EA | 1 | 0 | 0
| f. Cement Bond Log on Final FRP Casing | EA | 1 | 0 | 0
V-6. | Furnish and Install Casing:
| a. 16-inch Dia. Carbon Steel to 350 feet | FT | 350 | 0 | 0
| b. 6-inch Dia. FRP to 1,500 feet | FT | 1150 | 0 | 0
V-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 1500 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 900 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 600 | 0 | 0
V-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 5 | 0 | 0
V-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 | 0 | 0
V-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
V-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 2 | 0 | 0
V-12. | Packer Test Pumping Time, Complete | HR | 32 | 0 | 0 | 32
V-13. | Standby Time (Max. 12 hr/day) | HR | 20 | 0 | 0
V-14. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 | 0 | 0
V-15. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 22 | 0 | 0
| b. Exhibit 1, List A | EA | 28 | 0 | 0
| c. Exhibit 1, List C | EA | 1 | 0 | 0
|  |  | TOTAL PART VA |  | 0

## Bid A Part VI
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART VIA- DEEP ZONE MONITOR WELL (DZMW-3)
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
VI-1. | Mobilize and Demobilize All Equip. to the DZMW-3 Well Site to complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for DZMW-3, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 | 0 | 0
VI-2. | Set Pit Casing, Complete | LS | 1 | 0 | 0
VI-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
VI-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 23-inch Diameter to 350 feet (Mud Rotary) | FT | 350 | 0 | 0
| b. 15-inch Diameter to 1,600 feet (Reverse-air) | FT | 1250 | 0 | 0
VI-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 350 feet | EA | 1 | 0 | 0
| b. Reamed Hole to 350 feet | EA | 1 | 0 | 0
| c. Pilot Hole to 1,600 feet | EA | 1 | 0 | 0
| d. Reamed Hole to 1,600 feet | EA | 1 | 0 | 0
| e. Completed Well to 1,600 feet | EA | 1 | 0 | 0
| f. Cement Bond Log on Final FRP Casing | EA | 1 | 0 | 0
VI-6. | Furnish and Install Casing:
| a. 16-inch Dia. Carbon Steel to 350 feet | FT | 350 | 0 | 0
| b. 6-inch Dia. FRP to 1,500 feet | FT | 1150 | 0 | 0
VI-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 1500 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 900 | 0 | 0
| c. Up to 8% Bentonite | FT3 | 600 | 0 | 0
VI-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | YD3 | 5 | 0 | 0
VI-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 | 0 | 0
VI-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
VI-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 2 | 0 | 0
VI-12. | Packer Test Pumping Time, Complete | HR | 32 | 0 | 0
VI-13. | Standby Time (Max. 12 hr/day) | HR | 20 | 0 | 0
VI-14. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 | 0 | 0
VI-15. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 22 | 0 | 0
| b. Exhibit 1, List A | EA | 28 | 0 | 0
| c. Exhibit 1, List C | EA | 1 | 0 | 0
|  |  | TOTAL PART VIA |  | 0

## Bid A Part VII
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
PART VII- AVON PARK MONITOR WELL CONVERSION (APMW)
ITEM No. | DESCRIPTION | U/M | EST QTY | UNIT COST | EXTENDED COST
VII-1. | Mobilize and Demobilize All Equip. to the Existing Avon Park Test Well Site to Complete Construction and Testing as required, including 200-ft gravel access road, Complete | LS | 1 | 0 | 0
VII-2. | Drill Out Open Hole (if needed) to Depth of:
| a. 8-inch Diameter up to 1,100 feet (Reverse-air) | FT | 100 | 0 | 0
VII-3. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Existing Well to 1,050 feet | EA | 1 | 0 | 0
| b. Converted Well to 1,100 feet (if needed) | EA | 1 | 0 | 0
VII-4. | Furnish and Install Liner Casing (if needed):
| a. 4-inch Dia. Carbon Steel | FT | 900 | 0 | 0
VII-5. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | FT3 | 200 | 0 | 0
| b. Up to 6% Bentonite | FT3 | 80 | 0 | 0
VII-6. | Development - Develop Well by Air Lifting, Complete | HR | 24 | 0 | 0
VII-7. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 | 0 | 0
VII-8. | Standby Time (Max. 12 hr/day) | HR | 20 | 0 | 0
VII-9. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 | 0 | 0
VII-10. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Exhibit 1, List A | EA | 1 | 0 | 0
| b. Exhibit 1, List C | EA | 1 | 0 | 0
|  |  | TOTAL PART VIIA |  | 0

## Bid A Summary
BID A 1,260 DAYS FOR SUBSTANTIAL COMPLETION
SUMMARY OF BID A
Total Part IA– Injection Well No. 1 (IW-1) Municipal |  |  | 0
Total Part IIA – Injection Well No. 2 (IW-2) Municipal |  |  | 0
Total Part IIIA – Injection Well No. 3 (IW-3) RO/Municipal |  |  | 0
Total Part IVA – Deep Zone Monitoring Well No. 1 (DZMW-1) |  |  | 0
Total Part VA – Deep Zone Monitoring Well No. 2 (DZMW-2) |  |  | 0
Total Part VIA – Deep Zone Monitoring Well No. 3 (DZMW-3) |  |  | 0
Total Part VIIA – Avon Park Monitoring Well Conversion (APMW) |  |  | 0
Total Parts IA through VIIA |  |  | 0
| Contingency (10% of Total Parts 1A through VIIA) |  | 0
Total Parts IA through VIIA Plus Contingency |  |  | 0
TIME OF SUBSTANTIAL COMPLETION for Total Project (Parts IA through VIIA) |  |  | 1,260 days
| IW-1, DZMW-1, and APMW (Parts IA, IVA, and VIIA) | 420 days
| IW-2 and DZMW-2 (Parts IIA and VA) | 420 days
| IW-3 and DZMW-3 (Parts IIIA and VIA) | 420 days
TIME OF FINAL COMPLETION for Total Project (Parts IA through VIIA) |  |  | 1,290 days