## Sheet1
APPENDIX K, BID PRICING FORM REVISED 22-TA004058DJ PHASE II DAM REPAIRS COUNTY PROJECT NO. 6108870 |  |  |  | EOC--WOOD
Pay Item Number | Description | Estimated Quantity | Unit | Unit Price | Total Bid Price | Unit Price 214 Calendar Days | Total Bid Price
100 Mobilization
101 | Pre-Mobilization Activities (Construction Submittals….) | 1 | LS |  | 0
102 | Utility Locates | 1 | LS |  | 0
103 | Laydown and Setup | 1 | LS |  | 0
104 | Office Set-Up | 1 | LS |  | 0
104 | Office Maintenance and Operation | 30 | WK |  | 0
105 | Erosion and Sediment Control Best Management Practices | 30 | WK |  | 0
106 | Temporary Downstream Access Road | 1 | LS |  | 0
108 | General Conditions | 1 | LS |  | 0
109 | Permits, Bonding, etc. | 1 | LS |  | 0
MOBILIZATION SUBTOTAL |  |  |  |  | 0
200 Construction Access Road
201 | Cut for Regrading | 600 | CY |  | 0
202 | Furnish & Install Grading Material | 1300 | CY |  | 0
CONSTRUCTION ACCESS ROAD SUBTOTAL |  |  |  |  | 0
300 Void Filling
Apron Area
301 | Furnish & Install Pressure Relief Wells | 4 | LS |  | 0
302 | Core Slab, Fill Voids, and Repair Cores | 120 | CY |  | 0
Stilling Basin
303 | Furnish & Install Vertical Pressure Relief Wells | 9 | LS |  | 0
304 | Furnish & Install Inclined Pressure Relief Wells | 10 | LS |  | 0
305 | Core Slab, Fill Voids, and Repair Cores | 150 | CY |  | 0
VOID FILLING SUBTOTAL |  |  |  |  | 0
400 Apron Area Repairs
Site Preparation
401 | Full Depth Demo of Trench and Grade Preparation for Cutoff Wall Installation | 160 | CY |  | 0
402 | Partial Depth Demo and Preparation for Overlay Slab Key Trenches | 20 | CY |  | 0
403 | Preparation of Apron Area for Concrete Overlay | 20000 | SF |  | 0
New Work
404 | Furnish & Install Soil Mix Cutoff Wall | 1610 | VLF |  | 0
405 | Furnish & Install 8 Ft Diameter Jet Grout Cells Along Cutoff Wall | 100 | VLF |  | 0
406 | Furnish & Install 4 Ft Diameter Jet Grout Tie-ins for Cutoff Wall | 100 | VLF |  | 0
407 | Furnish & Install Reinforced Concrete Trench Slab Across Apron to Engage Cutoff Wall | 160 | CY |  | 0
408 | Furnish & Install Reinforced Concrete Topping Slab Over Existing Apron | 650 | CY |  | 0
409 | Furnish & Install Reinforced Concrete Access Steps | 1 | EA |  | 0
APRON AREA REPAIRS SUBTOTAL |  |  |  |  | 0
500 North Training Wall
Site Preparation
501 | RipRap Removal and Excavation at Training Wall to Wing Wall Interface | 600 | CY |  | 0
502 | Furnish & Install Engineered Fill in Cut at Training Wall to Wing Wall Interface | 600 | CY |  | 0
503 | Furnish & Install Steel Sheet Piling Along Toe Drain Piping and Adjacent to Stoplog Storage Pad | 3000 | SF |  | 0
New Work
504 | Cut Work Volume As-Needed for Cutoff Wall Installation Equipment | 1000 | CY |  | 0
505 | Transport & Place Fill Work Volume As-Needed for Cutoff Wall Installation Equipment | 120 | CY |  | 0
506 | Furnish & Install 3 ft Diameter Soil Mix Cutoff Wall | 1700 | LF |  | 0
507 | Furnish & Install 4 Ft Diameter Jet Grout Cells | 1500 | LF |  | 0
508 | Furnish & Install 8 Ft Diameter Jet Grout Tie-in Cells | 120 | LF |  | 0
509 | Furnish & Install 4 Ft Diameter Jet Grout Slab Support Columns on 10 ft Centers to Training Wall Footings | 450 | LF |  | 0
510 | Surplus Allotment of Soil Mix Grout Migrating into Remaining Voids Under Training Wall | 25 | CY |  | 0
511 | Cut Work and Seeding/Sodding As-Needed for Final Grade | 150 | CY |  | 0 |  |  | Changed
512 | Transport & Place Fill Work Volume As-Needed for Final Grade and Seed/Sod | 600 | CY |  | 0 |  |  | Changed
513 | Furnish & Install Continuous Reinforced Concrete Slab Between Training Wall and Cutoff Wall | 175 | CY |  | 0
514 | Furnish & Install Reinforced Concrete Slab Between End of Training Wall and Toe Drain Sheet Pile Wall | 10 | CY |  | 0
515 | Furnish & Install Reinforced Concrete Cap Along Sheet Pile Wall at Stoplog Storage Area | 5 | CY |  | 0
516 | Furnish & Install Guardrail System As-Needed Beyond Training Wall and Sheet Pile Wall at Stoplog Storage Area | 60 | LF |  | 0
517 | Install new electical conduit and wiring | 600 | LF |  | 0
518 | Replace rip rap, as-needed, adjacent to wing wall | 150 | CY |  | 0
519 | Seeding/Sodding behind North Training Wall, assume 90% seed and 10% sod | 1 | LS |  | 0 |  |  | Added
NORTH TRAINING WALL SUBTOTAL |  |  |  |  | 0
600 South Training Wall
Site Preparation
601 | Sawcut and Partial Removal of Existing Slab on Grade As-Needed for Sheet Pile Installation | 10 | CY |  | 0
602 | Transport & Place Fill Work Volume As-Needed for Cutoff Wall Installation Equipment | 20 | CY |  | 0
603 | Furnish & Install Steel Sheet Piling Along Toe Drain Piping and Adjacent to Control Building | 3200 | SF |  | 0
New Work
604 | Cut Work Volume As-Needed for Cutoff Wall Installation Equipment | 1100 | CY |  | 0
605 | Transport & Place Fill Work Volume As-Needed for Cutoff Wall Installation Equipment | 250 | CY |  | 0
606 | Furnish & Install 3 ft Diameter Soil Mix Cutoff Wall | 1800 | LF |  | 0
607 | Furnish & Install 4 Ft Diameter Jet Grout Cells | 1600 | LF |  | 0
608 | Furnish & Install 8 Ft Diameter Jet Grout Cells at Transitions | 400 | LF |  | 0
609 | Furnish & Install 4 Ft Diameter Jet Grout Slab Support Columns on 10 ft Centers to Training Wall Footings | 500 | LF |  | 0
610 | Surplus Allotment of Soil Mix Grout Migrating into Remaining Voids Under Training Wall | 25 | CY |  | 0
611 | Cut and Seeding/Sodding As-Needed for Final Grade | 250 | CY |  | 0 |  |  | Changed
612 | Transport & Place Fill and Seeding/Sodding As-Needed for Final Grade | 1000 | CY |  | 0 |  |  | Changed
613 | Furnish & Install Continuous Reinforced Concrete Slab Between Training Wall and Cutoff Wall | 250 | CY |  | 0
614 | Furnish & Install Reinforced Concrete Slab Between End of Training Wall and Toe Drain Sheet Pile Wall | 5 | CY |  | 0
615 | Furnish & Install Reinforced Concrete Cap Along Sheet Pile Wall at Control Building | 3 | CY |  | 0
616 | Furnish & Install Guardrail System As-Needed Along Sheetpile Beyond Training Wall | 40 | LF |  | 0
617 | Furnish & Install Guardrail System Adjacent to Steps Near Crest | 40 | LF |  | 0
618 | Install new electical conduit and wiring | 1200 | LF |  | 0
619 | Seeding/Sodding behind North Training Wall, assume 90% seed and 10% sod | 1 | LS |  | 0 |  |  | Added
SOUTH TRAINING WALL SUBTOTAL |  |  |  |  | 0
700 Stilling Basin Repairs
701 | Remove Existing Plugs from Underdrain and Abandoned Toe Drain Outfalls, Permentantly Seal | 4 | LS |  | 0
STILLING BASIN REPAIRS SUBTOTAL |  |  |  |  | 0
800 Mechanical Improvements
801 | Replace existing electrical, instructmentation, and mechanical drive components with new equipment | 3 | Gates Total Price |  | 0
MECHANICAL IMPROVEMENTS SUBTOTAL |  |  |  |  | 0
900 Daily Mandated Freshwater Release
901 | Furnish, Inspect, Maintain, and Operate 2700 gpm Intake Water Pump | 212 | Days |  | 0
DAILY MANDATED FRESHWATER RELEASE SUBTOTAL |  |  |  |  | 0
1000 Demobilization
1001 | Office Removal, Staging/Laydown Area Removal | 1 | LS |  | 0
1002 | Punchlist Inspection | 1 | LS |  | 0
1003 | Closeout Manuals / Submittals | 1 | LS |  | 0
1004 | Red-Line Construction Drawings | 1 | LS |  | 0
DEMOBILIZATION SUBTOTAL |  |  |  |  | 0
SUBTOTAL ALL SECTIONS (MOBILZATION, CONSTRUCTION ACCESS ROAD, VOID FILLING, APRON AREA REPAIRS, NORTH TRAINING WALL, SOUTH TRAINING WALL, STILL BASIN REPAIRS, MECHANINCAL IMPROVEMENTS, DAILY MANDATED FRESHWATER RELEASE, DEMOBILIZATION) |  |  |  |  | 0
CONTRACT CONTINGENCY WORK (USED ONLY WITH COUNTY APPROVAL) |  |  |  | 10% | 0 | 10%
GRAND TOTAL |  |  |  |  | 0
THE FOLLOWING PAY ITEMS ARE INTENDED TO ESTABLISH UNIT RATES FOR UNFORESEEN CIRCUMSTANCES DURING THE CONTRACT PERIOD, AND WILL NOT BE UTILIZED TO DETERMINE CONTRACT AWARD.
1100
1101 | Emergency Demobilization |  |  |  | 0
| a. Demobilization | 1 | LS |  | 0
| b. Site Monitoring & Standby Rate | 1 | Day |  | 0
| d. Mobilization | 1 | LS |  | 0
1102 | Replace Fuze Plug in Emergency Spillway after Major Storm Event | 1 | Plug |  | 0
1103 | Flowable Structural Cement Mix for Void Repair (F&I) | 1 | CY |  | 0 |  |  | Deleted
1104 1103 | Turf Reinforcement Mat (Type 3) F&I with Anchors | 1 50 | SY |  | #VALUE! |  |  | Changed
1105 1104 | FDOT Type D4 Filter Fabric (FDOT Std. Spec. 985) F&I for Slope Stabilization | 1 50 | SY |  | #VALUE! |  |  | Changed
1106 1105 | Bank & Shore Riprap (D50=18" and generally per FDOT Std. Spec. 530-2.1.3.1) F&I | 1 20 | TN |  | #VALUE! |  |  | Changed
BIDDER NAME________________________________________________
BIDDER SIGNATURE___________________________________________