## Const Cost
| APPENDIX L, BID PRICING FORM |  |  | FILLABLE
IFBC 24-TA005165LP |  | Summer Place Condo Waterline Replacement
PROJECT NUMBER: 6110070
WATER LINES 6-INCH & UNDER
ITEM NO. | DESCRIPTION | UNITS | QTY. | BID A UNIT PRICE 330 CALENDAR DAYS ($) | BID A EXTENDED PRICE 330 CALENDAR DAYS ($) | BID B UNIT PRICE 330 CALENDAR DAYS ($) | BID B EXTENDED PRICE 330 CALENDAR DAYS ($)
Bidders must provide prices for each line item for this to be considered responsive
1 | Pavement Repair & Road Restoration
1.01 | Road Pavement Base | SY | 1432 |  | 0 |  | 0
1.02 | Road Pavement Asphalt | SY | 1700 |  | 0 |  | 0
1.03 | Mill & Overlay | SY | 7027 |  | 0 |  | 0
2 | Sidewalk Replacement, conc. (4" min. thick.) | SY | 23 |  | 0 |  | 0
3 | Sodding | SY | 800 |  | 0 |  | 0
4 | Grout Fill Abandoned Pipe | CY | 32 |  | 0 |  | 0
5 | 2" Blow-off Assembly | EA | 3 |  | 0 |  | 0
6 | Permitting Fees- Building Dept.- BPA Installation | EA | 5 |  | 0 |  | 0
7 | Backflow Prevention Assemblies
7.01 | DC 3/4" | EA | 10 |  | 0 |  | 0
7.02 | RPZ 3/4" | EA | 39 |  | 0 |  | 0
8 | Remove Ex. Utilties
8.01 | 2" Gate Valve | EA | 1 |  | 0 |  | 0
8.02 | 6" Gate Valve | EA | 19 |  | 0 |  | 0
8.03 | Fire Hydrant Assembly | EA | 2 |  | 0 |  | 0
9 | Pipe
9.01 | 2" COPPER, (SDR-9) | LF | 23 |  | 0 |  | 0
9.02 | 4" PVC, (C-900) | LF | 80 |  | 0 |  | 0
9.03 | 6" PVC, (C-900) | LF | 596 |  | 0 |  | 0
9.04 | 4" DIP, (Class 350) | LF | 31 |  | 0 |  | 0
9.05 | 6" DIP, (Class 350) | LF | 2984 |  | 0 |  | 0
9.06 | 2" PE, (SDR-9) | LF | 578 |  | 0 |  | 0
9.07 | 4" HDPE, (DR-11) | LF | 117 |  | 0 |  | 0
10 | 14" Steel Casing Pipe (Class 350) | LF | 50 |  | 0 |  | 0
11 | Water Services
11.01 | 1" PE Single Service (Short) | EA | 13 |  | 0 |  | 0
11.02 | 1" PE Single Service (Long), w/ 2" casing | EA | 27 |  | 0 |  | 0
11.03 | 1" PE Double Service (Short) | EA | 3 |  | 0 |  | 0
11.04 | 1" PE Double Service (Long), w/ 2" casing | EA | 13 |  | 0 |  | 0
11.05 | Additional 1" Service Pipe over 10' (Short) & 30' (Long) | LF | 302 |  | 0 |  | 0
12 | Ductile Iron Fittings
12.01 | 4" Plug x 2" Compression Fitting, DI | EA | 3 |  | 0 |  | 0
12.02 | 4" 45 Degree Bend, MJ | EA | 2 |  | 0 |  | 0
12.03 | 6"x4" Reducer, MJ | EA | 2 |  | 0 |  | 0
12.04 | 6" 22.5 Degree Bend, MJ | EA | 2 |  | 0 |  | 0
12.05 | 6" 45 Degree Bend, MJ | EA | 30 |  | 0 |  | 0
12.06 | 6" 90 Degree Bend, MJ | EA | 1 |  | 0 |  | 0
12.07 | 6"x4" Cross MJ | EA | 1 |  | 0 |  | 0
12.08 | 6" Tee, MJ | EA | 8 |  | 0 |  | 0
12.09 | 6" Tee, MJ (Cut-in) | EA | 1 |  | 0 |  | 0
13 | Pipe Joint Restraints
13.01 | 4" | EA | 6 |  | 0 |  | 0
13.02 | 6" | EA | 174 |  | 0 |  | 0
14 | HDPE Pipe Adapter, MJ
14.01 | 2" | EA | 6 |  | 0 |  | 0
14.02 | 4" | EA | 2 |  | 0 |  | 0
15 | Valves
15.01 | 2" Gate Valve | EA | 2 |  | 0 |  | 0
15.02 | 4" Gate Valve | EA | 1 |  | 0 |  | 0
15.03 | 6" Gate Valve | EA | 11 |  | 0 |  | 0
16 | Fire Hydrant Assembly | EA | 3 |  | 0 |  | 0
17 | Thermoplastic Striping
17.02 | Stop Bar, White, 24" | LF | 12 |  | 0 |  | 0
17.02 | White, 6" | LF | 40 |  | 0 |  | 0
17.03 | Double Yellow, 6" | LF | 80 |  | 0 |  | 0
18 | Erosion Control | LS | 1 |  | 0 |  | 0
19 | Silt Fence | LF | 9 |  | 0 |  | 0
20 | Inlet Protection | EA | 16 |  | 0 |  | 0
21 | Traffic Control | LS | 1 |  | 0 |  | 0
22 | Misc. Concrete, 3,000 psi | CY | 5 |  | 0 |  | 0
SubTotal Construction Cost
23 | Mobilization (10% of SubTotal) | 10% | 1
24 | Record Drawings | LS | 1
25 | Contingency (Used with prior County approval only) | 10% | 1
Total Construction Cost
*To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-total, contingency, and total bid price fields.
Bidder:_____________________________________________________
Signature:___________________________________________________