## OVERALL ESTIMATE (hidden)
|  | PROJECT NAME: | SLS R&R 2023 Group 2 - BID FORM
|  | PROJECT NUMBER: | Varies ( See individual Sheet) | [6 empty] | Combined
|  | SECTION / TWNSHP / RANGE: | Varies ( See individual Sheet) | [6 empty] | =MID(CELL("filename"),FIND("]",CELL("filename"))+1,255)
|  | PROJECT DESCRIPTION: | Rehab wetwell, valve vault, & piping for lift station
|  | PROJECT SITE DIMENSIONS: | All work within LS site.
|  | PREPARED BY: | Kyle Wright
LIFT STATION REHABILITATION
| ITEM NO. | DESCRIPTION |  | UNITS | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($) | Bay Drive | Victoria Square East | Cortez Plaza 2 | Cortez Plaza 5
1AA | 1 | Wetwell Cleaning |  | SF |  |  |  | 0 | 0 | 0 | 0
4-8AA | 2 | Wetwell Discharge Piping, HDPE DR-11 |  | LF |  |  |  | 0 | 0 | 0 | 0
20-22AA | 3 | Pump Base Ells, BPIU-14 |  | EA |  |  |  | 0 | 0 | 0 | 0
23-26AA | 4 | Pump Base Ell Mounting Plate |  | EA |  |  |  | 0 | 0 | 0 | 0
26-32AA | 5 | S.S. Pipe Bracing |  | EA |  |  |  | 0 | 0 | 0 | 0
| 6 | Modify Existing Rim Elevation
34-37AA | 6.01 | Wet Well |  | VF |  |  |  | 0 | 0 | 0 | 0
| 7 | Replace Existing Top Slab
38-41AA | 7.01 | Wet Well, thickness varies |  | EA |  |  |  | 0 | 0 | 0 | 0
| 8 | PVC Vent, Sch 80 |  | EA |  |  |  | 0 | 0 | 0 | 0
| 9 | Aluminum Hatch Cover
42-48AA | 9.01 | Wet Well. varies, single door |  | EA |  |  |  | 0 | 0 | 0 | 0
| 10 | S.S.Pump Guide Rail System |  | LF |  |  |  | 0 | 0 | 0 | 0
| 11 | Liner, spray-on |  | SF |  |  |  | 0 | 0 | 0 | 0
49AA | 12 | Remove / Repair Ex. Liner |  | SF |  |  |  | 0 | 0 | 0 | 0
59-65AA | 13 | Grout Fill Ex. Drain, abandon |  | EA |  |  |  | 0 | 0 | 0 | 0
| 14 | Remove & Replace Ex. PVC Drain P-trap (regrout) & Liner Repair |  | EA |  |  |  | 0 | 0 | 0 | 0
| 15 | Gate Valve, FLG |  | EA |  |  |  | 0 | 0 | 0 | 0
| 16 | Swing Check Valve, FLG |  | EA |  |  |  | 0 | 0 | 0 | 0
78-82AA | 17 | Pipe, D.I., FLG |  | LF |  |  |  | 0 | 0 | 0 | 0
1-12P | 18 | Pipe, PVC (DR-18) |  | LF |  |  |  | 0 | 0 | 0 | 0
83-87AA | 19 | Fittings, ductile iron
106-110AA | 19.01 | Tee, FLG |  | EA |  |  |  | 0 | 0 | 0 | 0
88AA | 19.02 | Tee, FLG, w/ side-outlet |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.03 | 90, FLG |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.04 | 90, MJ |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.05 | Reducer, MJ |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.06 | Foster Joint |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.07 | MJ Sleeve |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.08 | Cross, FLG |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.09 | 90, PVC |  | EA |  |  |  | 0 | 0 | 0 | 0
| 19.1 | Van-Stone, flanges |  | EA |  |  |  | 0 | 0 | 0 | 0
95-96AA | 20 | Quick Coupler Adapter, aluminum, male, w/ Alum. Dust Cap |  | EA |  |  |  | 0 | 0 | 0 | 0
97AA | 21 | S.S. Adjustable Valve Supports, FLG attachment |  | EA |  |  |  | 0 | 0 | 0 | 0
| 22 | Complete Removal of Existing Structure |  | EA |  |  |  | 0 | 0 | 0 | 0
| 23 | Concrete Slab, Valve Assembly |  | EA |  |  |  | 0 | 0 | 0 | 0
| 24 | Influent Line Plug |  | EA |  |  |  | 0 | 0 | 0 | 0
116-123AA | 25 | By-Pass Pumping |  | LS |  |  |  | 0 | 0 | 0 | 0
124-127AA | 26 | Water Service Connection and Line |  | LF |  |  |  | 0 | 0 | 0 | 0
129AA | 27 | Install Meter, Backflow, & Hose Bibb Assembly |  | EA |  |  |  | 0 | 0 | 0 | 0
131AA | 28 | Relocate Ex. Meter, Backflow, & Hose Bibb Assembly |  | EA |  |  |  | 0 | 0 | 0 | 0
| 29 | Abandon Ex. Tapping Saddle; Install Brass Plug |  | EA |  |  |  | 0 | 0 | 0 | 0
| 30 | Remove & Replace Electric Meter Can |  | EA |  |  |  | 0 | 0 | 0 | 0
1AB | 31 | Remove & Replace Fused Safety Switch (disconnect) |  | EA |  |  |  | 0 | 0 | 0 | 0
2AB | 32 | Remove & Replace Control Panel |  | EA |  |  |  | 0 | 0 | 0 | 0
4AB | 32.01 | Includes TCU Bubbler Unit (RPT-001) by DFS |  | EA |  |  |  | 0 | 0 | 0 | 0
| 32.02 | Phase Converter, 1 Phase to 3 Phase, inside Control Panel |  | EA |  |  |  | 0 | 0 | 0 | 0
| 32.03 | Remote Emergency Generator Receptacle |  | EA |  |  |  | 0 | 0 | 0 | 0
| 33 | TCU & Fiberglass Enclosure, DFS |  | EA |  |  |  | 0 | 0 | 0 | 0
| 34 | Junction Box, 304 SS |  | EA |  |  |  | 0 | 0 | 0 | 0
| 35 | Remove & Replace PVC Conduit
| 35.01 | Sch 40, 1" |  | LF |  |  |  | 0 | 0 | 0 | 0
19AB | 35.02 | Sch 80, 2" |  | LF |  |  |  | 0 | 0 | 0 | 0
| 36 | Remove & Replace Electrical Service |  | LF |  |  |  | 0 | 0 | 0 | 0
| 37 | Remove & Replace Electrical Mounting Structure |  | EA |  |  |  | 0 | 0 | 0 | 0
25AB | 38 | Elect. System Study & Elect. Study Analysis, (NFPA 70E), complete |  | LS |  |  |  | 0 | 0 | 0 | 0
29AB | 39 | Ex. Antenna Concrete Base, remove & disposal |  | LS |  |  |  | 0 | 0 | 0 | 0
| 40 | Concrete Repair, 2" thick (if required) |  | SF |  |  |  | 0 | 0 | 0 | 0
| 41 | Remove Existing Fence |  | LS |  |  |  | 0 | 0 | 0 | 0
| 42 | Asphalt Pavement Restoration |  | SY |  |  |  | 0 | 0 | 0 | 0
| 43 | Bollards w/ Yellow PVC Covers, red reflector stripe |  | EA |  |  |  | 0 | 0 | 0 | 0
| 44 | Remove Ex. Conc. Bollards |  | EA |  |  |  | 0 | 0 | 0 | 0
| 45 | Washed Shell w/ Weed Barrier |  | SY |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | #REF! | #REF!
|  | Subtotal Construction Cost | [5 empty] | 0 | 0 | 0 | 0
| 46 | Mobilization* | [5 empty] | 0 | 0 | 0 | 0
| 47 | Contract Contingency (10% of Subtotal Construction Cost) |  |  | 10% |  |  | 0 | 0 | 0 | 0
|  | Total Construction Cost | [5 empty] | 0 | 0 | 0 | 0
*(% of Subtotal)
| Note: | Opinion of cost assumes construction to be completed by private contractor.
The 3-year average costs for all items listed have been multiplied by 20% in attempt to account for recent market events.
1000
| 1001 | Influent Drop Bowl/Pipe |  | EA |  |  | 0
| 1002 | New Polymer Concrete Lift Station & Aboveground Valve Assembly |  | LS |  |  | 0
| 1003 | Convert Ex. Lift Station to Concentric Manhole |  | LS |  |  | 0
| 1004 | Site Demolition |  | LS |  |  | 0
| 1005 | Tree Removal; 1"-6" |  | EA |  |  | 0
| 1006 | Fill Dirt, clean and compacted |  | CY |  |  | 0
| 1007 | Retaining Wall, railroad tie construction |  | LS |  |  | 0
| 1008 | Site Demolition |  | LS |  |  | 0
| 1009 | Reinforced Concrete Slab (poured in place) |  | SY |  |  | 0
| 1010 | Emergency Backup Pump & Fuel Tank |  | LS |  |  | 0
| 1011 | PVC Pipe (C900, DR-18), 6" (Pump Discharge Line) |  | LF |  |  | 0
| 1012 | HDPE DR-11, 8" (Pump Suction Line) |  | LF |  |  | 0
| 1013 | Ductile Iron Fittings
| 1013.1 | Red., FLG, 4"x6" |  | EA |  |  | 0
| 1013.2 | Red., FLG, 4"x8" |  | EA |  |  | 0
| 1013.3 | 45, MJ, 6" |  | EA |  |  | 0
| 1013.4 | 90, FLG, 6" |  | EA |  |  | 0
| 1013.5 | 45, FLG, 8" |  | EA |  |  | 0
| 1013.6 | 90, FLG. 8" |  | EA |  |  | 0
| 1013.7 | 90, MJ, 8" |  | EA |  |  | 0
| 1013.8 | 90, HDPE Molded , Fusion Welded, 8" |  | EA |  |  | 0
| 1014 | Sch 80 PVC Conduit, 2" |  | LF |  |  | 0
| 1015 | Level Transducer, GXS3-PP300-A49-B49-50-C01-D49 |  | EA |  |  | 0
| 1016 | PVC Stilling Well, 6" |  | LF |  |  | 0
| 1017 | Permits |  | LS |  |  | 0

## Bay Drive, RTU 102
|  | PROJECT NAME: | SLS R&R 2023 Group 2 - BID FORM
|  | PROJECT NUMBER: | 402-5120481
|  | SECTION / TWNSHP / RANGE: | 11/35/17
|  | PROJECT DESCRIPTION: | Rehab wetwell & valve vault piping for lift station.
|  | PROJECT SITE DIMENSIONS: | All work within lift station site.
|  | PREPARED BY: | Kyle Wright
APPENDIX L, BID PRICING FORM
IFBC NO. 23-TA004831SAM
PROJECT NAME: SATELLITE LIFT STATION R&R 2023 GROUP 2
Bidders must provide pricing for each available item with a quantity for their bid to be considered responsive.
LIFT STATION REHABILITATION - BAY DRIVE, RTU 102 (PROJECT #5120481)
| ITEM NO. | DESCRIPTION |  | U/M | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($)
1AA | 1 | Wetwell Cleaning |  | SF | 260 |  | 0
4-8AA | 2 | Wetwell Discharge Piping, HDPE DR-11, 4" |  | LF | 54 |  | 0 |  | 4
20-22AA | 3 | Pump Base Ells, BPIU-14 |  | EA | 2 |  | 0
23-26AA | 4 | Pump Base Ell Mounting Plate |  | EA | 2 |  | 0
26-32AA | 5 | S.S. Pipe Bracing, 4 ft |  | EA | 3 |  | 0
| 6 | Intentionally Left Blank
34-37AA | 6.01 | Intentionally Left Blank
| 7 | Replace Existing Top Slab
38-41AA | 7.01 | Wet Well, thickness 10" |  | EA | 1 |  | 0
| 8 | PVC Vent, Sch 80, 2" |  | EA | 1 |  | 0
42-48AA | 9 | Aluminum Hatch Cover
| 9.01 | Wet Well. 30" x 42", single door |  | EA | 1 |  | 0 |  |  |  |  | Hatch Cover Size Requirements
49AA | 10 | S.S.Pump Guide Rail System, 2" |  | LF | 38 |  | 0 |  |  |  |  | Disch Pipe Size |  | Hatch Size | WW Dia. Range
59-65AA | 11 | Liner, spray-on |  | SF | 260 |  | 0 |  |  |  |  | 3" |  | 30"x32" | 41" | *side-out let tee
| 12 | Remove / Repair Ex. Liner |  | SF | 260 |  | 0 |  |  |  |  | 4"* |  | 30"x42" | 4' | *side-out let tee
| 13 | Intentionally Left Blank | [9 empty] | 4" |  | 30"x48" | 5'
| 14 | Intentionally Left Blank | [9 empty] | 4" |  | 36"x48" | 6'
73-77AA | 15 | Gate Valve, FLG, 4" |  | EA | 3 |  | 0 |  |  |  |  | 6" |  | 36"x60" | 6', 8'
78-82AA | 16 | Swing Check Valve, FLG, 4" |  | EA | 2 |  | 0 |  |  |  |  | 8" |  | 36"x72" | 8'
83-87AA | 17 | Pipe, D.I., FLG, 4" |  | LF | 5 |  | 0
106-110AA | 18 | Pipe, PVC (DR-18), 3" |  | LF | 10 |  | 0
88AA | 19 | Fittings, ductile iron
| 19.01 | Intentionally Left Blank
| 19.02 | Tee, FLG, w/ side-outlet 4" |  | EA | 1 |  | 0
| 19.03 | 90, FLG, 4" |  | EA | 1 |  | 0
| 19.04 | 90, MJ, 4" |  | EA | 1 |  | 0
| 19.05 | Reducer, MJ, 3"x4" |  | EA | 1 |  | 0
| 19.06 | Foster Joint, 4" |  | EA | 1 |  | 0
| 19.07 | MJ Sleeve, 3" |  | EA | 1 |  | 0
| 19.08 | Intentionally Left Blank
| 19.09 | Intentionally Left Blank
| 19.1 | Intentionally Left Blank
95-96AA | 20 | Quick Coupler Adapter, aluminum, male, w/ Alum. Dust Cap, 4" |  | EA | 1 |  | 0
97AA | 21 | S.S. Adjustable Valve Supports, FLG attachment |  | EA | 2 |  | 0
| 22 | Complete Removal of Existing Structure |  | EA | 1 |  | 0
| 23 | Concrete Slab, Valve Assembly |  | EA | 1 |  | 0
116-123AA | 24 | Influent Line Plug, 8" |  | EA | 2 |  | 0
124-127AA | 25 | By-Pass Pumping |  | LS | 1 |  | 0
129AA | 26 | Water Service Connection and Line, 2" |  | LF | 10 |  | 0
131AA | 27 | Install Meter, Backflow, & Hose Bibb Assembly, standard |  | EA | 1 |  | 0
| 28 | Intentionally Left Blank
| 29 | Replace Ex. Tapping Saddle; Install Brass Plug |  | EA | 1 |  | 0
1AB | 30 | Remove & Replace Electric Meter Can |  | EA | 1 |  | 0
2AB | 31 | Remove & Replace Fused Safety Switch (disconnect) |  | EA | 1 |  | 0
4AB | 32 | Remove & Replace Control Panel (2020 Standard) |  | EA | 1 |  | 0
| 32.01 | Includes TCU Bubbler Unit (RPT-001) by DFS |  | EA | 1 |  | 0
| 32.02 | Phase Converter, 1 Phase to 3 Phase, inside Control Panel |  | EA | 2 |  | 0
| 32.03 | Intentionally Left Blank |  |  |  |  | 0
| 33 | TCU & Fiberglass Enclosure, DFS (use with 2020 standard) |  | EA | 1 |  | 0
| 34 | Junction Box, 304 SS (use with 2020 standard) |  | EA | 1 |  | 0
19AB | 35 | Remove & Replace PVC Conduit
| 35.01 | Sch 40, 1" |  | LF | 10 |  | 0
| 35.02 | Sch 80, 2" |  | LF | 30 |  | 0
25AB | 36 | Intentionally Left Blank
29AB | 37 | Remove & Replace Electrical Mounting Structure |  | EA | 1 |  | 0
| 38 | Elect. System Study & Elect. Study Analysis, (NFPA 70E), complete |  | LS | 1 |  | 0
| 39 | Intentionally Left Blank
| 40 | Concrete Repair, 2" thick (if required) |  | SF | 130 |  | 0
| 41 | Intentionally Left Blank
| 42 | Intentionally Left Blank
| 43 | Intentionally Left Blank
| 44 | Intentionally Left Blank
| 45 | Intentionally Left Blank
|  | Subtotal Construction Cost Bay Drive, RTU 102 (Project #5120481) | [7 empty] | Design Point: | 100 | @ | 15
| 46 | Mobilization (NTE 10%) | [10 empty] | 1 pump | 2 pumps (150%)
| 47 | Contract Contingency (10% of Subtotal Construction Cost, County Authorized Use Only) |  |  | 10% | [5 empty] | Dia. Disch. Pipe (in) | Design Flow (gpm) | Vel. In Disch. Pipe (f/s) | Vel. In Disch. Pipe (f/s)
|  | Total Construction Cost for Bay Drive, RTU 102 (Project #5120481) | [5 empty] | 10% |  |  | 3.89 | 100 | 2.7009 | 4.0514
|  | *(% of Subtotal) | [10 empty] | Keep Size
| Note: | Opinion of cost assumes construction to be completed by private contractor.
The 3-year average costs for all items listed have been multiplied by 20% in attempt to account for recent market events.
If Vel. In Disch. Pipe (1 pump) ≥ 8 f/s upsize pipe diameter
|  | taken from Lsinfo 2018 |  | Top Elevation: | 9.2 | NGVD | WW Depth: |  |  |  | DIA. | HDPE ID | PVC ID | Sch 80
|  |  |  | Bottom Elevation: | -9.5 | NGVD | 18.7
|  |  |  | Wet Well Dia: | 4 | ft |  |  |  |  | 2 |  |  | 2.047
|  |  |  | WW2Cross: | 6 | ft | No. of Pumps |  |  |  | 4 | 3.89 | 4.27
|  |  |  | Cross2P.V.: | 4 | ft | 2 |  |  |  | 6 | 5.59 | 6.13
|  |  |  | Top or Bottom Surface Area: | 13 | sq-ft |  |  |  |  | 8 | 7.34 | 8.04
|  |  |  | Total Internal Surface Area: | 260 | sq-ft | Add Stilling Well |  |  |  | 10 | 8.96 |  |  |  | Yes
|  |  |  | Wall Surface Area: | 234 | sq-ft | No |  |  |  | 12 | 10.66 |  |  |  | No
|  |  |  | Wet Well to be Raised/(Lowered): | 0 | ft
|  |  |  | Valve Vault to be Raised: | 0 | ft | New Spray Liner
|  |  |  | Meter Vault to be Raised: | 0 | ft | Yes
|  |  |  | Concrete Floor & Fillit Concrete Vol: | 2 | cu-yd
Above Ground Valve Assembly
Yes
Replace Guide Rails?
Yes
| 1000 | Influent Drop Bowl/Pipe |  | EA |  |  | 0
|  | New Polymer Concrete Lift Station & Aboveground Valve Assembly |  | LS |  |  | 0
| 1001 | Convert Ex. Lift Station to Concentric Manhole |  | LS |  |  | 0
| 1002 | Site Demolition |  | LS |  |  | 0
1003
1004
|  | Tree Removal; 1"-6" |  | EA |  |  | 0
|  | Fill Dirt, clean and compacted |  | CY |  |  | 0
| 1005 | Retaining Wall, railroad tie construction |  | LS |  |  | 0
| 1006 | Site Demolition |  | LS |  |  | 0
| 1007 | Reinforced Concrete Slab (poured in place) |  | SY |  |  | 0
| 1008 | Emergency Backup Pump & Fuel Tank |  | LS |  |  | 0
| 1009 | PVC Pipe (C900, DR-18), 6" (Pump Discharge Line) |  | LF |  |  | 0
| 1010 | HDPE DR-11, 8" (Pump Suction Line) |  | LF |  |  | 0
| 1011 | Ductile Iron Fittings
| 1012 | Red., FLG, 4"x6" |  | EA |  |  | 0
| 1013 | Red., FLG, 4"x8" |  | EA |  |  | 0
| 1013.1 | 45, MJ, 6" |  | EA |  |  | 0
| 1013.2 | 90, FLG, 6" |  | EA |  |  | 0
| 1013.3 | 45, FLG, 8" |  | EA |  |  | 0
| 1013.4 | 90, FLG. 8" |  | EA |  |  | 0
| 1013.5 | 90, MJ, 8" |  | EA |  |  | 0
| 1013.6 | 90, HDPE Molded , Fusion Welded, 8" |  | EA |  |  | 0
| 1013.7 | Sch 80 PVC Conduit, 2" |  | LF |  |  | 0
| 1013.8 | Level Transducer, GXS3-PP300-A49-B49-50-C01-D49 |  | EA |  |  | 0
| 1014 | PVC Stilling Well, 6" |  | LF |  |  | 0
| 1015 | Permits |  | LS |  |  | 0
1016
1017
**To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-totals, contingencies, and total bid prices for each lift station.**

## Cortez Plaza 5, RTU 423
|  | PROJECT NAME: | SLS R&R 2023 Group 2 - BID FORM
|  | PROJECT NUMBER: | 402-5120482
|  | SECTION / TWNSHP / RANGE: | 11/35/17
|  | PROJECT DESCRIPTION: | Rehab wetwell & valve vault piping for lift station.
|  | PROJECT SITE DIMENSIONS: | All work within lift station site.
|  | PREPARED BY: | Kyle Wright
APPENDIX L, BID PRICING FORM
IFBC NO. 23-TA004831SAM
PROJECT NAME: SATELLITE LIFT STATION R&R 2023 GROUP 2
Bidders must provide pricing for each available item with a quantity for their bid to be considered responsive.
LIFT STATION REHABILITATION - CORTEZ PLAZA 5, RTU 423 (PROJECT #5120482)
| ITEM NO. | DESCRIPTION |  | U/M | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($)
1AA | 1 | Wetwell Cleaning |  | SF | 209 |  | 0
4-8AA | 2 | Wetwell Discharge Piping, PVC Schedule 80, 3" |  | LF | 27 |  | 0 |  | 4
20-22AA | 3 | Pump Base Ells, BPIU-13 |  | EA | 2 |  | 0
23-26AA | 4 | Pump Base Ell Mounting Plate |  | EA | 2 |  | 0
26-32AA | 5 | S.S. Pipe Bracing, 4 ft dia. |  | EA | 2 |  | 0
| 6 | Modify Existing Rim Elevation
34-37AA | 6.01 | Wet Well |  | VF | 0.5 |  | 0
| 7 | Replace Existing Top Slab
38-41AA | 7.01 | Wet Well, thickness, 6' Dia. 10" |  | EA | 1 |  | 0
| 8 | PVC Vent, Sch 80, 2" |  | EA | 1 |  | 0
42-48AA | 9 | Aluminum Hatch Cover
| 9.01 | Wet Well. 30" x 42", single door |  | EA | 1 |  | 0 |  |  |  |  | Hatch Cover Size Requirements
49AA | 10 | S.S.Pump Guide Rail System, 1.5" |  | LF | 30 |  | 0 |  |  |  |  | Disch Pipe Size |  | Hatch Size | WW Dia. Range
59-65AA | 11 | Liner, spray-on |  | SF | 209 |  | 0 |  |  |  |  | 3" |  | 30"x32" | 41" | *side-out let tee
| 12 | Intentionally Left Blank | [9 empty] | 4"* |  | 30"x42" | 4' | *side-out let tee
| 13 | Intentionally Left Blank | [9 empty] | 4" |  | 30"x48" | 5'
| 14 | Remove & Replace Ex. PVC Drain P-trap (regrout) & Liner Repair |  | EA | 1 |  | 0 |  |  |  |  | 4" |  | 36"x48" | 6'
73-77AA | 15 | Gate Valve, THD, 3" (brass w/ hand wheel) |  | EA | 3 |  | 0 |  |  |  |  | 6" |  | 36"x60" | 6', 8'
78-82AA | 16 | Swing Check Valve, THD, 3" |  | EA | 2 |  | 0 |  |  |  |  | 8" |  | 36"x72" | 8'
83-87AA | 17 | Intentionally Left Blank
106-110AA | 18 | Intentionally Left Blank
88AA | 19 | Fittings, PVC
| 19.01 | Intentionally Left Blank
| 19.02 | Intentionally Left Blank
| 19.03 | Intentionally Left Blank
| 19.04 | Intentionally Left Blank
| 19.05 | Intentionally Left Blank
| 19.06 | Intentionally Left Blank
| 19.07 | Intentionally Left Blank
| 19.08 | Cross, 3" |  | EA | 1 |  | 0
| 19.09 | 90, PVC, 3" |  | EA | 2 |  | 0
| 19.1 | Van-Stone, flanges, 3" |  | EA | 3 |  | 0
95-96AA | 20 | Quick Coupler Adapter, aluminum, male, w/ Alum. Dust Cap, 4" |  | EA | 1 |  | 0
97AA | 21 | Intentionally Left Blank
| 22 | Intentionally Left Blank
| 23 | Intentionally Left Blank
116-123AA | 24 | Influent Line Plug, 8" |  | EA | 1 |  | 0
124-127AA | 25 | By-Pass Pumping |  | LS | 1 |  | 0
129AA | 26 | Intentionally Left Blank
131AA | 27 | Intentionally Left Blank
| 28 | Intentionally Left Blank
| 29 | Intentionally Left Blank
1AB | 30 | Intentionally Left Blank
2AB | 31 | Remove & Replace Fused Safety Switch (disconnect) |  | EA | 1 |  | 0
4AB | 32 | Remove & Replace Control Panel (2020 Standard) |  | EA | 1 |  | 0
| 32.01 | Includes TCU Bubbler Unit (RPT-001) by DFS |  | EA | 1 |  | 0
| 32.02 | Intentionally Left Blank
| 32.03 | Intentionally Left Blank
| 33 | TCU & Fiberglass Enclosure, DFS (use with 2020 standard) |  | EA | 1 |  | 0
| 34 | Junction Box, 304 SS (use with 2020 standard) |  | EA | 1 |  | 0
19AB | 35 | Remove & Replace PVC Conduit
| 35.01 | Sch 40, 1" |  | LF | 10 |  | 0
| 35.02 | Sch 80, 2" |  | LF | 30 |  | 0
25AB | 36 | Remove & Replace Electrical Service |  | LF | 10 |  | 0
29AB | 37 | Remove & Replace Electrical Mounting Structure |  | EA | 1 |  | 0
| 38 | Elect. System Study & Elect. Study Analysis, (NFPA 70E), complete |  | LS | 1 |  | 0
| 39 | Intentionally Left Blank
| 40 | Concrete Repair, 2" thick (if required) |  | SF | 105 |  | 0
53AA | 41 | Intentionally Left Blank
| 42 | Asphalt Pavement Restoration |  | SY | 20 |  | 0
| 43 | Intentionally Left Blank
| 44 | Intentionally Left Blank
| 45 | Intentionally Left Blank
|  | Subtotal Construction Cost - Cortez Plaza 5, RTU 423 (Project #5120482) | [7 empty] | Design Point: | 150 | @ | 17
| 46 | Mobilization (NTE 10%) | [5 empty] | 10% |  |  |  |  | 1 pump | 2 pumps (150%)
| 47 | Contract Contingency (10% of Subtotal Construction Cost, County Authoirzed Use Only) |  |  | 10% | [5 empty] | Dia. Disch. Pipe (in) | Design Flow (gpm) | Vel. In Disch. Pipe (f/s) | Vel. In Disch. Pipe (f/s)
|  | Total Construction Cost - Cortez Plaza 5, RTU 423 (Project #5120482) | [8 empty] | 3.89 | 150 | 4.0514 | 6.0771
|  | *(% of Subtotal) | [10 empty] | Keep Size
| Note: | Opinion of cost assumes construction to be completed by private contractor. | [8 empty] | If Vel. In Disch. Pipe (1 pump) ≥ 8 f/s upsize pipe diameter
The 3-year average costs for all items listed have been multiplied by 20% in attempt to account for recent market events.
|  | taken from Lsinfo 2018 |  | Top Elevation: | 12.31 | NGVD | WW Depth: |  |  |  | DIA. | HDPE ID | PVC ID | Sch 80
|  |  |  | Bottom Elevation: | -2.83 | NGVD | 14.64
|  |  |  | Wet Well Dia: | 4 | ft |  |  |  |  | 2 |  |  | 2.047
|  |  |  | WW2Cross: | 0 | ft | No. of Pumps |  |  |  | 4 | 3.89 | 4.27
|  |  |  | Cross2P.V.: | 0 | ft | 2 |  |  |  | 6 | 5.59 | 6.13 |  |  | Yes
|  |  |  | Top or Bottom Surface Area: | 13 | sq-ft |  |  |  |  | 8 | 7.34 | 8.04 |  |  | No
|  |  |  | Total Internal Surface Area: | 209 | sq-ft | Add Stilling Well
|  |  |  | Wall Surface Area: | 183 | sq-ft | No
|  |  |  | Wet Well to be Raised/(Lowered): | -0.5 | ft
|  |  |  | Valve Vault to be Raised: | 0 | ft | New Spray Liner
|  |  |  | Meter Vault to be Raised: | 0 | ft | Yes
|  |  |  | Concrete Floor & Fillit Concrete Vol: | 2 | cu-yd
Above Ground Valve Assembly
No
Replace Guide Rails?
Yes
1000
| 1001 | Influent Drop Bowl/Pipe |  | EA |  |  | 0
| 1002 | New Polymer Concrete Lift Station & Aboveground Valve Assembly |  | LS |  |  | 0
| 1003 | Convert Ex. Lift Station to Concentric Manhole |  | LS |  |  | 0
| 1004 | Site Demolition |  | LS |  |  | 0
| 1005 | Tree Removal; 1"-6" |  | EA |  |  | 0
| 1006 | Fill Dirt, clean and compacted |  | CY |  |  | 0
| 1007 | Retaining Wall, railroad tie construction |  | LS |  |  | 0
| 1008 | Site Demolition |  | LS |  |  | 0
| 1009 | Reinforced Concrete Slab (poured in place) |  | SY |  |  | 0
| 1010 | Emergency Backup Pump & Fuel Tank |  | LS |  |  | 0
| 1011 | PVC Pipe (C900, DR-18), 6" (Pump Discharge Line) |  | LF |  |  | 0
| 1012 | HDPE DR-11, 8" (Pump Suction Line) |  | LF |  |  | 0
| 1013 | Ductile Iron Fittings
| 1013.1 | Red., FLG, 4"x6" |  | EA |  |  | 0
| 1013.2 | Red., FLG, 4"x8" |  | EA |  |  | 0
| 1013.3 | 45, MJ, 6" |  | EA |  |  | 0
| 1013.4 | 90, FLG, 6" |  | EA |  |  | 0
| 1013.5 | 45, FLG, 8" |  | EA |  |  | 0
| 1013.6 | 90, FLG. 8" |  | EA |  |  | 0
| 1013.7 | 90, MJ, 8" |  | EA |  |  | 0
| 1013.8 | 90, HDPE Molded , Fusion Welded, 8" |  | EA |  |  | 0
| 1014 | Sch 80 PVC Conduit, 2" |  | LF |  |  | 0
| 1015 | Level Transducer, GXS3-PP300-A49-B49-50-C01-D49 |  | EA |  |  | 0
| 1016 | PVC Stilling Well, 6" |  | LF |  |  | 0
| 1017 | Permits |  | LS |  |  | 0
**To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-totals, contingencies, and total bid prices for each lift station.**

## Cortez Plaza 2, RTU 420
|  | PROJECT NAME: | SLS R&R 2023 Group 2 - BID FORM
|  | PROJECT NUMBER: | 402-5120483
|  | SECTION / TWNSHP / RANGE: | 11/35/17
|  | PROJECT DESCRIPTION: | Rehab wetwell & valve vault piping for lift station.
|  | PROJECT SITE DIMENSIONS: | All work within lift station site.
|  | PREPARED BY: | Kyle Wright
APPENDIX L, BID PRICING FORM
IFBC NO. 23-TA004831SAM
PROJECT NAME: SATELLITE LIFT STATION R&R 2023 GROUP 2
Bidders must provide pricing for each available item with a quantity for their bid to be considered responsive.
4-8AA | LIFT STATION REHABILITATION - CORTEZ PLAZA 2, RTU 420 (PROJECT #5120483) | [7 empty] | 4
20-22AA | ITEM NO. | DESCRIPTION |  | U/M | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($)
23-26AA | 1 | Wetwell Cleaning |  | SF | 340 |  | 0
26-32AA | 2 | Wetwell Discharge Piping, HDPE DR-11, 4" |  | LF | 43 |  | 0
| 3 | Pump Base Ells, BPIU-14 |  | EA | 2 |  | 0
34-37AA | 4 | Pump Base Ell Mounting Plate |  | EA | 2 |  | 0
| 5 | S.S. Pipe Bracing, 6 ft |  | EA | 2 |  | 0
38-41AA | 6 | Intentionally Left Blank
| 6.01 | Intentionally Left Blank |  |  |  |  | 0
42-48AA | 7 | Replace Existing Top Slab
| 7.01 | Wet Well, thickness 10" |  | EA | 1 |  | 0 |  |  |  | Hatch Cover Size Requirements
49AA | 8 | PVC Vent, Sch 80, 4" |  | EA | 1 |  | 0 |  |  |  | Disch Pipe Size |  | Hatch Size | WW Dia. Range
59-65AA | 9 | Aluminum Hatch Cover | [8 empty] | 3" |  | 30"x32" | 41" | *side-out let tee
| 9.01 | Wet Well. 36" x 48", single door |  | EA | 1 |  | 0 |  |  |  | 4"* |  | 30"x42" | 4' | *side-out let tee
| 10 | S.S.Pump Guide Rail System, 2" |  | LF | 30 |  | 0 |  |  |  | 4" |  | 30"x48" | 5'
| 11 | Liner, spray-on |  | SF | 340 |  | 0 |  |  |  | 4" |  | 36"x48" | 6'
73-77AA | 12 | Intentionally Left Blank | [8 empty] | 6" |  | 36"x60" | 6', 8'
78-82AA | 13 | Intentionally Left Blank | [8 empty] | 8" |  | 36"x72" | 8'
83-87AA | 14 | Intentionally Left Blank
106-110AA | 15 | Gate Valve, FLG, 4" |  | EA | 3 |  | 0
88AA | 16 | Swing Check Valve, FLG, 4" |  | EA | 2 |  | 0
| 17 | Pipe, D.I., FLG, 4" |  | LF | 5 |  | 0
| 18 | Pipe, PVC (DR-18), 4" |  | LF | 8.5 |  | 0
| 19 | Fittings, ductile iron
| 19.01 | Tee, FLG, 4" |  | EA | 2 |  | 0
| 19.02 | Intentionally Left Blank
| 19.03 | 90, FLG, 4" |  | EA | 1 |  | 0
| 19.04 | 90, MJ, 4" |  | EA | 1 |  | 0
| 19.05 | Intentionally Left Blank
| 19.06 | Intentionally Left Blank
| 19.07 | MJ Sleeve, 4" |  | EA | 1 |  | 0
95-96AA | 19.08 | Intentionally Left Blank
97AA | 19.09 | Intentionally Left Blank
| 19.1 | Intentionally Left Blank
| 20 | Quick Coupler Adapter, aluminum, male, w/ Alum. Dust Cap, 4" |  | EA | 1 |  | 0
116-123AA | 21 | S.S. Adjustable Valve Supports, FLG attachment |  | EA | 2 |  | 0
124-127AA | 22 | Complete Removal of Existing Structure |  | EA | 1 |  | 0
129AA | 23 | Concrete Slab, Valve Assembly |  | EA | 1 |  | 0
131AA | 24 | Influent Line Plug, 8" |  | EA | 1 |  | 0
| 25 | By-Pass Pumping |  | LS | 1 |  | 0
| 26 | Water Service Connection and Line |  | LF | 15 |  | 0
1AB | 27 | Intentionally Left Blank
2AB | 28 | Relocate Ex. Meter, Backflow, & Hose Bibb Assembly |  | EA | 1 |  | 0
4AB | 29 | Intentionally Left Blank
| 30 | Remove & Replace Electric Meter Can |  | EA | 1 |  | 0
| 31 | Remove & Replace Fused Safety Switch (disconnect) |  | EA | 1 |  | 0
| 32 | Remove & Replace Control Panel (2020 Standard) |  | EA | 1 |  | 0
| 32.01 | Includes TCU Bubbler Unit (RPT-001) by DFS |  | EA | 1 |  | 0
| 32.02 | Intentionally Left Blank
19AB | 32.03 | Intentionally Left Blank
| 33 | TCU & Fiberglass Enclosure, DFS (use with 2020 standard) |  | EA | 1 |  | 0
| 34 | Junction Box, 304 SS (use with 2020 standard) |  | EA | 1 |  | 0
25AB | 35 | Remove & Replace PVC Conduit
29AB | 35.01 | Sch 40, 1" |  | LF | 10 |  | 0
| 35.02 | Sch 80, 2" |  | LF | 30 |  | 0
| 36 | Remove & Replace Electrical Service |  | LF | 15 |  | 0
| 37 | Remove & Replace Electrical Mounting Structure |  | EA | 1 |  | 0
| 38 | Elect. System Study & Elect. Study Analysis, (NFPA 70E), complete |  | LS | 1 |  | 0
| 39 | Ex. Antenna Concrete Base, remove & disposal |  | LS | 1 |  | 0
| 40 | Concrete Repair, 2" thick (if required) |  | SF | 170 |  | 0
| 41 | Intentionally Left Blank
| 42 | Intentionally Left Blank
| 43 | Bollards w/ Yellow PVC Covers, red reflector stripe |  | EA | 6 |  | 0
| 44 | Remove Ex. Bollards |  | EA | 4 |  | 0
| 45 | Washed Shell w/ Weed Barrier |  | SY | 23 |  | 0 | 10%
Subtotal Construction Cost - Cortez Plaza 2, RTU 420 (Project #5120483)
| 46 | Mobilization (NTE 10%)
| 47 | Contract Contingency (10% of Subtotal Construction Cost, County Authoirzed Use Only) |  |  | 10%
Total Construction Cost - Cortez Plaza 2, RTU 420 (Project #5120483)
*(% of Subtotal)
| Note: | Opinion of cost assumes construction to be completed by private contractor.
The 3-year average costs for all items listed have been multiplied by 20% in attempt to account for recent market events.
[10 empty] | Design Point: | 220 | @ | 23
|  | taken from Lsinfo 2018 |  | Top Elevation: | 17.38 | NGVD | WW Depth: | [5 empty] | 1 pump | 2 pumps (150%)
|  |  |  | Bottom Elevation: | 2.38 | NGVD | 15 |  |  |  | Dia. Disch. Pipe (in) | Design Flow (gpm) | Vel. In Disch. Pipe (f/s) | Vel. In Disch. Pipe (f/s)
|  |  |  | Wet Well Dia: | 6 | ft |  |  |  |  | 3.89 | 220 | 5.942 | 8.913
|  |  |  | WW2Cross: | 4.5 | ft | No. of Pumps | [5 empty] | Keep Size
|  |  |  | Cross2P.V.: | 4 | ft | 2
|  |  |  | Top or Bottom Surface Area: | 29 | sq-ft
|  |  |  | Total Internal Surface Area: | 340 | sq-ft | Add Stilling Well
|  |  |  | Wall Surface Area: | 282 | sq-ft | No |  |  |  | If Vel. In Disch. Pipe (1 pump) ≥ 8 f/s upsize pipe diameter
|  |  |  | Wet Well to be Raised/(Lowered): | 0 | ft |  |  |  |  | DIA. | HDPE ID | PVC ID | Sch 80
|  |  |  | Valve Vault to be Raised: | 0 | ft | New Spray Liner
|  |  |  | Meter Vault to be Raised: | 0 | ft | Yes |  |  |  | 2 |  |  | 2.047
|  |  |  | Concrete Floor & Fillit Concrete Vol: | 2 | cu-yd |  |  |  |  | 4 | 3.89 | 4.27
[7 empty] | Above Ground Valve Assembly |  |  |  | 6 | 5.59 | 6.13
[7 empty] | Yes |  |  |  | 8 | 7.34 | 8.04 |  |  | Yes
[11 empty] | 10 | 8.96 |  |  |  | No
[7 empty] | Replace Guide Rails? |  |  |  | 12 | 10.66
Yes
1000
1001
1002
| 1003 | Influent Drop Bowl/Pipe |  | EA |  |  | 0
| 1004 | New Polymer Concrete Lift Station & Aboveground Valve Assembly |  | LS |  |  | 0
|  | Convert Ex. Lift Station to Concentric Manhole |  | LS |  |  | 0
|  | Site Demolition |  | LS |  |  | 0
1005
1006
| 1007 | Tree Removal; 1"-6" |  | EA |  |  | 0
| 1008 | Fill Dirt, clean and compacted |  | CY |  |  | 0
| 1009 | Retaining Wall, railroad tie construction |  | LS |  |  | 0
| 1010 | Site Demolition |  | LS |  |  | 0
| 1011 | Reinforced Concrete Slab (poured in place) |  | SY |  |  | 0
| 1012 | Emergency Backup Pump & Fuel Tank |  | LS |  |  | 0
| 1013 | PVC Pipe (C900, DR-18), 6" (Pump Discharge Line) |  | LF |  |  | 0
| 1013.1 | HDPE DR-11, 8" (Pump Suction Line) |  | LF |  |  | 0
| 1013.2 | Ductile Iron Fittings
| 1013.3 | Red., FLG, 4"x6" |  | EA |  |  | 0
| 1013.4 | Red., FLG, 4"x8" |  | EA |  |  | 0
| 1013.5 | 45, MJ, 6" |  | EA |  |  | 0
| 1013.6 | 90, FLG, 6" |  | EA |  |  | 0
| 1013.7 | 45, FLG, 8" |  | EA |  |  | 0
| 1013.8 | 90, FLG. 8" |  | EA |  |  | 0
| 1014 | 90, MJ, 8" |  | EA |  |  | 0
| 1015 | 90, HDPE Molded , Fusion Welded, 8" |  | EA |  |  | 0
| 1016 | Sch 80 PVC Conduit, 2" |  | LF |  |  | 0
| 1017 | Level Transducer, GXS3-PP300-A49-B49-50-C01-D49 |  | EA |  |  | 0
|  | PVC Stilling Well, 6" |  | LF |  |  | 0
|  | Permits |  | LS |  |  | 0
**To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-totals, contingencies, and total bid prices for each lift station.**

## Victoria SQ, RTU 111
|  | PROJECT NAME: | SLS R&R 2023 Group 2 - BID FORM
|  | PROJECT NUMBER: | 402-5120484
|  | SECTION / TWNSHP / RANGE: | 10/35/17
|  | PROJECT DESCRIPTION: | Rehab wetwell & valve vault piping for lift station
|  | PROJECT SITE DIMENSIONS: | All work within lift station site
|  | PREPARED BY: | Kyle Wright
APPENDIX L, BID PRICING FORM
IFBC NO. 23-TA004831SAM
PROJECT NAME: SATELLITE LIFT STATION R&R 2023 GROUP 2
1AA | Bidders must provide pricing for each available item with a quantity for their bid to be considered responsive.
4-8AA | LIFT STATION REHABILITATION - VICTORIA SQ, RTU 111 (PROJECT #5120484) | [7 empty] | 4
20-22AA | ITEM NO. | DESCRIPTION |  | U/M | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($)
23-26AA | 1 | Wetwell Cleaning |  | SF | 120 |  | 0
26-32AA | 2 | Wetwell Discharge Piping, HDPE DR-11, 4" |  | LF | 32 |  | 0
| 3 | Pump Base Ells, BPIU-14 |  | EA | 2 |  | 0
34-37AA | 4 | Pump Base Ell Mounting Plate |  | EA | 2 |  | 0
| 5 | S.S. Pipe Bracing, 4 ft dia. |  | EA | 2 |  | 0
38-41AA | 6 | Intentionally Left Blank
| 6.01 | Intentionally Left Blank
42-48AA | 7 | Replace Existing Top Slab
| 7.01 | Wet Well, thickness 10" |  | EA | 1 |  | 0 |  |  |  |  | Hatch Cover Size Requirements
49AA | 8 | PVC Vent, Sch 80, 2" |  | EA | 1 |  | 0 |  |  |  |  | Disch Pipe Size |  | Hatch Size | WW Dia. Range
59-65AA | 9 | Aluminum Hatch Cover
| 9.01 | Wet Well. 30" x 42", single door |  | EA | 1 |  | 0 |  |  |  |  | 4"* |  | 30"x42" | 4' | *side-out let tee
| 10 | 2" S.S.Pump Guide Rail System, 2" |  | LF | 15 |  | 0 |  |  |  |  | 4" |  | 30"x48" | 5'
| 11 | Liner, spray-on |  | SF | 120 |  | 0 |  |  |  |  | 4" |  | 36"x48" | 6'
73-77AA | 12 | Intentionally Left Blank | [9 empty] | 6" |  | 36"x60" | 6', 8'
78-82AA | 13 | Grout Fill Ex. Drain, abandon |  | EA | 1 |  | 0 |  |  |  |  | 8" |  | 36"x72" | 8'
83-87AA | 14 | Intentionally Left Blank
106-110AA | 15 | Gate Valve, FLG, 4" |  | EA | 3 |  | 0
88AA | 16 | Swing Check Valve, FLG, 4" |  | EA | 2 |  | 0
| 17 | Pipe, D.I., FLG, 4" |  | LF | 5 |  | 0
| 18 | Pipe, PVC (DR-18), 4" |  | LF | 9.5 |  | 0
| 19 | Fittings, ductile iron
| 19.01 | Intentionally Left Blank
| 19.02 | Tee, FLG, w/ side-outlet 4" |  | EA | 1 |  | 0
| 19.03 | 90, FLG, 4" |  | EA | 1 |  | 0
| 19.04 | 90, MJ, 4" |  | EA | 1 |  | 0
| 19.05 | Intentionally Left Blank
| 19.06 | Intentionally Left Blank
| 19.07 | MJ Sleeve, 4" |  | EA | 1 |  | 0
95-96AA | 19.08 | Intentionally Left Blank
97AA | 19.09 | Intentionally Left Blank
| 19.1 | Intentionally Left Blank
| 20 | Quick Coupler Adapter, aluminum, male, w/ Alum. Dust Cap, 4" |  | EA | 1 |  | 0
116-123AA | 21 | S.S. Adjustable Valve Supports, FLG attachment |  | EA | 2 |  | 0
124-127AA | 22 | Complete Removal of Existing Structure |  | EA | 1 |  | 0
129AA | 23 | Concrete Slab, Valve Assembly |  | EA | 1 |  | 0
131AA | 24 | Influent Line Plug, 8" |  | EA | 1 |  | 0
| 25 | By-Pass Pumping |  | LS | 1 |  | 0
| 26 | Water Service Connection and Line, 2" |  | LF | 60 |  | 0
1AB | 27 | Install Meter, Backflow, & Hose Bibb Assembly, standard |  | EA | 1 |  | 0
2AB | 28 | Intentionally Left Blank
4AB | 29 | Abandon Ex. Tapping Saddle; Install Brass Plug |  | EA | 1 |  | 0
| 30 | Remove & Replace Electric Meter Can |  | EA | 1 |  | 0
| 31 | Remove & Replace Fused Safety Switch (disconnect) |  | EA | 1 |  | 0
| 32 | Remove & Replace Control Panel (use 2015 standard) |  | EA | 1 |  | 0
| 32.01 | Includes TCU Bubbler Unit (RPT-001) by DFS |  | EA | 1 |  | 0
| 32.02 | Phase Converter, 1 Phase to 3 Phase, inside Control Panel |  | EA | 2 |  | 0
19AB | 32.03 | Remote Emergency Generator Receptacle |  | EA | 1 |  | 0
| 33 | TCU & Fiberglass Enclosure, DFS (use 2015 standard) |  | EA | 1 |  | 0
| 34 | Junction Box, 304 SS (use 2015 standard) |  | EA | 1 |  | 0
25AB | 35 | Remove & Replace PVC Conduit
29AB | 35.01 | Sch 40, 1" |  | LF | 10 |  | 0
| 35.02 | Sch 80, 2" |  | LF | 30 |  | 0
| 36 | Remove & Replace Electrical Service |  | LF | 20 |  | 0
| 37 | Remove & Replace Electrical Mounting Structure |  | EA | 1 |  | 0
53AA | 38 | Elect. System Study & Elect. Study Analysis, (NFPA 70E), complete |  | LS | 1 |  | 0
| 39 | Ex. Antenna Concrete Base, remove & disposal |  | LS | 1 |  | 0
| 40 | Concrete Repair, 2" thick (if required) |  | SF | 60 |  | 0
| 41 | Remove Existing Fence |  | LS | 1 |  | 0
| 42 | Intentionally Left Blank |  |  |  |  | 0
| 43 | Intentionally Left Blank |  |  |  |  | 0
| 44 | Remove Ex. Conc. Bollards |  | EA | 4 |  | 0
| 45 | Intentionally Left Blank | [5 empty] | 10% |  | Design Point: | 150 | @ | 20
[13 empty] | 1 pump | 2 pumps (150%)
|  | Subtotal Construction Cost - Victoria SQ, RTU 111 (Project #5120484) | [8 empty] | Dia. Disch. Pipe (in) | Design Flow (gpm) | Vel. In Disch. Pipe (f/s) | Vel. In Disch. Pipe (f/s)
| 46 | Mobilization (NTE 10%) | [8 empty] | 3.89 | 150 | 4.0514 | 6.0771
| 47 | Contract Contingency (10% of Subtotal Construction Cost, County Authoirzed Use Only) |  |  | 10% | [7 empty] | Keep Size
Total Construction Cost - Victoria SQ, RTU 111 (Project #5120484)
|  | *(% of Subtotal) | [8 empty] | If Vel. In Disch. Pipe (1 pump) ≥ 8 f/s upsize pipe diameter
| Note: | Opinion of cost assumes construction to be completed by private contractor.
|  | The 3-year average costs for all items listed have been multiplied by 20% in attempt to account for recent market events. | [8 empty] | DIA. | HDPE ID | PVC ID | Sch 80
|  | taken from Lsinfo 2018 |  | Top Elevation: | 16.37 | NGVD | WW Depth: |  |  |  | 2 |  |  | 2.047
|  |  |  | Bottom Elevation: | 8.87 | NGVD | 7.5 |  |  |  | 4 | 3.89 | 4.27
|  |  |  | Wet Well Dia: | 4 | ft |  |  |  |  | 6 | 5.59 | 6.13 |  |  | Yes
|  |  |  | WW2Cross: | 6.5 | ft | No. of Pumps |  |  |  | 8 | 7.34 | 8.04 |  |  | No
|  |  |  | Cross2P.V.: | 3 | ft | 2
|  |  |  | Top or Bottom Surface Area: | 13 | sq-ft
|  |  |  | Total Internal Surface Area: | 120 | sq-ft | Add Stilling Well
|  |  |  | Wall Surface Area: | 94 | sq-ft | No
|  |  |  | Wet Well to be Raised/(Lowered): | 0 | ft
|  |  |  | Valve Vault to be Raised: | 0 | ft | New Spray Liner
|  |  |  | Meter Vault to be Raised: | 0 | ft | Yes
|  |  |  | Concrete Floor & Fillit Concrete Vol: | 2 | cu-yd
Above Ground Valve Assembly
Yes
Replace Guide Rails?
Yes
1000
| 1001 | Influent Drop Bowl/Pipe |  | EA |  |  | 0
| 1002 | New Polymer Concrete Lift Station & Aboveground Valve Assembly |  | LS |  |  | 0
| 1003 | Convert Ex. Lift Station to Concentric Manhole |  | LS |  |  | 0
| 1004 | Site Demolition |  | LS |  |  | 0
| 1005 | Tree Removal; 1"-6" |  | EA |  |  | 0
| 1006 | Fill Dirt, clean and compacted |  | CY |  |  | 0
| 1007 | Retaining Wall, railroad tie construction |  | LS |  |  | 0
| 1008 | Site Demolition |  | LS |  |  | 0
| 1009 | Reinforced Concrete Slab (poured in place) |  | SY |  |  | 0
| 1010 | Emergency Backup Pump & Fuel Tank |  | LS |  |  | 0
| 1011 | PVC Pipe (C900, DR-18), 6" (Pump Discharge Line) |  | LF |  |  | 0
| 1012 | HDPE DR-11, 8" (Pump Suction Line) |  | LF |  |  | 0
| 1013 | Ductile Iron Fittings
| 1013.1 | Red., FLG, 4"x6" |  | EA |  |  | 0
| 1013.2 | Red., FLG, 4"x8" |  | EA |  |  | 0
| 1013.3 | 45, MJ, 6" |  | EA |  |  | 0
| 1013.4 | 90, FLG, 6" |  | EA |  |  | 0
| 1013.5 | 45, FLG, 8" |  | EA |  |  | 0
| 1013.6 | 90, FLG. 8" |  | EA |  |  | 0
| 1013.7 | 90, MJ, 8" |  | EA |  |  | 0
| 1013.8 | 90, HDPE Molded , Fusion Welded, 8" |  | EA |  |  | 0
| 1014 | Sch 80 PVC Conduit, 2" |  | LF |  |  | 0
| 1015 | Level Transducer, GXS3-PP300-A49-B49-50-C01-D49 |  | EA |  |  | 0
| 1016 | PVC Stilling Well, 6" |  | LF |  |  | 0
| 1017 | Permits |  | LS |  |  | 0
**To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-totals, contingencies, and total bid prices for each lift station.**

## Combined
APPENDIX L, BID PRICING FORM
IFBC NO. 23-TA004831SAM
PROJECT NAME: SATELLITE LIFT STATION R&R 2023 GROUP 2
COMBINED GRAND TOTAL FOR SATELLITE LIFT STATION R&R 2023 GROUP 2 (BAY DRIVE, CORTEZ PLAZA 5, CORTEZ PLAZA 2, VICTORIA SQ) WITH CONTRACT CONTINGENCY BASED ON A COMPLETION TIME OF 210 CALENDAR DAYS CONSTRUCTION.
0
Bidder Name:___________________________________________________
Bidder Signature:________________________________________________
**To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-totals, contingencies, and total bid prices for each lift station.**