## BID FORM
APPENDIX M, BID PRICING FORM (REVISED FILLABLE)
IFBC NO. 25-TA005763JH SR64 (MANATEE AVENUE) WATER MAIN INTRACOASTAL CROSSING Bidders must provide prices for each available line item on each tab for their bid to be considered responsive *To be considered responsive, it is the sole responsibility of the bidder to correctly calculate and manually enter all sub-total, contingency, and total bid price fields*
|  |  |  | BID A 410 CALENDAR DAYS |  | BID B 470 CALENDAR DAYS
ITEM | DESCRIPTION | QUANTITY |  | UNIT PRICE | TOTAL PRICE | UNIT PRICE | TOTAL PRICE
I. MISCELLANEOUS
1 | Mobilization (10%) | 1 | LS |  | 0 |  | 0
2 | Maintenance of Traffic | 1 | LS |  | 0 |  | 0
3 | Maintenance of Drill & Temporary Culverts for Laydown Pipe | 1 | LS |  | 0 |  | 0
4 | Erosion and Sediment Control | 1 | LS |  | 0 |  | 0
5 | Clearing and Grubbing | 1 | LS |  | 0 |  | 0
6 | Preconstruction Video | 1 | LS |  | 0 |  | 0
7 | Project Signs | 1 | LS |  | 0 |  | 0
8 | Record Drawings | 1 | LS |  | 0 |  | 0
9 | Pipeline Testing and Chlorine Injection | 1 | LS |  | 0 |  | 0
MISCELLANEOUS SUBTOTAL
II. PROPOSED IMPROVEMENTS
10 | 20" HDPE DR 9 Water Main (HDD) | 3840 | LF |  | 0 |  | 0
11 | 30" Steel Casing and 16" DIP Class 350 Water Main (Jack and Bore) | 50 | LF |  | 0 |  | 0
12 | 30" Steel Casing and 16" DIP Class 350 Water Main (Open Cut) | 40 | LF |  | 0 |  | 0
13 | 16" DIP Class 350 Water Main (Open Cut) | 2600 | LF |  | 0 |  | 0
14 | 16" DI Fitting - 90 Deg. Bend, MJ | 2 | EA |  | 0 |  | 0
15 | 16" DI Fitting - 45 Deg. Bend, MJ | 18 | EA |  | 0 |  | 0
16 | 16" DI Fitting - Tee, MJ | 2 | EA |  | 0 |  | 0
17 | 20" DI Fitting - 11.25 Deg. Bend, MJ | 2 | EA |  | 0 |  | 0
18 | 20" X 16" DI Fitting - Reducer, MJ | 2 | EA |  | 0 |  | 0
19 | 16" DI FLG Adapter | 1 | EA |  | 0 |  | 0
20 | 16" MJ Sleeve | 2 | EA |  | 0 |  | 0
21 | Cut and Connect to 16" Water Main | 2 | EA |  | 0 |  | 0
22 | Water Monitoring Valve Vault | 1 | EA |  | 0 |  | 0
23 | 16" Endress+Hauser Electromagnetic Flow Meter | 1 | EA |  | 0 |  | 0
24 | 16" Mechanical Electric Actuated Gate Valve & Actuator | 1 | EA |  | 0 |  | 0
25 | Pressure Monitor | 1 | EA |  | 0 |  | 0
26 | 16" DI Gate Valve, MJ | 5 | EA |  | 0 |  | 0
27 | Above Ground Air Release Valve Assembly | 2 | EA |  | 0 |  | 0
28 | 6" Fire Hydrant Assembly | 5 | EA |  | 0 |  | 0
29 | Water Service and Meter Removal and Replacement | 1 | LS |  | 0 |  | 0
30 | Remove Existing 4" Inactive Force Main (Excavation) | 20 | LF |  | 0 |  | 0
31 | Remove Existing 8" Inactive Water Main (Excavation) | 10 | LF |  | 0 |  | 0
32 | Remove Existing 16" Water Main (Excavation) | 3030 | LF |  | 0 |  | 0 | Changed
33 | Remove Existing 16" Water Main (On Bridge Deck) | 1550 | LF |  | 0 |  | 0
34 | Grout-fill and Abandon Existing 16" Water Main | 5 | CY |  | 0 |  | 0
35 | Grout-fill and Abandon Existing Water Service Line | 1 | CY |  | 0 |  | 0
36 | Full Road Restoration | 94 | SY |  | 0 |  | 0
37 | Mill and Resurface | 230 | SY |  | 0 |  | 0
38 | Sidewalk Restoration | 85 | SY |  | 0 |  | 0
39 | FDOT Bank Run Shell Restoration | 1670 | SY |  | 0 |  | 0
40 | Sodding | 3840 | SY |  | 0 |  | 0
41 | Tree and Shrub Removal | 1 | LS |  | 0 |  | 0 | Changed
42 | Wetland Restoration | 1 | LS |  | 0 |  | 0
43 | Bollards | 20 | EA |  | 0 |  | 0
44 | Wooden Bollards | 13 | EA |  | 0 |  | 0 | Added
45 | 20" DIP Class 250 Water Main (Open Cut) | 6 | LF |  | 0 |  | 0 | Added
PROPOSED IMPROVEMENTS SUBTOTAL
BASE BID CONSTRUCTION TOTAL WITHOUT CONTINGENCY
46 | Contract Contingency (Used only with County approval) | 10% | [5 empty] | Changed
TOTAL BASE BID (SUBTOTAL PRICE PLUS THE CONTINGENCY)
Bidders name__________________________________
Bidders Signature______________________________