## BID A.15-0465-OV.
BID FORM (Submit in Duplicate) / IFB#15-0465-OV / Addendum #4
53rd Avenue West, 43rd Street West to 75th Street West, Roadway, Striping & Signal Work, Force Main 27-A, from 51st Street West to the Southwest Water Reclamation Facility (SWWRF), including Reclaimed Water and Potable Water.
BID "A" Based on a Completion Time of 730 Calendar Days
NO. | LINE NO. | ITEM NO. | DESCRIPTION | EST. QTY. | U/M | UNIT PRICE | EXTENDED PRICE
1 | 1 | 101-1 | Mobiliziation | 1 | LS |  | 0
2 | 2 | 102-1 | Maintenance of Traffic | 1 | LS |  | 0
| 3 | 102-99 | Portable Changeable Message Sign - Temporary | 84 | ED |  | 0
9 | 4 | 104-10-3 | Staked Silt Fence (Type III) | 12192 | LF |  | 0
7 | 5 | 104-11 | Floating Turbidity Barrier | 240 | LF |  | 0
10 | 6 | 104-15 | Soil Tracking Prevention Device | 2 | EA |  | 0
6 | 7 | 104-18 | Inlet Protection System | 18 | EA |  | 0
13 | 8 | 110-1-MC | *Clearing & Grubbing, removal includes, riprap, trees, pipes, structures, wells, & underdrain (Addendum #3) | 31.2 | AC |  | 0
16 | 9 | 120-1 | Regular Excavation | 39826 | CY |  | 0
17 | 10 | 120-4 | Excavation, Subsoil | 5300 | CY |  | 0
| 11 | 120-5-MC | Channel Excavation | 4764 | CY |  | 0
19 | 12 | 120-6 | Embankment (Regular) | 37925 | CY |  | 0
21 | 13 | 145-1 | Geosynthetic Reinforced Soil Slope | 3250 | SF |  | 0
23 | 14 | 160-4 | 12" Stabilized Sub-base (LBR 60) | 34000 | SY |  | 0
26 | 15 | 285-704 | Optional Base Group 4: | 276 | SY |  | 0
26 | 16 | 285-709 | Optional Base Group 9: | 32777 | SY |  | 0
29 | 17 | 327-70-1 | Milling Exist. Asph. Pavement (1" Avg. Depth) | 29268 | SY |  | 0
32 | 18 | 334-1-MC1 | 2" Type S-I Asphalt Concrete (Incl Tack Coat) | 3727 | TN |  | 0
36 | 19 | 334-1-MC2 | 1" Type S-III Asphalt Concrete | 3587 | TN |  | 0
38 | 20 | 400-1 | Class I Concrete (Endwalls), Including Reinforcing Steel / Wingwalls | 15.5 | CY |  | 0
38 | 21 | 400-1 | Class I Concrete (Weir Wall), Including Reinforcing Steel | 6.4 | CY |  | 0
| 22 | 400-1 | Class I Concrete (Agricultural crossing at sta. 61+00), Incl. Reinforcing Steel | 23.7 | CY |  | 0
126 | 23 | 425-1-351 | Inlets, Curb, Type P-5, <10' | 1 | EA |  | 0
51 | 24 | 425-1-549 | *Inlet (Dt Bot) (Type D Modified) (<10') (Addendum #3) (Revise Qty) | 6 | EA |  | 0
50 | 25 | 425-1-MC1 | Grate Inlets w/ 4' Sump | 4 | EA |  | 0
126 | 26 | 425-1-MC2 | Diversion Boxes | 2 | EA |  | 0
127 | 27 | 425-1-MC3 | *Concrete Block Box 4' x 4' (Addendum #3) (Revise Qty) | 3 | EA |  | 0
127 | 28 | 425-1-MC4 | Adjust/Reconstruct Existing Inlet | 2 | EA |  | 0
64 | 29 | 430-174-112 | Pipe Side Drain Culv (A2000,PVC)(12") | 75 | LF |  | 0
64 | 30 | 430-174-115 | Pipe Side Drain Culv (A2000,PVC)(15") | 22 | LF |  | 0
73 | 31 | *430-174-136 | Pipe Side Drain Culv (RCP)(36") (Addendum #4) (Revise Qty) | 56 | LF |  | 0
64 | 32 | *430-174-142 | Pipe Side Drain Culv (RCP)(42") (Addendum #4) (Revise Qty) | 80 | LF |  | 0
64 | 33 | *430-175-115 | Pipe Cross Drain Culv (A2000,PVC)(15") (Addendum #4) (Revise Qty) | 147 | LF |  | 0
64 | 34 | 430-175-115 | Pipe Cross Drain Culv (ADS)(15") | 19 | LF |  | 0
| 35 | 430-175-118 | Pipe Storm Sewer Culv (A2000)(18") | 144 | LF |  | 0
66 | 36 | 430-175-121 | Pipe Storm Sewer Culv (A2000)(21") | 324 | LF |  | 0
68 | 37 | 430-175-124 | Pipe Cross Drain Culv (RCP)(24") | 10 | LF |  | 0
69 | 38 | 430-175-124 | Pipe Storm Sewer Culv (A2000)(24") | 765 | LF |  | 0
| 39 | 430-175-130 | Pipe Storm Sewer Culv (A2000)(30") | 719 | LF |  | 0
76 | 40 | 430-175-142 | Pipe Cross Drain Culv (RCP)(42") | 19 | LF |  | 0
79 | 41 | 430-175-215 | Pipe Storm Drain Culv (ERCP) (12"x18") | 443 | LF |  | 0
81 | 42 | 430-175-224 | Pipe Cross Drain Culv (ERCP) (19"x30") | 120 | LF |  | 0
72 | 43 | 430-175-230 | Pipe Cross Drain Culv (ERCP)(24"x38") | 190 | LF |  | 0
72 | 44 | 430-830 | Pipe Filling and Plugging - Place out of Service | 10.9 | CY |  | 0
93 | 45 | 430-982-123 | MES (Cross Drain) 15" (Addendum #3) (Revise Qty) | 2 | EA |  | 0
93 | 46 | 430-982-129 | *MES (Cross Drain) 24"(Addendum #3) (Revise Qty) | 4 | EA |  | 0
93 | 47 | 430-982-140 | MES (Cross Drain) 42" | 1 | EA |  | 0
93 | 48 | 430-982-633 | MES (Cross Drain) 24"x38" | 4 | EA |  | 0
97 | 49 | 430-984-121 | MES (Round) (12" SD) | 5 | EA |  | 0
97 | 50 | 430-984-123 | MES (Round) (15" SD) | 2 | EA |  | 0
97 | 51 | 430-984-133 | MES (Round) (30" SD) | 1 | EA |  | 0
97 | 52 | 430-984-138 | MES (Round) (36" SD) | 1 | EA |  | 0
97 | 53 | 430-984-140 | MES (Round) (42" SD) | 6 | EA |  | 0
98 | 54 | 430-984-623 | *MES (Conc Pipe Ellip) (12"x18") (SD) (Addendum #3) (Revise Qty) | 8 | EA |  | 0
| 55 | 440-1-MC | 6" Underdrain | 624 | LF |  | 0
103 | 56 | 515-2-302 | Pedestrian / Bicycle Railing, Aluminum, 54" Picket Railing | 80 | LF |  | 0
104 | 57 | 520-1-MC1 | Type AB Curb & Gutter | 171 | LF |  | 0
105 | 58 | 520-1-10 | Type F Curb & Gutter | 294 | LF |  | 0
105 | 59 | 520-2-1 | Type A, Concrete Curb | 16082 | LF |  | 0
| 60 | 520-5-MC | Emergency Crossing | 70 | LF |  | 0
108 | 61 | 522-1-MC | 4" Concrete Sidewalk (Incl. Detectable Warning Truncated Dome) | 5007 | SY |  | 0
109 | 62 | 522-2-MC | 6" Concrete Sidewalk, Reinforced Driveway (Incl. 6" x 6" #10 Mesh) | 711 | SY |  | 0
112 | 63 | 530-3-4 | Rip-Rap (Rubble) | 275 | TN |  | 0
| 64 | *550-10-910 | Chain Link Fencing, Special Type, 0.0-5.0', Standard (Addendum #3) (Revise Description) | 600 | LF |  | 0
| 64A | *550-MC2 | Hog Wire Fence and Barbed Wire Fence (Addendum #3) (New Bid Item) | 600 | LF |  | 0
116 | 65 | 550-MC | Fence, Removal and Reloc. (Incl. Gates, All Types incl. hog wire, barbed wire & chain link) | 3055 | LF |  | 0
123 | 66 | 570-1-2 | Sodding (Performance Turf, Bahia) (Includes Mowing) | 76896 | SY |  | 0
| 67 | 570-MC | Wetland creation, mitigation and enhancement at SW corner of 53rd Ave W & 43rd St W | 1 | LS |  | 0
| 68 | 630-2-11 | CONDUIT (F&I) (OPEN TRENCH) | 7794 | LF |  | 0
| 69 | 630-2-12 | CONDUIT (F & I) (DIRECTIONAL BORE) | 2537 | LF |  | 0
| 70 | 632-7-1 | CABLE, SIGNAL (F&I) | 2 | PI |  | 0
| 71 | 633-1-121 | FIBER OPTIC CABLE (F&I) (UNDERGROUND) (2-12 FIBERS) | 190 | LF |  | 0
| 72 | 633-2-31 | FIBER OPTIC CONNECTION (INSTALL SPLICE) | 4 | EA |  | 0
| 73 | 633-3-11 | FIBER OPTIC CONNECTION HARDWARE (F&I) (SPLICE ENCLOSURE) | 1 | EA |  | 0
| 74 | 633-3-12 | FIBER OPTIC CONNECTION HARDWARE (F&I) (SPLICE TRAY) | 1 | EA |  | 0
| 75 | 633-3-15 | FIBER OPTIC CONNECTION HARDWARE (F&I) (PATCH PANEL, PRETERMINATED) | 1 | EA |  | 0
| 76 | 635-2-11 | PULL & SPLICE BOXES (F&I) (17" X 30" COVER SIZE) | 22 | EA |  | 0
| 77 | 635-2-12 | PULL & SPLICE BOXES (F&I) (24" X 36" COVER SIZE) | 19 | EA |  | 0
| 78 | 635-2-13 | PULL & SPLICE BOXES (F&I) (30" X 60" RECTANGLE) | 4 | EA |  | 0
| 79 | 639-1-122 | ELECTRICAL POWER SERVICE (UNDERGROUND) METER PURCH. BY CONT. | 2 | AS |  | 0
| 80 | 639-2-1 | ELECTRICAL SERVICE WIRE | 771 | LF |  | 0
| 81 | 639-3-11 | ELECTRICAL SERVICE DISCONNECT (F&I) (POLE MOUNT) | 1 | EA |  | 0
| 82 | 639-4-6 | EMERGENCY GENERATOR - PORTABLE, INSTALL HOUSING ONLY | 2 | EA |  | 0
| 83 | 641-2-12 | PRESTRESSED CONCRETE POLE (F&I) (TYPE P-II SERVICE POLE) 12' | 2 | EA |  | 0
| 84 | 646-1-11 | ALUMINUM SIGNALS POLE (PEDESTAL) (F&I) | 8 | EA |  | 0
| 85 | 649-31-207 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (SNGLE ARM) (W/ LUMINAIRE) (46') | 1 | EA |  | 0
| 86 | 649-31-208 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (SINGLE ARM) (W/ LUMINAIRE) (60') | 3 | EA |  | 0
| 87 | 649-31-299 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (DOUBLE ARM) (W/ LUMINAIRE) (60'-60') | 1 | EA |  | 0
| 88 | 650-1-311 | TRAFFIC SIGNAL (F&I) (3 SECT) (1 WAY) (STANDARD) (ALUMINUM) | 14 | AS |  | 0
| 89 | 650-1-511 | TRAFFIC SIGNAL (F&I) (5 SECT) (1 WAY) (STANDARD) (ALUMINUM) | 2 | AS |  | 0
| 90 | 653-191 | PEDESTRIAN SIGNAL (F&I) (LED-COUNTDOWN) (1 WAY) | 8 | AS |  | 0
| 91 | *660-4-11 | VEHICLE DETECTION SYSTEM-VIDEO (F&I) (CABINET EQUIPMENT) (Addendum #3) (Revise Qty) | 2 | EA |  | 0
| 92 | 660-4-12 | VEHICLE DETECTION SYSTEM-VIDEO (F&I) (ABOVE GRND EQUIPMENT) | 6 | EA |  | 0
| 93 | 665-1-11 | PEDESTRIAN DETECTOR (F&I) | 8 | EA |  | 0
| 94 | 670-5-112 | TRAFFIC CONTROLLER ASSEMBLY (F&I) (NEMA) ( 2 PREEMPTION PLAN) | 2 | AS |  | 0
| 95 | 682-1-11 | CCTV CAMERA, DOME ENCLOSURE, PRESSURIZED | 1 | EA |  | 0
| 96 | 684-1-1 | ITS FIELD MANAGED ETHERNET SWITCH | 2 | EA |  | 0
| 97 | 684-3-11 | DIGITAL VIDEO ENCODER WITH SOFTWARE ENCODER | 1 | EA |  | 0
| 98 | 685-106 | SYSTEM AUXILIARIES (F&I) (UNINTERRUPTIBLE POWER SOURCE) | 2 | EA |  | 0
| 99 | 690-10 | TRAFFIC SIGNAL HEAD ASSEMBLY, REMOVAL | 12 | EA |  | 0
| 100 | 690-34-1 | POLE REMOVAL - DEEP (DIRECT BURIAL) | 4 | EA |  | 0
| 101 | 690-50 | CONTROLLER ASSEMBLY REMOVE (COMPLETE ASSEMBLY) | 2 | EA |  | 0
| 102 | 690-80 | SPAN WIRE ASSEMBLY REMOVE | 2 | EA |  | 0
| 103 | 690-90 | REMOVE CONDUIT & CABLING | 2 | PI |  | 0
| 104 | 690-100 | SIGNAL EQUIPMENT, MISCELLANEOUS REMOVE | 2 | PI |  | 0
| 105 | 700-1-11 | SINGLE POST SIGN (F&I GRND MOUNT) (UP TO 12 SF) | 22 | AS |  | 0
| 106 | 700-1-12 | SINGLE POST SIGN (F&I GRND MOUNT) (12-20 SF) | 14 | AS |  | 0
| 107 | 700-1-13 | SINGLE POST SIGN (F&I GRND MOUNT) (21-30 SF) | 2 | AS |  | 0
| 108 | 700-1-50 | SINGLE POST SIGN (RELOCATE) | 5 | AS |  | 0
| 109 | 700-1-60 | SINGLE POST SIGN (REMOVE) | 17 | AS |  | 0
| 110 | 700-2-13 | MULTI-POST SIGN (F&I GRND MOUNT 31-30 SF) | 4 | AS |  | 0
| 111 | 700-2-15 | MULTI-POST SIGN (F&I GRND MOUNT 51-100 SF) | 1 | AS |  | 0
| 112 | 700-3-601 | SIGN PANEL (REMOVE) (UP TO 12 SF) | 3 | EA |  | 0
| 113 | 700-5-22 | INTERNALLY ILLUMINATED SIGN (F&I) (LED) (12-18 SF) | 6 | EA |  | 0
| 114 | 705-10-1 | OBJECT MARKER (TYPE I) | 12 | EA |  | 0
| 115 | 705-11-1 | DELINEATOR, FLEXIBLE TUBULAR | 6 | EA |  | 0
| 116 | 706-3 | RETRO-REFLECTIVE PAVEMENT MARKERS | 575 | EA |  | 0
| 117 | 710-11-290 | PAINTED PAVEMENT MARKINGS (STANDARD) (YELLOW) (ISLAND NOSE) | 88 | SF |  | 0
| 118 | 711-11-123 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (12") | 564 | LF |  | 0
| 119 | 711-11-124 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (18") | 119 | LF |  | 0
| 120 | 711-11-125 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (24") | 654 | LF |  | 0
| 121 | 711-11-151 | THERMOPLASTIC (STANDARD) (WHITE) (6")(2' - 4' SKIP) & (6'-10' SKIP) | 552 | LF |  | 0
| 122 | 711-11-160 | THERMOPLASTIC (STANDARD) (WHITE) (MESSAGE) | 1 | EA |  | 0
| 123 | 711-11-170 | THERMOPLASTIC (STANDARD) (WHITE) (ARROW) | 27 | EA |  | 0
| 124 | 711-11-224 | THERMOPLASTIC (STANDARD) (YELLOW) (SOLID) (18") | 66 | LF |  | 0
| 125 | 711-11-251 | THERMOPLASTIC (STANDARD) (YELLOW) (6")(6'-10' SKIP) | 336 | LF |  | 0
| 126 | 711-14-160 | THERMOPLASTIC (PREFORMED) (WHITE) (MESSAGE) | 16 | EA |  | 0
| 127 | 711-14-170 | THERMOPLASTIC (PREFORMED) (WHITE) (ARROWS) | 16 | EA |  | 0
| 128 | 711-16-111 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SOLID) (6") | 3.744 | NM |  | 0
| 129 | 711-16-112 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SOLID) (8") | 0.186 | NM |  | 0
| 130 | 711-16-131 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SKIP) (6") (10'-30' SKIP) | 3.298 | GM |  | 0
| 131 | 711-16-211 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (YELLOW) (SOLID) (6") | 3.22 | NM |  | 0
| 132 | 711-17 | THERMOPLASTIC (REMOVE EXISTING THERMOPLASTIC PAVEMENT MARKINGS) | 92 | SF |  | 0
| 133 | 785-1-13 | ITS FIELD CABINET (F&I) CONCRETE POLE WITHOUT LOWERING DEVICE | 1 | EA |  | 0
| 134 | 785-2-132 | ITS FIELD CABINET (F&I) (TYPE 336S) (POLE MOUNT) | 1 | EA |  | 0
|  |  | SUBTOTAL ROADWAY, STRIPING & SIGNAL |  |  |  | 0
|  |  | Contract Contingency - 10% of Subtotal Roadway, Striping & Signal (Used only with County Approval) | 10 | % |  | 0
|  |  | TOTAL ROADWAY, STRIPING & SIGNAL, Bid "A" Based on a Completion Time of 730 Calendar Days (Including 10% Contingency) |  |  |  | 0
FORCE MAIN
| U1 |  | 42" DIP (CL350) Force Main | 5300 | LF |  | 0
| U2 |  | 42" DIP RJ (CL350) Force Main | 1500 | LF |  | 0
| U3 |  | 30" DIP (CL 350) Force Main | 70 | LF |  | 0
| U4 |  | 20" DIP (CL 350) Force Main | 345 | LF |  | 0
| U5. |  | *18" DIP (CL 350) Force Main (Addendum #3) (Revise Qty) | 310 | LF |  | 0
| U6 |  | 12" DIP (CL 350) Force Main | 150 | LF |  | 0
| U7 |  | 8" DIP (CL350) Force Main | 95 | LF |  | 0
| U8 |  | 42" Pipe Restraints | 30 | EA |  | 0
| U9 |  | 30" Pipe Restraints | 9 | EA |  | 0
| U10 |  | 20", 18", & 16" Pipe Restraints - Not for 18" Potable Water | 48 | EA |  | 0
| U11 |  | 12" & Smaller Pipe Restraints | 20 | EA |  | 0
| U12 |  | 42" Plug Valve for Force Main | 3 | EA |  | 0
| U13 |  | 30" Plug Valve for Force Main | 2 | EA |  | 0
| U14 |  | 20" or 18" Gate Valve for Force Main | 8 | EA |  | 0
| U15 |  | 20" x 18" Tapping Sleeve & Valve for Force Main | 4 | EA |  | 0
| U16 |  | 12" Gate Valve for Force Main | 2 | EA |  | 0
| U17 |  | *DI Fittings - WASTEWATER (Addendum #3) (Revise Qty) | 55500 | LB |  | 0
| U17A |  | *DI Fitting - WATER) (Addendum #3) (New Bid Item) | 7500 | LB |  | 0
| U18 |  | Connect to Exist. 42" Force Main | 2 | EA |  | 0
| U19 |  | Connect to Exist. 30" Force Main | 1 | EA |  | 0
| U20 |  | Adjust Existing Valve Boxes to Finish Grade | 8 | EA |  | 0
| U21 |  | *Grout Fill Abandoned Mains (Addendum#3) (Revise Qty) | 5500 | CF |  | 0
| U22 |  | *Asphalt Road Restoration (Base & Resurface) Type1 (Addendum #3) (Revise Qty) | 1200 | SY |  | 0
| U23 |  | Asphalt Road Restoration (Base & Resurface)Type 2 | 4500 | SY |  | 0
| U24 |  | Asphalt Road Restoration (Mill & Resurface) | 400 | SY |  | 0
| U25 |  | *8" Optional Base Group 6 (FDOT Index 514) (Addendum #3) (Description Revised) | 4100 | SY |  | 0
| U26 |  | Silt Fence (not on 53rd Ave) | 3000 | LF |  | 0
| U27 |  | Curb & Gutter Replacement | 80 | LF |  | 0
| U28 |  | Hydroseeding | 5000 | SY |  | 0
| U29 |  | Sodding | 2500 | SY |  | 0
| U30 |  | ARV Assembly - Water Mains | 3 | EA |  | 0
| U31 |  | ARV Assembly - Force Mains | 4 | EA |  | 0
| U32 |  | ARV Assembly including Manhole | 6 | EA |  | 0
| U33 |  | Erosion Control | 1 | LS |  | 0
| U34 |  | MOT to FDOT Stds. incl. Temp Roads & Barriers | 1 | LS |  | 0
| U35 |  | 20" Line Stop | 4 | EA |  | 0
| U36 |  | Concrete Thrust Blocks | 120 | CY |  | 0
| U37 |  | Golf FMain 4" HDPE (DR11) & 42x6 Tap Sleeve & GV. | 1 | LS |  | 0
| U38 |  | DELETE IN ITS ENTIRETY (Addendum #3) | 0 | LS |  | 0
| U39 |  | DELETE IN ITS ENTIRETY (Addendum #3) | 0 | LF |  | 0
| U40 |  | Storm Drain Inlet Type C incl. 30LF 12"x18" RCP | 2 | EA |  | 0
| U41 |  | Mobilization | 1 | LS |  | 0
| U42 |  | Miscellaneous Work & Clean Up | 1 | LS |  | 0
|  |  | SUBTOTAL FORCE MAIN |  |  |  | 0
| U43 |  | Contract Contingency - 5% of Subtotal Force Main (Used only with County Approval) | 5 | % |  | 0
|  |  | TOTAL FORCE MAIN, BID "A" Based on a Completion Time of 730 Calendar Days (Including 5% Contingency) |  |  |  | 0
RECLAIMED WATER ITEMS
| U44 |  | 24" DIP (CL 350) Reclaim Waterline (incl. removal) | 1340 | LF |  | 0
| U45 |  | 24" Pipe Restraints | 36 | EA |  | 0
| U46 |  | 24" Butterfly Valve for RCW | 5 | EA |  | 0
| U47 |  | Relocate and Replace Existing Reclaim Meter Assemblies & Hydrants (Addendum #3) (Revise Description) | 1 | LS |  | 0
| U48 |  | Mobilization | 1 | LS |  | 0
|  |  | SUBTOTAL RECLAIMED WATER ITEMS |  |  |  | 0
| U49 |  | Contract Contingency - 5% of Subtotal Reclaimed Water Items (Used only with County Approval) | 5 | % |  | 0
|  |  | TOTAL RECLAIMED WATER ITEMS, BID "A" Based on a Completion Time of 730 Calendar Days (Including 5% Contingency) |  |  |  | 0
POTABLE WATER ITEMS
| U50 |  | 8" DIP (CL350) Waterline (incl. removal) | 145 | LF |  | 0
| U51 |  | 18" Pipe Restraints for Existing 18" Potable Waterline | 100 | EA |  | 0
| U52 |  | Adjust Existing Valve Boxes to Finish Grade | 10 | EA |  | 0
52 | U53 |  | Fire Hydrant Assembly | 7 | EA |  | 0
| U54 |  | 8" Gate Valve for Waterline | 2 | EA |  | 0
|  |  | SUBTOTAL POTABLE WATER ITEMS |  |  |  | 0
| U55 |  | Contract Contingency - 10% of Subtotal Potable Water Items (Used only with County Approval) | 10 | % |  | 0
|  |  | TOTAL POTABLE WATER, BID "A" Based on a Completion Time of 730 Calendar Days (Including 10% Contingency) |  |  |  | 0
|  |  | GRAND TOTAL AWARD FOR ROADWAY, STRIPING & SIGNAL, FORCE MAIN, RECLAIMED WATER AND POTABLE WATER ITEMS. BID "A", BASED ON A COMPLETION TIME OF 730 CALENDAR DAYS (Including Contingency) |  |  |  | 0

## BID B.15-0465-OV.
BID FORM (Submit in Duplicate) / IFB#15-0465-OV / Addendum #4
53rd Avenue West, 43rd Street West to 75th Street West, Roadway, Striping & Signal Work, Force Main 27-A, from 51st Street West to the Southwest Water Reclamation Facility (SWWRF), including Reclaimed Water and Potable Water.
BID "B" Based on a Completion Time of 640 Calendar Days
NO. | LINE NO. | ITEM NO. | DESCRIPTION | EST. QTY. | U/M | UNIT PRICE | EXTENDED PRICE
1 | 1 | 101-1 | Mobiliziation | 1 | LS |  | 0
2 | 2 | 102-1 | Maintenance of Traffic | 1 | LS |  | 0
| 3 | 102-99 | Portable Changeable Message Sign - Temporary | 84 | ED |  | 0
9 | 4 | 104-10-3 | Staked Silt Fence (Type III) | 12192 | LF |  | 0
7 | 5 | 104-11 | Floating Turbidity Barrier | 240 | LF |  | 0
10 | 6 | 104-15 | Soil Tracking Prevention Device | 2 | EA |  | 0
6 | 7 | 104-18 | Inlet Protection System | 18 | EA |  | 0
13 | 8 | 110-1-MC | *Clearing & Grubbing, removal includes, riprap, trees, pipes, structures, wells, & underdrain (Addendum #3) (Description Revised) | 31.2 | AC |  | 0
16 | 9 | 120-1 | Regular Excavation | 39826 | CY |  | 0
17 | 10 | 120-4 | Excavation, Subsoil | 5300 | CY |  | 0
| 11 | 120-5-MC | Channel Excavation | 4764 | CY |  | 0
19 | 12 | 120-6 | Embankment (Regular) | 37925 | CY |  | 0
21 | 13 | 145-1 | Geosynthetic Reinforced Soil Slope | 3250 | SF |  | 0
23 | 14 | 160-4 | 12" Stabilized Sub-base (LBR 60) | 34000 | SY |  | 0
26 | 15 | 285-704 | Optional Base Group 4: | 276 | SY |  | 0
26 | 16 | 285-709 | Optional Base Group 9: | 32777 | SY |  | 0
29 | 17 | 327-70-1 | Milling Exist. Asph. Pavement (1" Avg. Depth) | 29268 | SY |  | 0
32 | 18 | 334-1-MC1 | 2" Type S-I Asphalt Concrete (Incl Tack Coat) | 3727 | TN |  | 0
36 | 19 | 334-1-MC2 | 1" Type S-III Asphalt Concrete | 3587 | TN |  | 0
38 | 20 | 400-1 | Class I Concrete (Endwalls), Including Reinforcing Steel / Wingwalls | 15.5 | CY |  | 0
38 | 21 | 400-1 | Class I Concrete (Weir Wall), Including Reinforcing Steel | 6.4 | CY |  | 0
| 22 | 400-1 | Class I Concrete (Agricultural crossing at sta. 61+00), Incl. Reinforcing Steel | 23.7 | CY |  | 0
126 | 23 | 425-1-351 | Inlets, Curb, Type P-5, <10' | 1 | EA |  | 0
51 | 24 | 425-1-549 | *Inlet (Dt Bot) (Type D Modified) (<10') (Addendum #3) (Revise Qty) | 6 | EA |  | 0
50 | 25 | 425-1-MC1 | Grate Inlets w/ 4' Sump | 4 | EA |  | 0
126 | 26 | 425-1-MC2 | Diversion Boxes | 2 | EA |  | 0
127 | 27 | 425-1-MC3 | *Concrete Block Box 4' x 4' (Addendum #3) (Revise Qty) | 3 | EA |  | 0
127 | 28 | 425-1-MC4 | Adjust/Reconstruct Existing Inlet | 2 | EA |  | 0
64 | 29 | 430-174-112 | Pipe Side Drain Culv (A2000,PVC)(12") | 75 | LF |  | 0
64 | 30 | 430-174-115 | Pipe Side Drain Culv (A2000,PVC)(15") | 22 | LF |  | 0
73 | 31 | *430-174-136 | Pipe Side Drain Culv (RCP)(36") (Addendum #4) (Revise Qty) | 56 | LF |  | 0
64 | 32 | *430-174-142 | Pipe Side Drain Culv (RCP)(42") (Addendum #4) (Revise Qty) | 80 | LF |  | 0
64 | 33 | *430-175-115 | Pipe Cross Drain Culv (A2000,PVC)(15") (Addendum #4) (Revise Qty) | 147 | LF |  | 0
64 | 34 | 430-175-115 | Pipe Cross Drain Culv (ADS)(15") | 19 | LF |  | 0
| 35 | 430-175-118 | Pipe Storm Sewer Culv (A2000)(18") | 144 | LF |  | 0
66 | 36 | 430-175-121 | Pipe Storm Sewer Culv (A2000)(21") | 324 | LF |  | 0
68 | 37 | 430-175-124 | Pipe Cross Drain Culv (RCP)(24") | 10 | LF |  | 0
69 | 38 | 430-175-124 | Pipe Storm Sewer Culv (A2000)(24") | 765 | LF |  | 0
| 39 | 430-175-130 | Pipe Storm Sewer Culv (A2000)(30") | 719 | LF |  | 0
76 | 40 | 430-175-142 | Pipe Cross Drain Culv (RCP)(42") | 19 | LF |  | 0
79 | 41 | 430-175-215 | Pipe Storm Drain Culv (ERCP) (12"x18") | 443 | LF |  | 0
81 | 42 | 430-175-224 | Pipe Cross Drain Culv (ERCP) (19"x30") | 120 | LF |  | 0
72 | 43 | 430-175-230 | Pipe Cross Drain Culv (ERCP)(24"x38") | 190 | LF |  | 0
72 | 44 | 430-830 | Pipe Filling and Plugging - Place out of Service | 10.9 | CY |  | 0
93 | 45 | 430-982-123 | *MES (Cross Drain) 15" (Addendum #3) (Revise Qty) | 2 | EA |  | 0
93 | 46 | 430-982-129 | *MES (Cross Drain) 24"(Addendum #3) (Revise Qty) | 4 | EA |  | 0
93 | 47 | 430-982-140 | MES (Cross Drain) 42" | 1 | EA |  | 0
93 | 48 | 430-982-633 | MES (Cross Drain) 24"x38" | 4 | EA |  | 0
97 | 49 | 430-984-121 | MES (Round) (12" SD) | 5 | EA |  | 0
97 | 50 | 430-984-123 | MES (Round) (15" SD) | 2 | EA |  | 0
97 | 51 | 430-984-133 | MES (Round) (30" SD) | 1 | EA |  | 0
97 | 52 | 430-984-138 | MES (Round) (36" SD) | 1 | EA |  | 0
97 | 53 | 430-984-140 | MES (Round) (42" SD) | 6 | EA |  | 0
98 | 54 | 430-984-623 | *MES (Conc Pipe Ellip) (12"x18") (SD) (Addendum #3) (Revise Qty) | 8 | EA |  | 0
| 55 | 440-1-MC | 6" Underdrain | 624 | LF |  | 0
103 | 56 | 515-2-302 | Pedestrian / Bicycle Railing, Aluminum, 54" Picket Railing | 80 | LF |  | 0
104 | 57 | 520-1-MC1 | Type AB Curb & Gutter | 171 | LF |  | 0
105 | 58 | 520-1-10 | Type F Curb & Gutter | 294 | LF |  | 0
105 | 59 | 520-2-1 | Type A, Concrete Curb | 16082 | LF |  | 0
| 60 | 520-5-MC | Emergency Crossing | 70 | LF |  | 0
108 | 61 | 522-1-MC | 4" Concrete Sidewalk (Incl. Detectable Warning Truncated Dome) | 5007 | SY |  | 0
109 | 62 | 522-2-MC | 6" Concrete Sidewalk, Reinforced Driveway (Incl. 6" x 6" #10 Mesh) | 711 | SY |  | 0
112 | 63 | 530-3-4 | Rip-Rap (Rubble) | 275 | TN |  | 0
| 64 | *550-10-910 | Chain Link Fencing, Special Type, 0.0-5.0', Standard (Addendum #3) (Revise Description) | 600 | LF |  | 0
| 64A | *550-MC2 | Hog Wire Fence and Barbed Wire Fence (Addendum #3) (New Bid Item) | 600 | LF |  | 0
116 | 65 | 550-MC | Fence, Removal and Reloc. (Incl. Gates, All Types incl. hog wire, barbed wire & chain link) | 3055 | LF |  | 0
123 | 66 | 570-1-2 | Sodding (Performance Turf, Bahia) (Includes Mowing) | 76896 | SY |  | 0
| 67 | 570-MC | Wetland creation, mitigation and enhancement at SW corner of 53rd Ave W & 43rd St W | 1 | LS |  | 0
| 68 | 630-2-11 | CONDUIT (F&I) (OPEN TRENCH) | 7794 | LF |  | 0
| 69 | 630-2-12 | CONDUIT (F & I) (DIRECTIONAL BORE) | 2537 | LF |  | 0
| 70 | 632-7-1 | CABLE, SIGNAL (F&I) | 2 | PI |  | 0
| 71 | 633-1-121 | FIBER OPTIC CABLE (F&I) (UNDERGROUND) (2-12 FIBERS) | 190 | LF |  | 0
| 72 | 633-2-31 | FIBER OPTIC CONNECTION (INSTALL SPLICE) | 4 | EA |  | 0
| 73 | 633-3-11 | FIBER OPTIC CONNECTION HARDWARE (F&I) (SPLICE ENCLOSURE) | 1 | EA |  | 0
| 74 | 633-3-12 | FIBER OPTIC CONNECTION HARDWARE (F&I) (SPLICE TRAY) | 1 | EA |  | 0
| 75 | 633-3-15 | FIBER OPTIC CONNECTION HARDWARE (F&I) (PATCH PANEL, PRETERMINATED) | 1 | EA |  | 0
| 76 | 635-2-11 | PULL & SPLICE BOXES (F&I) (17" X 30" COVER SIZE) | 22 | EA |  | 0
| 77 | 635-2-12 | PULL & SPLICE BOXES (F&I) (24" X 36" COVER SIZE) | 19 | EA |  | 0
| 78 | 635-2-13 | PULL & SPLICE BOXES (F&I) (30" X 60" RECTANGLE) | 4 | EA |  | 0
| 79 | 639-1-122 | ELECTRICAL POWER SERVICE (UNDERGROUND) METER PURCH. BY CONT. | 2 | AS |  | 0
| 80 | 639-2-1 | ELECTRICAL SERVICE WIRE | 771 | LF |  | 0
| 81 | 639-3-11 | ELECTRICAL SERVICE DISCONNECT (F&I) (POLE MOUNT) | 1 | EA |  | 0
| 82 | 639-4-6 | EMERGENCY GENERATOR - PORTABLE, INSTALL HOUSING ONLY | 2 | EA |  | 0
| 83 | 641-2-12 | PRESTRESSED CONCRETE POLE (F&I) (TYPE P-II SERVICE POLE) 12' | 2 | EA |  | 0
| 84 | 646-1-11 | ALUMINUM SIGNALS POLE (PEDESTAL) (F&I) | 8 | EA |  | 0
| 85 | 649-31-207 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (SNGLE ARM) (W/ LUMINAIRE) (46') | 1 | EA |  | 0
| 86 | 649-31-208 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (SINGLE ARM) (W/ LUMINAIRE) (60') | 3 | EA |  | 0
| 87 | 649-31-299 | STEEL MAST ARM ASSEM. (F&I) (WS-130) (DOUBLE ARM) (W/ LUMINAIRE) (60'-60') | 1 | EA |  | 0
| 88 | 650-1-311 | TRAFFIC SIGNAL (F&I) (3 SECT) (1 WAY) (STANDARD) (ALUMINUM) | 14 | AS |  | 0
| 89 | 650-1-511 | TRAFFIC SIGNAL (F&I) (5 SECT) (1 WAY) (STANDARD) (ALUMINUM) | 2 | AS |  | 0
| 90 | 653-191 | PEDESTRIAN SIGNAL (F&I) (LED-COUNTDOWN) (1 WAY) | 8 | AS |  | 0
| 91 | *660-4-11 | VEHICLE DETECTION SYSTEM-VIDEO (F&I) (CABINET EQUIPMENT) (Addendum #3) (Revise Qty) | 2 | EA |  | 0
| 92 | 660-4-12 | VEHICLE DETECTION SYSTEM-VIDEO (F&I) (ABOVE GRND EQUIPMENT) | 6 | EA |  | 0
| 93 | 665-1-11 | PEDESTRIAN DETECTOR (F&I) | 8 | EA |  | 0
| 94 | 670-5-112 | TRAFFIC CONTROLLER ASSEMBLY (F&I) (NEMA) ( 2 PREEMPTION PLAN) | 2 | AS |  | 0
| 95 | 682-1-11 | CCTV CAMERA, DOME ENCLOSURE, PRESSURIZED | 1 | EA |  | 0
| 96 | 684-1-1 | ITS FIELD MANAGED ETHERNET SWITCH | 2 | EA |  | 0
| 97 | 684-3-11 | DIGITAL VIDEO ENCODER WITH SOFTWARE ENCODER | 1 | EA |  | 0
| 98 | 685-106 | SYSTEM AUXILIARIES (F&I) (UNINTERRUPTIBLE POWER SOURCE) | 2 | EA |  | 0
| 99 | 690-10 | TRAFFIC SIGNAL HEAD ASSEMBLY, REMOVAL | 12 | EA |  | 0
| 100 | 690-34-1 | POLE REMOVAL - DEEP (DIRECT BURIAL) | 4 | EA |  | 0
| 101 | 690-50 | CONTROLLER ASSEMBLY REMOVE (COMPLETE ASSEMBLY) | 2 | EA |  | 0
| 102 | 690-80 | SPAN WIRE ASSEMBLY REMOVE | 2 | EA |  | 0
| 103 | 690-90 | REMOVE CONDUIT & CABLING | 2 | PI |  | 0
| 104 | 690-100 | SIGNAL EQUIPMENT, MISCELLANEOUS REMOVE | 2 | PI |  | 0
| 105 | 700-1-11 | SINGLE POST SIGN (F&I GRND MOUNT) (UP TO 12 SF) | 22 | AS |  | 0
| 106 | 700-1-12 | SINGLE POST SIGN (F&I GRND MOUNT) (12-20 SF) | 14 | AS |  | 0
| 107 | 700-1-13 | SINGLE POST SIGN (F&I GRND MOUNT) (21-30 SF) | 2 | AS |  | 0
| 108 | 700-1-50 | SINGLE POST SIGN (RELOCATE) | 5 | AS |  | 0
| 109 | 700-1-60 | SINGLE POST SIGN (REMOVE) | 17 | AS |  | 0
| 110 | 700-2-13 | MULTI-POST SIGN (F&I GRND MOUNT 31-30 SF) | 4 | AS |  | 0
| 111 | 700-2-15 | MULTI-POST SIGN (F&I GRND MOUNT 51-100 SF) | 1 | AS |  | 0
| 112 | 700-3-601 | SIGN PANEL (REMOVE) (UP TO 12 SF) | 3 | EA |  | 0
| 113 | 700-5-22 | INTERNALLY ILLUMINATED SIGN (F&I) (LED) (12-18 SF) | 6 | EA |  | 0
| 114 | 705-10-1 | OBJECT MARKER (TYPE I) | 12 | EA |  | 0
| 115 | 705-11-1 | DELINEATOR, FLEXIBLE TUBULAR | 6 | EA |  | 0
| 116 | 706-3 | RETRO-REFLECTIVE PAVEMENT MARKERS | 575 | EA |  | 0
| 117 | 710-11-290 | PAINTED PAVEMENT MARKINGS (STANDARD) (YELLOW) (ISLAND NOSE) | 88 | SF |  | 0
| 118 | 711-11-123 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (12") | 564 | LF |  | 0
| 119 | 711-11-124 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (18") | 119 | LF |  | 0
| 120 | 711-11-125 | THERMOPLASTIC (STANDARD) (WHITE) (SOLID) (24") | 654 | LF |  | 0
| 121 | 711-11-151 | THERMOPLASTIC (STANDARD) (WHITE) (6")(2' - 4' SKIP) & (6'-10' SKIP) | 552 | LF |  | 0
| 122 | 711-11-160 | THERMOPLASTIC (STANDARD) (WHITE) (MESSAGE) | 1 | EA |  | 0
| 123 | 711-11-170 | THERMOPLASTIC (STANDARD) (WHITE) (ARROW) | 27 | EA |  | 0
| 124 | 711-11-224 | THERMOPLASTIC (STANDARD) (YELLOW) (SOLID) (18") | 66 | LF |  | 0
| 125 | 711-11-251 | THERMOPLASTIC (STANDARD) (YELLOW) (6")(6'-10' SKIP) | 336 | LF |  | 0
| 126 | 711-14-160 | THERMOPLASTIC (PREFORMED) (WHITE) (MESSAGE) | 16 | EA |  | 0
| 127 | 711-14-170 | THERMOPLASTIC (PREFORMED) (WHITE) (ARROWS) | 16 | EA |  | 0
| 128 | 711-16-111 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SOLID) (6") | 3.744 | NM |  | 0
| 129 | 711-16-112 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SOLID) (8") | 0.186 | NM |  | 0
| 130 | 711-16-131 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (WHITE) (SKIP) (6") (10'-30' SKIP) | 3.298 | GM |  | 0
| 131 | 711-16-211 | THERMOPLASTIC (STANDARD-OTHER SURFACES) (YELLOW) (SOLID) (6") | 3.22 | NM |  | 0
| 132 | 711-17 | THERMOPLASTIC (REMOVE EXISTING THERMOPLASTIC PAVEMENT MARKINGS) | 92 | SF |  | 0
| 133 | 785-1-13 | ITS FIELD CABINET (F&I) CONCRETE POLE WITHOUT LOWERING DEVICE | 1 | EA |  | 0
| 134 | 785-2-132 | ITS FIELD CABINET (F&I) (TYPE 336S) (POLE MOUNT) | 1 | EA |  | 0
|  |  | SUBTOTAL ROADWAY, STRIPING & SIGNAL |  |  |  | 0
|  |  | Contract Contingency - 10% of Subtotal Roadway, Striping & Signal (Used only with County Approval) | 10 | % |  | 0
|  |  | TOTAL ROADWAY, STRIPING & SIGNAL, Bid "A" Based on a Completion Time of 730 Calendar Days (Including 10% Contingency) |  |  |  | 0
FORCE MAIN
| U1 |  | 42" DIP (CL350) Force Main | 5300 | LF |  | 0
| U2 |  | 42" DIP RJ (CL350) Force Main | 1500 | LF |  | 0
| U3 |  | 30" DIP (CL 350) Force Main | 70 | LF |  | 0
| U4 |  | 20" DIP (CL 350) Force Main | 345 | LF |  | 0
| U5. |  | *18" DIP (CL 350) Force Main (Addendum #3) (Revise Qty) | 310 | LF |  | 0
| U6 |  | 12" DIP (CL 350) Force Main | 150 | LF |  | 0
| U7 |  | 8" DIP (CL350) Force Main | 95 | LF |  | 0
| U8 |  | 42" Pipe Restraints | 30 | EA |  | 0
| U9 |  | 30" Pipe Restraints | 9 | EA |  | 0
| U10 |  | 20", 18", & 16" Pipe Restraints - Not for 18" Potable Water | 48 | EA |  | 0
| U11 |  | 12" & Smaller Pipe Restraints | 20 | EA |  | 0
| U12 |  | 42" Plug Valve for Force Main | 3 | EA |  | 0
| U13 |  | 30" Plug Valve for Force Main | 2 | EA |  | 0
| U14 |  | 20" or 18" Gate Valve for Force Main | 8 | EA |  | 0
| U15 |  | 20" x 18" Tapping Sleeve & Valve for Force Main | 4 | EA |  | 0
| U16 |  | 12" Gate Valve for Force Main | 2 | EA |  | 0
| U17 |  | *DI Fittings - WASTEWATER (Addendum #3) (Revise Qty) | 55500 | LB |  | 0
| U17A |  | *DI Fitting - WATER) (Addendum #3) (New Bid Item) | 7500 | LB |  | 0
| U18 |  | Connect to Exist. 42" Force Main | 2 | EA |  | 0
| U19 |  | Connect to Exist. 30" Force Main | 1 | EA |  | 0
| U20 |  | Adjust Existing Valve Boxes to Finish Grade | 8 | EA |  | 0
| U21 |  | *Grout Fill Abandoned Mains (Addendum#3) (Revise Qty) | 5500 | CF |  | 0
| U22 |  | *Asphalt Road Restoration (Base & Resurface) Type1 (Addendum #3) (Revise Qty) | 1200 | SY |  | 0
| U23 |  | Asphalt Road Restoration (Base & Resurface)Type 2 | 4500 | SY |  | 0
| U24 |  | Asphalt Road Restoration (Mill & Resurface) | 400 | SY |  | 0
| U25 |  | *8" Optional Base Group 6 (FDOT Index 514) (Addendum #3) (Description Revised) | 4100 | SY |  | 0
| U26 |  | Silt Fence (not on 53rd Ave) | 3000 | LF |  | 0
| U27 |  | Curb & Gutter Replacement | 80 | LF |  | 0
| U28 |  | Hydroseeding | 5000 | SY |  | 0
| U29 |  | Sodding | 2500 | SY |  | 0
| U30 |  | ARV Assembly - Water Mains | 3 | EA |  | 0
| U31 |  | ARV Assembly - Force Mains | 4 | EA |  | 0
| U32 |  | ARV Assembly including Manhole | 6 | EA |  | 0
| U33 |  | Erosion Control | 1 | LS |  | 0
| U34 |  | MOT to FDOT Stds. incl. Temp Roads & Barriers | 1 | LS |  | 0
| U35 |  | 20" Line Stop | 4 | EA |  | 0
| U36 |  | Concrete Thrust Blocks | 120 | CY |  | 0
| U37 |  | Golf FMain 4" HDPE (DR11) & 42x6 Tap Sleeve & GV. | 1 | LS |  | 0
| U38 |  | DELETE IN ITS ENTIRETY (Addendum #3) | 0 | LS |  | 0
| U39 |  | DELETE IN ITS ENTIRETY (Addendum #3) | 0 | LF |  | 0
| U40 |  | Storm Drain Inlet Type C incl. 30LF 12"x18" RCP | 2 | EA |  | 0
| U41 |  | Mobilization | 1 | LS |  | 0
| U42 |  | Miscellaneous Work & Clean Up | 1 | LS |  | 0
|  |  | SUBTOTAL FORCE MAIN |  |  |  | 0
| U43 |  | Contract Contingency - 5% of Subtotal Force Main (Used only with County Approval) | 5 | % |  | 0
|  |  | TOTAL FORCE MAIN, BID "A" Based on a Completion Time of 730 Calendar Days (Including 5% Contingency) |  |  |  | 0
RECLAIMED WATER ITEMS
| U44 |  | 24" DIP (CL 350) Reclaim Waterline (incl. removal) | 1340 | LF |  | 0
| U45 |  | 24" Pipe Restraints | 36 | EA |  | 0
| U46 |  | 24" Butterfly Valve for RCW | 5 | EA |  | 0
| U47 |  | Relocate and Replace Existing Reclaim Meter Assemblies & Hydrants (Addendum #3) (Revise Description) | 1 | LS |  | 0
| U48 |  | Mobilization | 1 | LS |  | 0
|  |  | SUBTOTAL RECLAIMED WATER ITEMS |  |  |  | 0
| U49 |  | Contract Contingency - 5% of Subtotal Reclaimed Water Items (Used only with County Approval) | 5 | % |  | 0
|  |  | TOTAL RECLAIMED WATER ITEMS, BID "A" Based on a Completion Time of 730 Calendar Days (Including 5% Contingency) |  |  |  | 0
POTABLE WATER ITEMS
| U50 |  | 8" DIP (CL350) Waterline (incl. removal) | 145 | LF |  | 0
| U51 |  | 18" Pipe Restraints for Existing 18" Potable Waterline | 100 | EA |  | 0
| U52 |  | Adjust Existing Valve Boxes to Finish Grade | 10 | EA |  | 0
52 | U53 |  | Fire Hydrant Assembly | 7 | EA |  | 0
| U54 |  | 8" Gate Valve for Waterline | 2 | EA |  | 0
|  |  | SUBTOTAL POTABLE WATER ITEMS |  |  |  | 0
| U55 |  | Contract Contingency - 10% of Subtotal Potable Water Items (Used only with County Approval) | 10 | % |  | 0
|  |  | TOTAL POTABLE WATER, BID "A" Based on a Completion Time of 730 Calendar Days (Including 10% Contingency) |  |  |  | 0
|  |  | GRAND TOTAL AWARD FOR ROADWAY, STRIPING & SIGNAL, FORCE MAIN, RECLAIMED WATER AND POTABLE WATER ITEMS. BID "B", BASED ON A COMPLETION TIME OF 640 CALENDAR DAYS (Including Contingency) |  |  |  | 0