## Part 1A Bid Form
BID FORM
(Submit in Triplicate)
Bid "A" Based on Completion Time of 450 Calendar Days
Bidder/Company's Name:
PART IA - RECHARGE WELL RW-1 (12 hours per day 5 days per week drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IA-1. | Mobilize and Demobilize All Equip. to the RW-1 Well Site to Complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for RW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 |  | 0
IA-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IA-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 2,100 feet (Reverse-air) | FT | 1800 |  | 0
IA-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 42-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 34-inch Diameter to 1,000 feet (Reverse-air) | FT | 700 |  | 0
| c. 23-inch Diameter up to 2,100 feet (Reverse-air) | FT | 1100 |  | 0
IA-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 1,000 feet | EA | 1 |  | 0
| d. Reamed Hole to 1,000 feet | EA | 1 |  | 0
| e. Pilot hole up to 2,100 feet | EA | 1 |  | 0
| f. Completed Well up to 2,100 feet | EA | 1 |  | 0
| g. Temperature Log Following Each Cement Stage | EA | 5 |  | 0
IA-6. | Furnish and Install Casing:
| a. 34-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 24-inch Dia. Carbon Steel | FT | 1000 |  | 0
IA-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 3200 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 1000 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 1000 |  | 0
IA-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 20 |  | 0
IA-9. | Pressure Test Casing - Successfully Complete Pressure Test on Final 24-Inch Casing Prior to Drilling Out Plug, Complete | LS | 1 |  | 0
IA-10. | Cores - During Pilot Hole or Open Hole Drilling, Provide 10-Foot Length, 4-Inch Diameter Cores at Selected Intervals, Complete | FT | 40 |  | 0
IA-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 4 |  | 0
IA-12. | Packer Test Pumping Time, Complete | HR | 40 |  | 0
IA-13. | Pumping Test Setup, Complete | LS | 1 |  | 0
IA-14. | Pumping Test Pumping Time, Complete | HR | 10 |  | 0
IA-15. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IA-16. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IA-17. | Standby Time (Max. 12 hr/day) | HR | 40 |  | 0
IA-18. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 40 |  | 0
IA-19. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 35 |  | 0
| b. Exhibit 1, List A | EA | 30 |  | 0
| c. Exhibit 1, List B | EA | 8 |  | 0
| d. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IA |  | 0

## Part 2A Bid Form
BID FORM
(Submit in Triplicate)
Bid "A" Based on Completion Time of 450 Calendar Days
PART IIA- RECHARGE ZONE MONITOR WELL RZMW-1 (12 /5 drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IIA-1. | Mobilize and Demobilize All Equip. to the RZMW-1 Well Site to complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for RZMW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 |  | 0
IIA-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IIA-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 1,000 feet (Reverse-air) | FT | 700 |  | 0
IIA-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 20-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 14-inch Diameter to 1,000 feet (Reverse-air) | FT | 700 |  | 0
| c. 6-inch Diameter to 1,050 feet (Reverse-air) | FT | 50 |  | 0
IIA-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 1,000 feet | EA | 1 |  | 0
| d. Reamed Hole to 1,000 feet | EA | 1 |  | 0
| e. Completed Well to 1,050 feet | EA | 1 |  | 0
IIA-6. | Furnish and Install Casing:
| a. 14-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 6-inch Dia. Carbon Steel | FT | 1000 |  | 0
IIA-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 1500 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 200 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 200 |  | 0
IIA-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 5 |  | 0
IIA-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IIA-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IIA-11. | Standby Time (Max. 12 hr/day) | HR | 20 |  | 0
IIA-12. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 |  | 0
IIA-13. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 35 |  | 0
| b. Exhibit 1, List A | EA | 15 |  | 0
| c. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IIA |  | 0

## Part 3A Bid Form
BID FORM
(Submit in Triplicate)
Bid "A" Based on Completion Time of 450 Calendar Days
PART IIIA- SUWANNEE LIMESTONE MONITOR WELL SLMW-1 (12 /5 drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IIIA-1. | Mobilize and Demobilize All Equip. to the SLMW-1 Well Site to complete Drilling (in a 12 Hr/Day, 5 Day/Week Schedule) and Testing Activities for SLMW-1 , Complete | LS | 1 |  | 0
IIIA-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IIIA-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 650 feet (Reverse-air) | FT | 350 |  | 0
IIIA-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 20-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 14-inch Diameter to 650 feet (Reverse-air) | FT | 350 |  | 0
| c. 6-inch Diameter to 700 feet (Reverse-air) | FT | 50 |  | 0
IIIA-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 650 feet | EA | 1 |  | 0
| d. Reamed Hole to 650 feet | EA | 1 |  | 0
| e. Completed Well to 700 feet | EA | 1 |  | 0
IIIA-6. | Furnish and Install Casing:
| a. 14-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 6-inch Dia. Carbon Steel | FT | 650 |  | 0
IIIA-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 850 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 200 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 200 |  | 0
IIIA-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 5 |  | 0
IIIA-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IIIA-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IIIA-11. | Standby Time (Max. 12 hr/day) | HR | 20 |  | 0
IIIA-12. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 |  | 0
IIIA-13. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Exhibit 1, List A | EA | 9 |  | 0
| b. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IIIA |  | 0

## Part 4A Bid Form
BID FORM
(Submit in Triplicate)
Bid "A" Based on Completion Time of 450 Calendar Days
PART IV- WELL ACIDIZATION (ADD ALTERNATE BID ITEM)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IV-1. | Mobilization - If Required, Re-Mobilize all Equip. Necessary to Acidize Recharge Well | EA | 1 |  | 0
IV-2. | Acidization Setup - Setup for Acidization of RW-1, Complete, Including well kills | EA | 1 |  | 0
IV-3. | Furnish and Emplace Acid, Complete | 1000 GAL | 25 |  | 0
IV-4. | Pump Set - Set Pump and Discharge Line for Post Acid Development, Complete | EA | 1 |  | 0
IV-5. | Development Time | HR | 24 |  | 0
|  |  |  | TOTAL PART IVA (ADD ALTERNATE BID) - AWARD AT COUNTY'S DISCRETION | 0
Note: Acidization will only be completed during daylight hours

## Summary of Bid A
SUMMARY OF BID A
Drilling Schedule 12 hrs/day, 5 days/wk
Time of Substantial Completion : 450 Calendar Days
Total Part IA – Recharge Well (RW-1) |  | 0
Total Part IIA – Recharge Zone Monitor Well (RZMW-1) |  | 0
Total Part IIIA – Suwannee Limestone Zone Monitor Well (SLMW-1) |  | 0
Total Base Bid - Parts IA through IIIA |  | 0
Contract Contingency - 10% of Base Bid (Part IA, IIA, IIIA) |  | 0
Total - Parts IA through IIIA and Contingency |  | 0
Total Part IVA – Well Acidization (Add Alternate) - Award at County's Discretion |  | 0
TOTAL A Part I-III, Contingency, and Part IV |  | 0
Addendum No. 1 Acknowledgment
(Signature)

## Part 1B Bid Form
BID FORM
(Submit in Triplicate)
Bid "B" Based on Completion Time of 240 Calendar Days
Bidder/Company's Name:
PART IB - RECHARGE WELL RW-1 (24 hours per day 5 days per week drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IB-1. | Mobilize and Demobilize All Equip. to the RW-1 Well Site to Complete Drilling (in a 24 Hr/Day, 5 Day/Week Schedule) and Testing Activities for RW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 |  | 0
IB-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IB-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 2,100 feet (Reverse-air) | FT | 1800 |  | 0
IB-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 42-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 34-inch Diameter to 1,000 feet (Reverse-air) | FT | 700 |  | 0
| c. 23-inch Diameter up to 2,100 feet (Reverse-air) | FT | 1100 |  | 0
IB-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 1,000 feet | EA | 1 |  | 0
| d. Reamed Hole to 1,000 feet | EA | 1 |  | 0
| e. Pilot hole up to 2,100 feet | EA | 1 |  | 0
| f. Completed Well up to 2,100 feet | EA | 1 |  | 0
| g. Temperature Log Following Each Cement Stage | EA | 5 |  | 0
IB-6. | Furnish and Install Casing:
| a. 34-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 24-inch Dia. Carbon Steel | FT | 1000 |  | 0
IB-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 3200 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 1000 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 1000 |  | 0
IB-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 20 |  | 0
IB-9. | Pressure Test Casing - Successfully Complete Pressure Test on Final 24-Inch Casing Prior to Drilling Out Plug, Complete | LS | 1 |  | 0
IB-10. | Cores - During Pilot Hole or Open Hole Drilling, Provide 10-Foot Length, 4-Inch Diameter Cores at Selected Intervals, Complete | FT | 40 |  | 0
IB-11. | Packer Test Set up - Furnish, Setup, Operate, and Remove all Equip. Necessary to Run Packer Pumping Test, Complete | EA | 4 |  | 0
IB-12. | Packer Test Pumping Time, Complete | HR | 40 |  | 0
IB-13. | Pumping Test Setup, Complete | LS | 1 |  | 0
IB-14. | Pumping Test Pumping Time, Complete | HR | 10 |  | 0
IB-15. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IB-16. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IB-17. | Standby Time | HR | 40 |  | 0
IB-18. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 40 |  | 0
IB-19. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 20 |  | 0
| b. Exhibit 1, List A | EA | 30 |  | 0
| c. Exhibit 1, List B | EA | 8 |  | 0
| d. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IB |  | 0

## Part 2B Bid Form
BID FORM
(Submit in Triplicate)
Bid "B" Based on Completion Time of 240 Calendar Days
PART IIB- RECHARGE ZONE MONITOR WELL RZMW-1 (24 /5 drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IIB-1. | Mobilize and Demobilize All Equip. to the RZMW-1 Well Site to complete Drilling (in a 24 Hr/Day, 5 Day/Week Schedule) and Testing Activities for RZMW-1, Complete, Including Drilling Pad and Four Water Table Monitoring Wells | LS | 1 |  | 0
IIB-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IIB-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 1,000 feet (Reverse-air) | FT | 700 |  | 0
IIB-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 20-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 14-inch Diameter to 1,000 feet (Reverse-air) | FT | 700 |  | 0
| c. 6-inch Diameter to 1,050 feet (Reverse-air) | FT | 50 |  | 0
IIB-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 1,000 feet | EA | 1 |  | 0
| d. Reamed Hole to 1,000 feet | EA | 1 |  | 0
| e. Completed Well to 1,050 feet | EA | 1 |  | 0
IIB-6. | Furnish and Install Casing:
| a. 14-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 6-inch Dia. Carbon Steel | FT | 1000 |  | 0
IIB-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 1500 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 200 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 200 |  | 0
IIB-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 5 |  | 0
IIB-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IIB-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IIB-11. | Standby Time | HR | 20 |  | 0
IIB-12. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 |  | 0
IIB-13. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Water Table Monitoring Wells Weekly Compliance Samples | EA | 15 |  | 0
| b. Exhibit 1, List A | EA | 15 |  | 0
| c. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IIB |  | 0

## Part 3B Bid Form
BID FORM
(Submit in Triplicate)
Bid "B" Based on Completion Time of 240 Calendar Days
PART IIIB- SUWANNEE LIMESTONE MONITOR WELL SLMW-1 (24 /5 drilling schedule)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IIIB-1. | Mobilize and Demobilize All Equip. to the SLMW-1 Well Site to complete Drilling (in a 24 Hr/Day, 5 Day/Week Schedule) and Testing Activities for SLMW-1 , Complete | LS | 1 |  | 0
IIIB-2. | Set Pit Casing, Complete | LS | 1 |  | 0
IIIB-3. | Drill Pilot Hole - Drill Nominal 8 to 12-¼ -Inch Dia. Pilot Hole Using Mud Rotary or Reverse-Air Drilling Techniques, Complete to Depth of:
| a. 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 650 feet (Reverse-air) | FT | 350 |  | 0
IIIB-4. | Pilot Hole Reaming or Open Hole to Depth of:
| a. 20-inch Diameter to 300 feet (Mud Rotary) | FT | 300 |  | 0
| b. 14-inch Diameter to 650 feet (Reverse-air) | FT | 350 |  | 0
| c. 6-inch Diameter to 700 feet (Reverse-air) | FT | 50 |  | 0
IIIB-5. | Geophysical Logging - Furnish, Setup, Operate, and Remove all Equip. to Conduct Geophysical Logs in Accordance with Table 1 of Section 02679 on:
| a. Pilot Hole to 300 feet | EA | 1 |  | 0
| b. Reamed Hole to 300 feet | EA | 1 |  | 0
| c. Pilot Hole to 650 feet | EA | 1 |  | 0
| d. Reamed Hole to 650 feet | EA | 1 |  | 0
| e. Completed Well to 700 feet | EA | 1 |  | 0
IIIB-6. | Furnish and Install Casing:
| a. 14-inch Dia. Carbon Steel | FT | 300 |  | 0
| b. 6-inch Dia. Carbon Steel | FT | 650 |  | 0
IIIB-7. | Grout Casing - Grout Carbon Steel Casing from Bottom to Land Surface and Pilot Holes Prior to Reaming Using ASTM Type II Cement with up to:
| a. 0% Bentonite (Neat) | Cubic Foot | 850 |  | 0
| b. Up to 6% Bentonite | Cubic Foot | 200 |  | 0
| c. Up to 12% Bentonite | Cubic Foot | 200 |  | 0
IIIB-8. | Gravel - Furnish and Emplace Clean Gravel Used to Plug Cavities, Complete | Cubic Yard | 5 |  | 0
IIIB-9. | Development - Develop Well by Air Lifting, Complete | HR | 24 |  | 0
IIIB-10. | Temporary Wellhead - Complete Wellhead in accordance with the Drawings, Complete | LS | 1 |  | 0
IIIB-11. | Standby Time | HR | 20 |  | 0
IIIB-12. | Extra Work - Furnish Drilling Rig and Crew to Perform Extra Work Not Included in the Specifications When Directed by the ENGINEER, Complete | HR | 20 |  | 0
IIIB-13. | Water Sampling - Collect, Analyze, and Report Water Samples in Accordance with Section 02311 for:
| a. Exhibit 1, List A | EA | 9 |  | 0
| b. Exhibit 1, List C | EA | 1 |  | 0
|  |  | TOTAL PART IIIB |  | 0

## Part 4B Bid Form
BID FORM
(Submit in Triplicate)
Bid "B" Based on Completion Time of 240 Calendar Days
PART IVB - WELL ACIDIZATION (ADD ALTERNATE BID ITEM)
Pay Item | Description | Unit | Est. QTY | Unit Cost | Computed Total Price for Item
IV-1. | Mobilization - If Required, Re-Mobilize all Equip. Necessary to Acidize Recharge Well | EA | 1 |  | 0
IV-2. | Acidization Setup - Setup for Acidization of RW-1, Complete, Including well kills | EA | 1 |  | 0
IV-3. | Furnish and Emplace Acid, Complete | 1000 GAL | 25 |  | 0
IV-4. | Pump Set - Set Pump and Discharge Line for Post Acid Development, Complete | EA | 1 |  | 0
IV-5. | Development Time | HR | 24 |  | 0
|  |  |  | TOTAL PART IVB (ADD ALTERNATE BID) - AWARD AT COUNTY'S DISCRETION | 0
Note: Acidization will only be completed during daylight hours

## Summary of Bid B
SUMMARY OF BID B
Drilling Schedule 24 hrs/day, 5 days/wk
Time of Substantial Completion : 240 Calendar Days
Total Part IB – Recharge Well (RW-1) |  | 0
Total Part IIB – Recharge Zone Monitor Well (RZMW-1) |  | 0
Total Part IIIB – Suwannee Limestone Zone Monitor Well (SLMW-1) |  | 0
Total Base Bid - Parts IB through IIIB |  | 0
Contract Contingency - 10% of Base Bid (Part IB, IIB, IIIB) |  | 0
Total - Parts IB through IIIB and Contingency |  | 0
Total Part IVB – Well Acidization (Add Alternate) - Award at County's Discretion |  | 0
TOTAL B Part I-III, Contingency, and Part IV |  | 0
Addendum No. 1 Acknowledgment
(Signature)