## bid_form _robinson resto__BLANK
BID FORM IFB#15-2513-OV (Submit in Duplicate) ROBINSON PRESERVE EXPANSION PHASE II BASED ON A COMPLETION TIME OF 300 CALENDAR DAYS (Addendum#6)
ITEM NO. | DESCRIPTION | UNIT | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($)
1.1 | MOBILIZATION | LS | 1 |  | 0
1.2 | MISCELLANEOUS PERMITS AND BONDING | LS | 1 |  | 0
1.3 | CONSTRUCTION SURVEYING AND STAKEOUT (INCLUDING RECORD DRAWINGS) | LS | 1 |  | 0
1.4 | EROSION AND TURBIDITY CONTROL
1.4.1.1 | Staked Silt Fence | LF | 17540 |  | 0
1.4.1.2 | Floating/Staked Turbidity Barrier | LF | 150 |  | 0
1.4.1.3 | Erosion and Turbidity Control Maintenance | LS | 1 |  | 0
1.5 | CLEARING AND GRUBBING
1.5.1 | Clearing and Grubbing | AC | 130.7 |  | 0
1.6 | EXCAVATION, EMBANKMENT, AND STOCKPILING
1.6.1.1 | Excavation | BCY | 559708 |  | 0
1.6.1.2 | Embankment (Haul, place, compact) | CCY | 303766 |  | 0
1.6.1.3 | Stockpile Point B (Load, haul & stockpile) | TMCY | 240000 |  | 0
1.6.1.4 | Oyster Islands 4" Thick Large Washed Shell (3" min) | SY | 10000 |  | 0
1.6.1.5 | Shell Weirs 8" Thick Large Washed Shell (3" min) | SY | 145 |  | 0
1.6.1.6 | Disposal of Unsuitable Material (Addendum #2) | TON | 1000 |  | 0
1.7 | FINISHED GRADING
1.7.1.1 | Pond Areas | AC | 58 |  | 0
1.7.1.2 | Dry Detention Area | AC | 1.43 |  | 0
1.7.1.3 | Embankment Areas | AC | 71.27 |  | 0
1.8 | SOD AND SEED/MULCH
1.8.1.1 | Sod | SY | 29282 |  | 0
1.8.1.2 | Seed and Mulch | SY | 338870 |  | 0
1.9 | DRAINAGE STRUCTURES
1.9.1.1 | Type "C" Inlet | EA | 11 |  | 0
1.9.1.2 | Type "C" Inlet Control Structure w/ Skimmer | EA | 1 |  | 0
1.9.1.3 | 12" PCP | LF | 400 |  | 0
1.9.1.4 | 18" PCP | LF | 1171 |  | 0
1.9.1.5 | 24" PCP | LF | 40 |  | 0
1.9.1.6 | 36" PCP | LF | 70 |  | 0
1.9.1.7 | 15" RCP | LF | 128 |  | 0
1.9.1.8 | 12" MES (includes rip-rap) | EA | 4 |  | 0
1.9.1.9 | 15" MES (includes rip-rap) | EA | 1 |  | 0
1.9.1.10 | 6" Treatment Underdrain System (Complete) | LF | 60 |  | 0
1.9.1.11 | Underdrain Cleanout | EA | 1 |  | 0
1.10. | SHELL TRAILS (Complete)
1.10.1.1 | Trail Stake-out and As-builts | LS | 1 |  | 0
1.10.1.2 | Shell Trails - 4" Bank Run Shell | SY | 7874 |  | 0
1.10.1.3 | Shell Maintenance Trail - 4" Bank Run Shell | SY | 2292 |  | 0
1.10.1.4 | Kayak Storage Area - 4" Bank Run Shell | SY | 524 |  | 0
1.11 | ASPHALT TRAILS (Complete)
1.11.1.1 | Trail Stake-out and As-builts | LS | 1 |  | 0
1.11.1.2 | 6" Cement Treated Base LBR 100 | SY | 13342 |  | 0
1.11.1.3 | 1" Asphaltic Concrete Type S-III | SY | 12316 |  | 0
1.12 | PARKING AREA & DRIVE
1.12.1.1 | Stake-out and As-builts | LS | 1 |  | 0
1.12.1.2 | 3/4" Asphaltic Concrete Type S-III (Initial Lift) (Addendum #2) | SY | 5242 |  | 0
1.12.1.3 | 3/4" Asphaltic Concrete Type S-III (Final Lift) (Addendum #2) | SY | 5242 |  | 0
1.12.1.4 | 6" Crushed Concrete Base LBR 100 | SY | 5612 |  | 0
1.12.1.5 | 6" Stabilized Subgrade LBR 40 | SY | 5819 |  | 0
1.12.1.6 | Shell Parking - 4" Bank Run Shell | SY | 2787 |  | 0
1.12.1.7 | 8" Stabilized Subgrade LBR 40 | SY | 2787 |  | 0
1.12.1.8 | Kayak Launch Sand (12" Depth) | CCY | 276 |  | 0
1.12.1.9 | Wheel Stops | EA | 113 |  | 0
1.12.1.10 | Handicap Parking Signs | EA | 5 |  | 0
1.12.1.11 | Handicap Striping (5 Spaces & 4 Loading Zones) | LS | 1 |  | 0
1.12.1.12 | 12" Wide Crosswalk (Thermoplastic) | LF | 336 |  | 0
1.13 | PEDESTRIAN BRIDGES
1.13.1.1 | Structural Design, Inspection, Certification | LS | 1 |  | 0
1.13.1.2 | Construction Surveying and Record Drawings | LS | 1 |  | 0
1.13.1.3 | Pedestrian Bridges 2 and 3 (12' Width) | LF | 180 |  | 0
| SUBTOTAL |  |  |  | 0
| Contingency Amount (10% of Subtotal) (Used only with County Approval) | % | 10 |  | 0
| TOTAL AWARD BASED ON A COMPLETION TIME OF 300 CALENDAR DAYS (Addendum #2) |  |  |  | 0

## bid_form _subcontract. %
BID FORM IFB#15-2513-OV / SUBCONTRACTOR'S % FORM (Submit in Duplicate) ROBINSON PRESERVE EXPANSION PHASE II BASED ON A COMPLETION TIME OF 300 CALENDAR DAYS (Addendum #6)
ITEM NO. | DESCRIPTION | % | MBE/WBE/SMALL BUSINESS | DESCRIPTION OF WORK BY SUBCONTRACTOR
1.1 | MOBILIZATION
1.2 | MISCELLANEOUS PERMITS AND BONDING
1.3 | CONSTRUCTION SURVEYING AND STAKEOUT (INCLUDING RECORD DRAWINGS)
1.4 | EROSION AND TURBIDITY CONTROL
1.4.1.1 | Staked Silt Fence
1.4.1.2 | Floating/Staked Turbidity Barrier
1.4.1.3 | Erosion and Turbidity Control Maintenance
1.5 | CLEARING AND GRUBBING
1.5.1 | Clearing and Grubbing
1.6 | EXCAVATION, EMBANKMENT, AND STOCKPILING
1.6.1.1 | Excavation
1.6.1.2 | Embankment (Haul, place, compact)
1.6.1.3 | Stockpile Point B (Load, haul & stockpile)
1.6.1.4 | Oyster Islands 4" Thick Large Washed Shell (3" min)
1.6.1.5 | Shell Weirs 8" Thick Large Washed Shell (3" min)
1.6.1.6 | Disposal of Unsuitable Material (Addendum #2)
1.7 | FINISHED GRADING
1.7.1.1 | Pond Areas
1.7.1.2 | Dry Detention Area
1.7.1.3 | Embankment Areas
1.8 | SOD AND SEED/MULCH
1.8.1.1 | Sod
1.8.1.2 | Seed and Mulch
1.9 | DRAINAGE STRUCTURES
1.9.1.1 | Type "C" Inlet
1.9.1.2 | Type "C" Inlet Control Structure w/ Skimmer
1.9.1.3 | 12" PCP
1.9.1.4 | 18" PCP
1.9.1.5 | 24" PCP
1.9.1.6 | 36" PCP
1.9.1.7 | 15" RCP
1.9.1.8 | 12" MES (includes rip-rap)
1.9.1.9 | 15" MES (includes rip-rap)
1.9.1.10 | 6" Treatment Underdrain System (Complete)
1.9.1.11 | Underdrain Cleanout
1.10. | SHELL TRAILS (Complete)
1.10.1.1 | Trail Stake-out and As-builts
1.10.1.2 | Shell Trails - 4" Bank Run Shell
1.10.1.3 | Shell Maintenance Trail - 4" Bank Run Shell
1.10.1.4 | Kayak Storage Area - 4" Bank Run Shell
1.11 | ASPHALT TRAILS (Complete)
1.11.1.1 | Trail Stake-out and As-builts
1.11.1.2 | 6" Cement Treated Base LBR 100
1.11.1.3 | 1" Asphaltic Concrete Type S-III
1.12 | PARKING AREA & DRIVE
1.12.1.1 | Stake-out and As-builts
1.12.1.2 | 3/4" Asphaltic Concrete Type S-III (Initial Lift) (Addendum #2)
1.12.1.3 | 3/4" Asphaltic Concrete Type S-III (Final Lift) (Addendum #2)
1.12.1.4 | 6" Crushed Concrete Base LBR 100
1.12.1.5 | 6" Stabilized Subgrade LBR 40
1.12.1.6 | Shell Parking - 4" Bank Run Shell
1.12.1.7 | 8" Stabilized Subgrade LBR 40
1.12.1.8 | Kayak Launch Sand (12" Depth)
1.12.1.9 | Wheel Stops
1.12.1.10 | Handicap Parking Signs
1.12.1.11 | Handicap Striping (5 Spaces & 4 Loading Zones)
1.12.1.12 | 12" Wide Crosswalk (Thermoplastic)
1.13 | PEDESTRIAN BRIDGES
1.13.1.1 | Structural Design, Inspection, Certification
1.13.1.2 | Construction Surveying and Record Drawings
1.13.1.3 | Pedestrian Bridges 2 and 3 (12' Width)
This is a duplication of the Bid Items where the Bidder shall state the percentage of work (of each item listed) and a description of the Work which shall be performed by a Subcontractor.