## Cortez Gardens EOPCC
APPENDIX K, BID PRICING FORM 21-TA003637 DJ, CORTEZ GARDENS SUBDIVISION WATER MAIN REPLACEMENT COUNTY PROJECT NO. 6097270 BID A BASED ON 275 CALENDAR DAYS
MCG Engieers Opinion of Costs
ITEM NO. | DESCRIPTION | UNITS | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($) | UNIT PRICE ($) | EXTENDED PRICE ($)
1 | Grout Abandoned 4" Pipe | LF | 1654 | 24 | 39696 |  | 0
2 | Grout Abandoned 6" Pipe | LF | 45 | 28 | 1260 |  | 0
3 | F&I 4" Caps | EA | 4 | 1450 | 5800 |  | 0
4 | F&I 6" Caps | EA | 1 | 1750 | 1750 |  | 0
5 | F&I 6" Polyvinyl Chloride (PVC) Pipe | LF | 533 | 64 | 34112 |  | 0
6 | F&I 6" Class 350 Ductile Iron (DIP) Pipe | LF | 720 | 100 | 72000 |  | 0
7 | F&I 6" Gate Valve | EA | 11 | 2800 | 30800 |  | 0
8 | F&I 6" Sleeves | EA | 6 | 2600 | 15600 |  | 0
9 | F&I Water Services Connection (Short 1" Polyethylene Pipe) | EA | 18 | 1450 | 26100 |  | 0
10 | F&I Water Services Connection (Long 1" Polyethylene Pipe) | EA | 13 | 2650 | 34450 |  | 0
11 | Remove Water Meter Box Assembly | EA | 70 | 250 | 17500 |  | 0
12 | F&I Fire Hydrant Assembly | EA | 2 | 7300 | 14600 |  | 0
13 | F&I Water Meter Box Assembly | EA | 32 | 950 | 30400 |  | 0
14 | F&I 6" X 6" Tee | EA | 5 | 1300 | 6500 |  | 0
15 | F&I 6" 45o Bend | EA | 13 | 1200 | 15600 |  | 0
16 | F&I 6" 90o Bend | EA | 3 | 1750 | 5250 |  | 0
17 | Re-Establish Residential Service Lines | EA | 32 | 1850 | 59200 |  | 0
18 | Maintenance of Traffic (MOT) | LS | 1 | 19500 | 19500 |  | 0
19 | Erosion And Sedimentation Control | LS | 1 | 4500 | 4500 |  | 0
20 | Restoration | LS | 1 | 115000 | 115000 |  | 0
| SubTotal Construction Cost |  |  |  | 549618 |  | 0
21 | Mobilization | LS | 1 | 43461.8 | 43461.8 |  | 0
22 | Miscellaneous Work & Clean Up | LS | 1 | 43461.8 | 43461.8 |  | 0
23 | Record Drawings | LS | 1 | 13038.54 | 13038.54 |  | 0
24 | Contract Contingency (10% of Subtotal Construction Cost) | % | 10% |  | 54961.8 |  | 0
| Total Construction Cost |  |  |  | 704541.94 |  | 0
APPENDIX K, BID PRICING FORM 21-TA003637 DJ, CORTEZ GARDENS SUBDIVISION WATER MAIN REPLACEMENT COUNTY PROJECT NO. 6097270 BID B BASED ON 365 CALENDAR DAYS
MCG Engieers Opinion of Costs
ITEM NO. | DESCRIPTION | UNITS | QTY. | UNIT PRICE ($) | EXTENDED PRICE ($) | UNIT PRICE ($) | EXTENDED PRICE ($)
1 | Grout Abandoned 4" Pipe | LF | 1654 | 24 | 39696 |  | 0
2 | Grout Abandoned 6" Pipe | LF | 45 | 28 | 1260 |  | 0
3 | F&I 4" Caps | EA | 4 | 1450 | 5800 |  | 0
4 | F&I 6" Caps | EA | 1 | 1750 | 1750 |  | 0
5 | F&I 6" Polyvinyl Chloride (PVC) Pipe | LF | 533 | 64 | 34112 |  | 0
6 | F&I 6" Class 350 Ductile Iron (DIP) Pipe | LF | 720 | 100 | 72000 |  | 0
7 | F&I 6" Gate Valve | EA | 11 | 2800 | 30800 |  | 0
8 | F&I 6" Sleeves | EA | 6 | 2600 | 15600 |  | 0
9 | F&I Water Services Connection (Short 1" Polyethylene Pipe) | EA | 18 | 1450 | 26100 |  | 0
10 | F&I Water Services Connection (Long 1" Polyethylene Pipe) | EA | 13 | 2650 | 34450 |  | 0
11 | Remove Water Meter Box Assembly | EA | 70 | 250 | 17500 |  | 0
12 | F&I Fire Hydrant Assembly | EA | 2 | 7300 | 14600 |  | 0
13 | F&I Water Meter Box Assembly | EA | 32 | 950 | 30400 |  | 0
14 | F&I 6" X 6" Tee | EA | 5 | 1300 | 6500 |  | 0
15 | F&I 6" 45o Bend | EA | 13 | 1200 | 15600 |  | 0
16 | F&I 6" 90o Bend | EA | 3 | 1750 | 5250 |  | 0
17 | Re-Establish Residential Service Lines | EA | 32 | 1850 | 59200 |  | 0
18 | Maintenance of Traffic (MOT) | LS | 1 | 19500 | 19500 |  | 0
19 | Erosion And Sedimentation Control | LS | 1 | 4500 | 4500 |  | 0
20 | Restoration | LS | 1 | 115000 | 115000 |  | 0
| SubTotal Construction Cost |  |  |  | 549618 |  | 0
21 | Mobilization | LS | 1 | 43461.8 | 43461.8 |  | 0
22 | Miscellaneous Work & Clean Up | LS | 1 | 43461.8 | 43461.8 |  | 0
23 | Record Drawings | LS | 1 | 13038.54 | 13038.54 |  | 0
24 | Contract Contingency (10% of Subtotal Construction Cost) | % | 10% |  | 54961.8 |  | 0
| Total Construction Cost |  |  |  | 704541.94 |  | 0
BIDDER NAME______________________________________________
BIDDER SIGNATURE_________________________________________