## Bid Tab A
APPENDIX K, BID PRICING FORM
IFBC No. 21-TA003796JH
26th AVENUE EAST FROM 27TH STREET EAST TO 45TH STREET EAST SIDEWALK
BID "A" BASED ON 270 CALENDAR DAYS COMPLETION
Bidders must provide prices for each line item for their bid to be considered responsive
ITEM NO. | SPEC. | ITEM DESCRIPTION | U/M | EST. QTY. | UNIT PRICE | EXTENDED PRICE
I. Sidewalk & Bridge
1 |  | Mobilization | LS | 1
2 |  | Maintenance of Traffic (MOT) | LS | 1
3 | 104-10-3 | Sediment Barrier | LF | 3481
4 | 104-11 | Floating Turbidity Barrier | LF | 27
5 | 104-18 | Inlet Protection System | EA | 1
6 | 110-1-1 | Clearing & Grubbing | AC | 3.6
7 | 120-1 | Regular Excavation | CY | 30
8 | 120-4 | Subsoil Excavation | CY | 10
9 | 120-6 | Embankment | CY | 30
10 | 125-1 | EXCAVATION FOR STRUCTURES (BRIDGE) | CY | 35
11 | 125-3 | SELECT BEDDING MATERIAL (BRIDGE) | CY | 7
12 | 339-1 | Miscellaneous Asphalt Pavement | TN | 6
13 | 400-2-2 | Conc Class Class II, End Walls | CY | 25
14 | 400-4-5 | CONC CLASS IV, SUBSTRUCTURE (BRIDGE) | CY | 20.3
15 | 415-1-5 | REINF STEEL- SUBSTRUCTURE (BRIDGE) | LB | 1336
16 | 430-175-115 | Pipe Culvert, Optional Material, Round, 15" S/CD | LF | 230
17 | 430-175-118 | Pipe Culvert, Optional Material, Round, 18" S/CD | LF | 233
18 | 430-175-236 | Pipe Culvert, Opt Material, Other Shape -29"x45" | LF | 8
19 | 430-536-102 | Straight Concrete Endwalls, 36", Single, 0 Degrees, Elliptical | EA | 2
20 | 430-530-100 | Straight Concrete Endwalls, 30", Single, 0 Degrees,Round | EA | 2
21 | 430-982-123 | Mitered End Section, Optional Round, 15" CD | EA | 2
22 | 430-982-125 | Mitered End Section, Optional Round, 18" CD | EA | 3
23 | 455-112-14 | AUGER GROUTED PILE, 14" (BRIDGE) | LF | 120
24 | 455-119-101 | STATIC LOAD TEST(BRIDGE) | EA | 1
25 | 460-5 | PREFABRICATED ALUMINUM PEDESTRIAN BRIDGE (95' x 6' Interior Width) | EA | 1
26 | 515-1-2 | Pipe Handrail - Guiderail, Aluminum | LF | 64
27 | 522-1 | Concrete Sidewalk 4" Thick, including HC Ramps | SY | 1828
28 | 522-2 | Concrete Sidewalk and Driveways, 6" Thick | SY | 150
29 | 527-2 | Detectable Warnings | SF | 50
30 | 570-1-2 | Performance Turf, Sod | SY | 12890
31 | 530-3-4 | Riprap, Rubble, F&I, Ditch Lining | TN | 20
32 | 530-74 | Bedding Stone | TN | 12
33 | 536-1-0 | Guardrail - Roadway, General TL-3 w/ end treatment | LF | 171
34 | 700-1-11 | Single Post Sign, F&I Ground Mount, Up To 12 SF | EA | 1
35 | 711-11-123 | Thermoplastic, Standard, White, Solid, 12" For Crosswalk | LF | 520
36 | 711-11-125 | Thermoplastic, Standard, White, Solid, 24" For Stop Line | LF | 34
37 | MC4 | Boardwalk | SF | 2121
38 | MC7 | PVC Fence and Gates (Sugar Creek Country Club) | LS | 1
39 | MC8 | Drop Inlet | EA | 2
40 | MC9 | Remove Existing MES/Connect to Existing Pipe | EA | 5
Subtotal (Sidewalk & Bridge) | [5 empty] | 0
II. Forcemain (Utilities)
1 |  | Asphalt Pavement Restoration
1.01 |  | Base & Resurface | SY | 40
1.02 |  | Mill & Resurface | SY | 185
2 |  | PVC (C-900, DR-18)
2.1 |  | 4" PVC | LF | 235
2.2 |  | 8" PVC (Casing) | LF | 18
3 |  | Ductile Iron Fittings
3.1 |  | 4" 45-Degree Bend | EA | 12
4 |  | Pipe Joint Restraints (4") | EA | 20
5 |  | Plug Valve (4") | EA | 3
6 |  | Air Release Valve Assembly, (Above Ground) | EA | 1
7 |  | Air Release Valve Assembly, (Waterway Canal Crossing) | EA | 1
8 |  | Utility Pipe - Remove & Dispose | LF | 235
9 |  | Sewage Disposal-Pumper Trucks | LS | 1
10 |  | Traffic Control Plan | LS | 1
11 |  | Record Drawing | LS | 1
Subtotal (Forcemain Utilities) | [5 empty] | 0
Sections I, II Construction Total | [5 empty] | 0
CONTRACT CONTINGENCY WORK (USED ONLY WITH COUNTY APPROVAL) |  |  |  |  | 10% | 0
TOTAL BID "A" SECTIONS I, II WITH CONTINGENCY - BASED ON COMPLETITION TIME OF 270 CALENDAR DAYS | [5 empty] | 0
Bidder Name:_______________________________________
Authorized Signature:_________________________________

## Bid Tab B
APPENDIX K, BID PRICING FORM
IFBC No. 21-TA003796JH
26th AVENUE EAST FROM 27TH STREET EAST TO 45TH STREET EAST SIDEWALK
BID "B" BASED ON 360 CALENDAR DAYS COMPLETION
Bidders must provide prices for each line item for their bid to be considered responsive
ITEM NO. | SPEC. | ITEM DESCRIPTION | U/M | EST. QTY. | UNIT PRICE | EXTENDED PRICE
I. Sidewalk & Bridge
1 |  | Mobilization | LS | 1
2 |  | Maintenance of Traffic (MOT) | LS | 1
3 | 104-10-3 | Sediment Barrier | LF | 3481
4 | 104-11 | Floating Turbidity Barrier | LF | 27
5 | 104-18 | Inlet Protection System | EA | 1
6 | 110-1-1 | Clearing & Grubbing | AC | 3.6
7 | 120-1 | Regular Excavation | CY | 30
8 | 120-4 | Subsoil Excavation | CY | 10
9 | 120-6 | Embankment | CY | 30
10 | 125-1 | EXCAVATION FOR STRUCTURES (BRIDGE) | CY | 35
11 | 125-3 | SELECT BEDDING MATERIAL (BRIDGE) | CY | 7
12 | 339-1 | Miscellaneous Asphalt Pavement | TN | 6
13 | 400-2-2 | Conc Class Class II, End Walls | CY | 25
14 | 400-4-5 | CONC CLASS IV, SUBSTRUCTURE (BRIDGE) | CY | 20.3
15 | 415-1-5 | REINF STEEL- SUBSTRUCTURE (BRIDGE) | LB | 1336
16 | 430-175-115 | Pipe Culvert, Optional Material, Round, 15" S/CD | LF | 230
17 | 430-175-118 | Pipe Culvert, Optional Material, Round, 18" S/CD | LF | 233
18 | 430-175-236 | Pipe Culvert, Opt Material, Other Shape -29"x45" | LF | 8
19 | 430-536-102 | Straight Concrete Endwalls, 36", Single, 0 Degrees, Elliptical | EA | 2
20 | 430-530-100 | Straight Concrete Endwalls, 30", Single, 0 Degrees,Round | EA | 2
21 | 430-982-123 | Mitered End Section, Optional Round, 15" CD | EA | 2
22 | 430-982-125 | Mitered End Section, Optional Round, 18" CD | EA | 3
23 | 455-112-14 | AUGER GROUTED PILE, 14" (BRIDGE) | LF | 120
24 | 455-119-101 | STATIC LOAD TEST(BRIDGE) | EA | 1
25 | 460-5 | PREFABRICATED ALUMINUM PEDESTRIAN BRIDGE (95' x 6' Interior Width) | EA | 1
26 | 515-1-2 | Pipe Handrail - Guiderail, Aluminum | LF | 64
27 | 522-1 | Concrete Sidewalk 4" Thick, including HC Ramps | SY | 1828
28 | 522-2 | Concrete Sidewalk and Driveways, 6" Thick | SY | 150
29 | 527-2 | Detectable Warnings | SF | 50
30 | 570-1-2 | Performance Turf, Sod | SY | 12890
31 | 530-3-4 | Riprap, Rubble, F&I, Ditch Lining | TN | 20
32 | 530-74 | Bedding Stone | TN | 12
33 | 536-1-0 | Guardrail - Roadway, General TL-3 w/ end treatment | LF | 171
34 | 700-1-11 | Single Post Sign, F&I Ground Mount, Up To 12 SF | EA | 1
35 | 711-11-123 | Thermoplastic, Standard, White, Solid, 12" For Crosswalk | LF | 520
36 | 711-11-125 | Thermoplastic, Standard, White, Solid, 24" For Stop Line | LF | 34
37 | MC4 | Boardwalk | SF | 2121
38 | MC7 | PVC Fence and Gates (Sugar Creek Country Club) | LS | 1
39 | MC8 | Drop Inlet | EA | 2
40 | MC9 | Remove Existing MES/Connect to Existing Pipe | EA | 5
Subtotal (Sidewalk & Bridge) | [5 empty] | 0
II. Forcemain (Utilities)
1 |  | Asphalt Pavement Restoration
1.01 |  | Base & Resurface | SY | 40
1.02 |  | Mill & Resurface | SY | 185
2 |  | PVC (C-900, DR-18)
2.1 |  | 4" PVC | LF | 235
2.2 |  | 8" PVC (Casing) | LF | 18
3 |  | Ductile Iron Fittings
3.1 |  | 4" 45-Degree Bend | EA | 12
4 |  | Pipe Joint Restraints (4") | EA | 20
5 |  | Plug Valve (4") | EA | 3
6 |  | Air Release Valve Assembly, (Above Ground) | EA | 1
7 |  | Air Release Valve Assembly, (Waterway Canal Crossing) | EA | 1
8 |  | Utility Pipe - Remove & Dispose | LF | 235
9 |  | Sewage Disposal-Pumper Truck | LS | 1
10 |  | Traffic Control Plan | LS | 1
11 |  | Record Drawing | LS | 1
Subtotal (Forcemain Utilities) | [5 empty] | 0
Sections I, II Construction Total | [5 empty] | 0
CONTRACT CONTINGENCY WORK (USED ONLY WITH COUNTY APPROVAL) |  |  |  |  | 10% | 0
TOTAL BID "B" SECTIONS I, II WITH CONTINGENCY - BASED ON COMPLETITION TIME OF 360 CALENDAR DAYS | [5 empty] | 0
Bidder Name:___________________________________
Authorized Signature:____________________________