## Sheet1
BID FORM
PHASE II REAPIRS TO LAKE MANATEE DAM
BID "A" BASED ON COMPLETION TIME OF 600 CALENDAR DAYS
Task Pay Item Number | Description | Estimated Quantity | Unit | UNIT PRICE | TOTAL BID PRICE
100 | Mobilization
101 | Pre-Mobilization Activities (Construction Submittals….) | 1 | LS |  | 0
102 | Utility Locates | 1 | LS |  | 0
103 | Laydown and Setup | 1 | LS |  | 0
104 | Office Set-Up, Maintenance and Operation | 1 | LS |  | 0
105 | Erosion and Sediment Control Best Management Practices | 1 | LS |  | 0
106 | Temporary Downstream Access Road | 1 | LS |  | 0
107 | Temporary Boat/Barge Dock | 1 | LS |  | 0
108 | General Conditions | 1 | LS |  | 0
109 | Permits, Bonding, etc. | 1 | LS |  | 0
MOBILIZATION SUBTOTAL= |  |  |  |  | 0
200 | Void Filling
201 | Demonstration Project | 1 | LS |  | 0
202 | Production – Downstream Apron | 1 | LS |  | 0
203 | Production – Stilling Basin | 1 | LS |  | 0
VOID FILLING SUBTOTAL= |  |  |  |  | 0
300 | Downstream Channel Repairs
301 | Site Preparation (rip rap removal, excavation, engineered fill) | 1 | LS |  | 0
302 | Existing Apron Slab Preparation | 1 | LS |  | 0
303 | Reinforcement, Miscellaneous Metals, Expansion Joints, Sealant and Waterstop | 1 | LS |  | 0
304 | Form, Pour and Cure Downstream Concrete Apron Overlay | 1 | LS |  | 0
305 | Cast-in-Place Concrete Stairs | 1 | LS |  | 0
306 | Concrete Stilling Basin Repairs (Skim Coat on End sill) | 1 | LS |  | 0
307 | Training Wall Repairs | 1 | LS |  | 0
308 | Demolition and Abandonment of Miscellaneous Metals and Drains | 1 | LS |  | 0
309 | Ogee Repairs (Downstream and Upstream) | 1 | LS |  | 0
DOWNSTREAM CHANNEL REPAIRS SUBTOTAL= |  |  |  |  | 0
400 | Downstream Pressure Relief System
401 | Vertical Relief Wells | 1 | LS |  | 0
402 | End Sill Relief Wells | 1 | LS |  | 0
DOWNSTREAM PRESSURE RELIEF SYSTEM SUBTOTAL= |  |  |  |  | 0
500 | Encase Spillway with Seepage Barrier
501 | Construction Grading | 1 | LS |  | 0
502 | Sheet Piling Including Concrete Cap and Handrail Installation | 1 | LS |  | 0
503 | Deep Soil Mixing (Test Sections, Final Design Approval, F&I), Assume 10% Portland Cement and 5% Bentonite by Weight | 1 | LS |  | 0
504 | Jet Grouting (Test Sections, Final Design Approval, F&I), Assume 10% Portland Cement and 5% Bentonite by Weight | 1 | LS |  | 0
505 | Concrete Slab on Grade Installation | 1 | LS |  | 0
506 | Final Grading and Restoration | 1 | LS |  | 0
ENCASE SPILLWAY WITH SEEPAGE BARRIER SUBTOTAL= |  |  |  |  | 0
600 | Approach Channel Repairs
601 | Installation of Combi-Wall North and South Embankments | 1 | LS |  | 0
602 | Complete Demolition and Removal of Slope Paving and Soldier Pile Wall and Lagging | 1 | LS |  | 0
603 | Removal, Abandonment and Grouting of Monitoring Wells and Drains | 1 | LS |  | 0
604 | Excavation of Embankments North and South of the Spillway and in Approach Channel Including Removal of Jet Grout Spoils, Organics and Other Debris | 1 | LS |  | 0
605 | Removal of Grout Spoils from Approach Slab and Approach Wall Footings | 1 | LS |  | 0
606 | Install Sheet Pile and Combi-Wall System with Structural Bracing for Containment Area (Cofferdam) | 1 | LS |  | 0
607 | Install Dewatering Wells and Grout Plugs in Containment Area (Cofferdam) | 1 | LS |  | 0
608 | Partial Dewater of Containment Area (Cofferdam). Contractor May Fully Dewater at Their Discretion. | 1 | LS |  | 0
609 | Fully Dewater Containment Area (Cofferdam) for Minimum 30 Consecutive Days | 1 | LS |  | 0
610 | Complete Approach Slab Repairs | 1 | LS |  | 0
611 | Complete Approach Wall Repairs | 1 | LS |  | 0
612 | Flood Containment Area and Cut Sheet Pile Along Approach Walls and Combi-Wall Along Approach Slab | 1 | LS |  | 0
613 | Install Secondary Seal on Approach Wall Footings and Concrete Cap on Combi-Wall Along Approach Slab | 1 | LS |  | 0
614 | Backfill Around Approach Walls with Engineered Fill to Achieve Final Grades | 1 | LS |  | 0
615 | Install Continuous Reinforced Concrete Cap on Combi-Wall along North and South Embankments and Restore Grade and Slope Paving | 1 | LS |  | 0
616 | Install Riprap to Final Grade | 1 | LS |  | 0
617 | Placement of Watertight Slab on Grade on Embankment | 1 | LS |  | 0
618 | Install Handrail | 1 | LS |  | 0
APPROACH CHANNEL REPAIRS SUBTOTAL= |  |  |  |  | 0
700 | Stoplog Guide and Tainter Gate Rehabilitation
701 | Stoplog Guide Repairs | 1 | LS |  | 0
702 | Tainter Gate Repairs | 1 | LS |  | 0
703 | Threshold Replacement | 1 | LS |  | 0
704 | Course Screen Chamber - Concrete Repairs | 1 | LS |  | 0
705 | Course Screen Chamber Miscellaneous Metal Removal/Refurbishment/Coating | 1 | LS |  | 0
706 | 48" Pipe Inspection | 1 | LS |  | 0
STOPLOG GUIDE AND TAINTER GATE REHABILITATION SUBTOTAL= |  |  |  |  | 0
800 | Upstream Soil Cement Refurbishment
801 | Uniform Section Mat Test Section | 1 | LS |  | 0
802 | Concrete Slope Pavement Test Section | 1 | LS |  | 0
803 | Spot Repair Test Section | 1 | LS |  | 0
804 | Full Depth Soil Cement Test Section | 1 | LS |  | 0
805 | Spot Repair at End of Flume | 1 | LS |  | 0
UPSTREAM SOIL CEMENT REFURBISHMENT SUBTOTAL= |  |  |  |  | 0
900 | Mechanical Upgrade
901 | Replace Electric Motors | 1 | LS |  | 0
902 | Replace Gear Boxes | 1 | LS |  | 0
903 | Replace Instrumentation and Controls | 1 | LS |  | 0
MECHANICAL UPGRADE SUBTOTAL= |  |  |  |  | 0
1000 | Miscellaneous Improvements
1001 | Laybys | 1 | LS |  | 0
1002 | Concrete Deck Repairs | 1 | LS |  | 0
1003 | New Deck Paint: Sand Blast, Remove Rust, Primer and Paint | 1 | LS |  | 0
1004 | Add Safety Ladders | 1 | LS |  | 0
1005 | Add/Replace Handrails | 1 | LS |  | 0
1006 | Skim Coat Over Piers | 1 | LS |  | 0
1007 | Boat Launch Improvements | 1 | LS |  | 0
1008 | Bridge Repairs | 1 | LS |  | 0
MISCELLANEOUS IMPROVEMENTS SUBTOTAL= |  |  |  |  | 0
1100 | Demobilization
1101 | Full Depth Asphalt Milling and Asphalt Pavement | 1 | LS |  | 0
1102 | Punchlist Inspection | 1 | LS |  | 0
1103 | Restoration of Laydowns | 1 | LS |  | 0
1104 | Final Cleanup | 1 | LS |  | 0
1105 | Closeout Manuals / Submittals | 1 | LS |  | 0
1106 | Red-Line Construction Drawings | 1 | LS |  | 0
1107 | Borrow Area Reclamation | 1 | LS |  | 0
DEMOBILIZATION SUBTOTAL= |  |  |  |  | 0
| TOTAL BASE BID "A"- Based on Completion Time of 600 Calendar Days |  |  |  | 0
| CONTRACT CONTINGENCY WORK (USED ONLY WITH COUNTY APPROVAL) |  |  | 10% | 0
| TOTAL OFFER FOR BID "A" with Contract Contingenct- Vased on Completion Time of 600 Calendar Days |  |  |  | 0
THE FOLLOWING PAY ITEMS ARE INTENDED TO ESTABLISH UNIT RATES FOR UNFORESEEN CIRCUMSTANCES DURING THE CONTRACT PERIOD, AND WILL NOT BE UTILIZED TO DETERMNINE CONTRACT AWARD. UNIT PRICCES SHALL INCLUDE ALL LABOR, MATERIAL, AND EQUIPENT REQUIRED.
1200
Task Number | Description | Estimated Quantity | Unit | Total Unit Price | Total Bid Price
A
1 | Standby Rate
| a. Unmanned Equipment Rates | 1 | Hour |  | 0
| b. Earthwork Equipment Rates | 1 | Hour |  | 0
| c. Jet Grout Column Equipment Rates | 1 | Hour |  | 0
| d. Soil-Mixed Column Equipment Rates | 1 | Hour |  | 0
| e. Cofferdam Equipment Rates | 1 | Hour |  | 0
| f. Dive Team | 1 | Hour |  | 0
| g. Void Filling Equipment Rates | 1 | Hour |  | 0
2 | Emergency Demobilization
| a. Demobilization | 1 | LS |  | 0
| b. Site Monitoring | 5 | Day |  | 0
| c. Standby rate | 5 | Day |  | 0
| d. Mobilization | 1 | LS |  | 0
3 | Full Dewatering for Upstream Inspection | 1 | LS |  | 0
4 | Installation of new Monitoring Wells and Instrumentation and Controls | 1 | LS |  | 0
5 | 48-inch Pipe Repair (In Situ-Form or equal) | 1 | LS |  | 0
6 | Extra Jet Grout Columns (4-ft diameter), per length of wall | 1 | LF |  | 0
7 | Extra Jet Grout Columns (8-ft diameter) per length of wall | 1 | LF |  | 0
8 | Extra Combi-Wall (Choose the total length of 1 pipe pile and sheet pile section) | 1 | LF |  | 0
9 | Extra Concrete Surface Repairs | 1 | SF |  | 0
10 | Extra Sheet Pile Wall | 1 | SF |  | 0
11 | Extra Deep Soil Mix Columns (3-ft diameter), per length of wall | 1 | LF |  | 0
12 | Placing Select Engineered Fill (in-the-dry) | 1 | CYD |  | 0
13 | Placing Select Engineered Fill (through the water column) | 1 | CYD |  | 0
14 | Expansion Joint Replacement | 1 | LF |  | 0
15 | Excavation and Disposal of Unsuitable Material | 1 | CYD |  | 0
16 | Reinforcing steel locating services (GPR or similar) | 1 | Day |  | 0